NGAO System Design Phase: Work Scope Planning Sheet

WBS Element Title:		NGAO System Architecture Definition

WBS Element Number:		3.1.3

Work Package Lead:		Richard Dekany

Work Package Participants:	Bauman, Gavel, Flicker, Neyman, Velur, Wizinowich

Work Scope

WBS Dictionary Entry: 	Produce Baseline NGAO System Architecture and Program Scope in consideration of input from the system/science requirements, performance budgets and trade studies, and iterate with these efforts.  Provide top-level guidance on architectural choices that meet the requirements, in order to allow the designs of the major systems (AO system, LGS facility, science operations and science instruments) to proceed.  Document the system architecture considerations, trade-offs and decisionsin support of the system design manual.

Inputs:	System Requirements Document Rev 2.0

Detailed NGAO Observing Scenario Use Cases

The set of WBS 3.1.1 Performance Budget Tools and Reports

Numerous WBS 3.1.2 Trade Study Reports

Draft Operational Requirements Functional Requirements

Science Instrument Priorities (updated from 6/06 proposal ranking)

On-going Science Team Feedback (via in particular Claire)

Products:	Documentation of the architecture selection process and selection criteria
System Design Manual v1.0
Functional Requirements Document v1.0 for the AO and laser systems

Initial subsystem cost estimates

Technical risk analysis v1.0

Methodology:			Develop subsystem selection process and selection criteria

Review potential top-down architectures [All day meeting.]

Keck 1 upgrades

Large FoV Relay, instruments, d-IFU

Small FoV Relay(s), instrument d-IFU

AM2 / no AM2

Review constraints from SRD

KI support

Science instrument priorities (updated from 6/06 proposal ranking)

Define a set of NGAO functions to be supported by the NGAO architecture (see Table 1 as an example.)

The definition of system functions should follow the System Requirements Document and the collection of NGAO Observing Scenario Use Cases.

Make initial flow-down of system level performance requirements onto this set of system functions

Example:  Acquire TT NGS – over YYY arcsec FoV (driven by EE vs. Sky Coverage requirement for Extended Groth Strip.)

Define subsystem evaluation criteria

Suggest candidate subsystems that can perform these functions

Rank order candidate subsystems in terms of performance, cost, risk, reliability, maintainability, and system expandability

Identify constraints and conditions on subsystem candidates that justify this ranking

Example:  Approach A is only preferred under conditions B, C, and D…

Define architecture evaluation criteria

Propose candidate architectures as combinations of subsystems having top ranking determined above.

Document functional requirements v1.0 for AO and laser systems.

Rank order candidate architectures in terms of performance, cost, risk, reliability, maintainability, and system expandability.

Solicit external input as appropriate (e.g. latest guidance from Advancement Office)

Identify likely funding levels ($15M, $25M, $35M, $45M ‘baskets’?)

Collect architecture elements into prioritized, initial cost estimated program; input into SDM v1.0

Document technical risk analysis.

Timeline:	This work package will be executed by a small team (6 persons) working on a regular Monday afternoon meeting cadence (2-3 hour Monday meeting followed by ~10 hrs of additional work per person per week.)

All meetings will be by video, with as frequent collection of team members in one location as possible (suggest Monday/Tuesday meetings for Bauman, Dekany, Gavel, Velur when possible)

May 24, 2007 	Team Kickoff Meeting

Review WBS 3.1.3 Plan

Review Top-Level Architectures

May 29, 2007	Adopt relevant list of system functions

Assign functions for candidate subsystems

June 5, 2007	Assign initial performance requirements to functions

First batch candidate subsystems described

(note constraint of Dekany, Velur traveling 6/6-6/20)

June 12, 2007	Second batch candidate subsystems described

June 19, 2007	No meeting (OSA Week)

June 26, 2007	Initial subsystems ranking including cost basis

July 9-13, 2007	Architecture Retreat (UCSC)

Review of ranked subsystems role in top-down architectures

Brainstorming on new subsystem combinations

Initial architecture system-level cost estimation (parametric)

Drafting of initial Subsystems Functional Requirements Documents

July 24, 2007	Initial architecture prioritized ranking

Identify key outstanding issues to address

July 31, 2007	Review resolution of key issues, collect into Risk Register

Aug 9, 2007	Incorporate external considerations

Formally adopt baseline architecture and program scope

Assign SDM v1.0 writing assignments

Aug 16, 2007	Initial draft sections of SDM v1.0 due to SDM Editor

Aug 23, 2007	Final SDM section input, editorial review

Aug 30, 2007	Initial release of SDM v1.0 (WBS 3.6.1)

Initial release of Technical Risk Analysis v1 (WBS 3.1.3.4)

Estimate of effort:		3.1.3.1 	Candidate Subsystems (subtotal = 480 hrs)

        - Define Candidate Subsystems = 228 hr (6 x 12 x 2 + 24 add’l management (keeping things moving, Dekany) + 60 consultations outside 3.1.3. team)

        - Subsystem Performance Evaluation = 72 hrs (3 x 12 x 2, Dekany, Gavel, Wizinowich)

        - Subsystem Cost Evaluation = 72 hr (3 x 12 x 2, Bauman, Neyman, Velur)

        - Subsystem Risk Analysis = 36 hr (3 x 12 x 1, Bauman, Neyman, Velur)

        - Organize Candidate Subsystems = 72 (6 x 12 x 1)

3.1.3.2  Candidate Architectures (subtotal = 586 hrs)

3.1.3.2.1	Define Candidate Architectures = 358 hr (6 x 12 x 2 + 16 add’l management (keeping things moving, Dekany) + 30 consultations outside 3.1.3. team + 6 x 20 architecture retreat + 6 x 8 one add’l face-to-face mtg)

3.1.3.2.2	Architecture Performance Evaluation = 72 hrs (3 x 12 x 2, Dekany, Gavel, Wizinowich)

3.1.3.2.3	Architecture Cost Evaluation = 72 hr (3 x 12 x 2, Bauman, Neyman, Velur)

3.1.3.2.4	Architecture Risk Analysis = 36 hr (3 x 12 x 1, Bauman, Neyman, Velur)

3.1.3.2.5	Adopt Baseline Architecture = 48 hr (6 x 8 x 1)

3.1.3.3	Functional Requirements (subtotal = 400 hrs)

3.1.3.3.1	Draft Functional Requirements Document  = 20 hr Wizinowich

3.1.3.3.2	AO System Functional Requirements (subtotal = 240)

3.1.3.3.2.1		AO Functional Requirements Ver 1 = 160 hr (5 x 8 x 4 weeks, Johansson, Dekany, Gavel, Neyman, Wizinowich)

3.1.3.3.2.2		AO Functional Requirements Ver 2 = 80 hr (5 x 8 x 2 weeks, Johansson, Dekany, Gavel, Neyman, Wizinowich)

3.1.3.3.3	Laser System Requirements (subtotal = 140 hr)

3.1.3.3.3.1		Laser Functional Requirements Ver 1 = 92 hr (3 x 8 x 4 weeks, Chin, Velur, Johansson)

3.1.3.3.3.2		Laser Functional Requirements Ver 2 = 48 hr (3 x 8 x 2 weeks, Chin, Velur, Johansson)

      - Technical Risk Analysis (subtotal = 40 hrs)

        - Technical Risk Analysis Ver 1 = 20 hrs (Neyman)

        - Technical Risk Analysis Ver 2 = 20 hrs (Neyman)

(Editorial labor for SDM writing contained in 3.6.1)

Grand Total = 1,506 hours

Approvals:

| Control | Name | Date |
| --- | --- | --- |
| Authored by: | Richard Dekany | 5/16/07 |
| Approved by: |  |  |

Appendix:	▼	Example NGAO Functions

▼		Configure

Power On/Off

Record AO Status

Configure Calibration Source

Configure Pupil Sampling

▼		Configure HO Loops

Configure HO WFS Transmissions

Configure HO WFS Camera Settings

Configure HO WFS Servo Loops

Configure HO WFS Reconstructor

▼		Configure TT Loops

Configure TT WFS Transmissions

Configure TT WFS Camera Settings

Configure TT WFS Servo Loops

▼		Configure T WFS Loop

Configure T WFS Transmissions

Configure T WFS Camera Settings

Configure T WFS Servo Loops

▼		Calibrate

Calibrate WFS Zero Points

▼			Calibrate WFS Backgrounds

Dither Laser Wavelength

Calibrate WFS Centroid Gain Curves

Register DM and WFS Pupil Sampling

Measure Cn2(h,t)

Generate Reconstructors

▼		Acquire

▼			Acquire Guide Stars

▼			NGS mode

Acquire HO WFS NGS

Acquire calibration source

▼			LGS mode

Project Lasers

Compensate Uplink(s)

Acquire HO WFS LGS

Acquire TT WFS NGS's

Acquire T WFS NGS

Acquire Science Target(s)

▼			Sense Wavefronts

Sense Tip/Tilt

Sense Focus

▼				NGS Mode

Sense HO NGS Wavefront

▼				LGS Mode

Sense HO LGS Wavefront

Sense Truth Wavefront

▼				Compensate Wavefronts

Compensate HO Wavefronts

Record AO Telemetry

Offload DM’s

Compensate Tip/Tilt

Compensate Atmospheric Refraction

Compensate Field Rotation

Apply Static HO Corrections

Apply Static Tip/Tilt Corrections

▼			Science

Relay Science Light

Dither Science Light

Measure Science Light

Record Observational Parameters

Report Performance to Operator

▼			System Integration and Test

Calibrate WFS's

Calibrate DM's

Align Optical Relay

Align WFS's

Register DM's to One Another

Register DM's to WFS's

Check Vignetting

Table 1.  Example function definitions for NGAO Observations.

# Comments

I don't currently have Ralf on any of the system architecture tasks.  Should I?

I'm not sure of what this means and/or if it is appropriate as part of this task.

I believe that we only have one of these so far.  What is the impact of not having more?  Do we need to aggressively get a couple more and if so by when?  Do we need to have some of David's time for this WBS?

Can you either identify which WBS element each of these methodology items falls under and recommend a new WBS structure for me to include in the MS Project Plan if necessary.

I have two project meetings on Monday's between 2 & 4 pm PDT that I cannot easily move.  Also Monday pm twice a month we have senior management meetings.  Another day would be better for me.  Tuesday?

Should I cancel Team Meeting #7 currently scheduled for May 30 or move it to a new date?

Who will lead this meeting?  Obviously can't assign much to RD or VV during this period.

I will be on vacation from July 16 to 27.

Currently 9/4 in v25 of project plan.

I need to know this breakdown at the next level down in the WBS in order to put it into the MS Project plan.  I also don't know who the consultation hours should be applied to.  Can you look at v25 and tell me what you would like changed?

Previous total was 510h vs new total of 612h.

Previous total was 905h vs new total of 868h.  However, you are not including WBS 3.1.3.2.7 System Architecture v2 which I had listed as 70h.

Previous was 25h.  You have separately recommended increasing to 60h.

Total increase of 55 or 90h.

I have not looked at this yet.