NGAO System Design Phase: Work Scope Planning Sheet v2.0

WBS Element Title:		NGAO System Architecture Definition

WBS Element Number:		3.1.3

Work Package Lead:		Richard Dekany

Work Package Participants:	Bauman, Gavel, Flicker, Neyman, Velur, Wizinowich

Work Scope

WBS Dictionary Entry: 	Produce Baseline NGAO System Architecture and Program Scope in consideration of input from the system/science requirements, performance budgets and trade studies, and iterate with these efforts.  Provide top-level guidance on architectural choices that meet the requirements, in order to allow the designs of the major systems (AO system, LGS facility, science operations and science instruments) to proceed.  Document the system architecture considerations, trade-offs and decisionsin support of the system design manual.

Inputs:	System Requirements Document Rev 2.0

Detailed NGAO Observing Scenario Use Cases

The set of WBS 3.1.1 Performance Budget Tools and Reports

Numerous WBS 3.1.2 Trade Study Reports

Draft Operational Requirements Functional Requirements

Science Instrument Priorities (updated from 6/06 proposal ranking)

On-going Science Team Feedback (via in particular Claire)

Products:	Documentation of the architecture selection process and selection criteria
System Design Manual v1.0
Functional Requirements Document v1.0 for the AO and laser systems

Initial subsystem cost estimates

Technical risk analysis v1.0

Methodology:	This work package will be executed by a small team (6 persons) working on a regular Monday afternoon meeting cadence (2-3 hour Wednesday meeting followed by ~10 hrs of additional work per person per week.)

All meetings will be by video, with as frequent collection of team members in one location as possible (suggest Wednesday face-to-face meetings for Bauman, Dekany, Gavel, Velur when possible)

Work Plan:			May 24, 2007

Review WBS 3.1.3 Plan

Review Constraints from SRD

KI support

Science instrument priorities (updated from 6/06 proposal ranking)

Review potential top-down architectures

Keck 1 upgrades

Large FoV Relay, instruments, d-IFU

Small FoV Relay(s), instrument d-IFU

AM2 / no AM2

May 30, 2007

Develop subsystem selection process and selection criteria

Examples: Cost, cost risk, schedule risk, reliability, maintainability, vendor options, and system expandability

Discuss and adopt relevant list of system functions (see Table 1 for an example starting point)

The definition of system functions should follow the System Requirements Document and the collection of NGAO Observing Scenario Use Cases.

Assign functions to team members, who will suggest, develop, and later rank candidate subsystems (resources include KAON library, literature, experience)

Schedule flow-down interviews with subsystem assignees

Tuesday, June 5, 2007 (Velur traveling)

First batch candidate subsystems described by assignees

Includes initial evaluation against selection criteria

Identify constraints and conditions on subsystem candidates that justify this ranking

Example:  Subsystem A is only preferred under conditions B, C, and D.  (Could be other subsystem choices or certain risk mitigation successes.)

Assign development of subsystem cost estimate basis template (for later ease of estimation)

June 13, 2007 (Velur and Dekany traveling)

Second batch candidate subsystems described by assignees

Includes initial evaluation against selection criteria

Includes cost estimate basis

June 20, 2007 – No Meeting (OSA conflict)

June 27, 2007

Review and adopt subsystem candidate rankings

Address questions raised during initial evaluations

Define architecture evaluation criteria

Examples: Cost, cost risk, schedule risk, performance, reliability, maintainability, vendor options, and system expandability

July 9-13, 2007 – Architecture Retreat

Propose candidate architectures as combinations of subsystems having top ranking determined above.

Include original top-down architectures

Brainstorm on new subsystem combinations

Develop architecture system-level cost estimation (parametric)

Assign and begin drafting initial Subsystems Functional Requirements Documents

July 24, 2007

Discuss and generate initial rank order candidate architectures in terms of architecture selection criteria.

Identify and assign key outstanding architecture issues to address

July 31, 2007

Review resolution of key issues, collect into Risk Register

Solicit external input as appropriate (e.g. latest guidance from Advancement Office)

Aug 9, 2007

Review external considerations

Collect architecture elements into prioritized, initial cost estimated program; input into SDM v1.0

Formally adopt baseline architecture and program scope

Assign SDM v1.0 writing assignments

Aug 16, 2007

Initial draft sections of SDM v1.0 due to SDM Editor

Aug 23, 2007

Final SDM section input, editorial review

Aug 30, 2007

Initial release of SDM v1.0 (WBS 3.6.1)

Initial release of Technical Risk Analysis v1 (WBS 3.1.3.4)

Estimate of effort:		3.1.3.1 	Candidate Subsystems (subtotal = 480 hrs)

        - Define Candidate Subsystems = 228 hr (6 x 12 x 2 + 24 add’l management (keeping things moving, Dekany) + 60 consultations outside 3.1.3. team)

        - Subsystem Performance Evaluation = 72 hrs (3 x 12 x 2, Dekany, Gavel, Wizinowich)

        - Subsystem Cost Evaluation = 72 hr (3 x 12 x 2, Bauman, Neyman, Velur)

        - Subsystem Risk Analysis = 36 hr (3 x 12 x 1, Bauman, Neyman, Velur)

        - Organize Candidate Subsystems = 72 (6 x 12 x 1)

3.1.3.2  Candidate Architectures (subtotal = 586 hrs)

3.1.3.2.1	Define Candidate Architectures = 358 hr (6 x 12 x 2 + 16 add’l management (keeping things moving, Dekany) + 30 consultations outside 3.1.3. team + 6 x 20 architecture retreat + 6 x 8 one add’l face-to-face mtg)

3.1.3.2.2	Architecture Performance Evaluation = 72 hrs (3 x 12 x 2, Dekany, Gavel, Wizinowich)

3.1.3.2.3	Architecture Cost Evaluation = 72 hr (3 x 12 x 2, Bauman, Neyman, Velur)

3.1.3.2.4	Architecture Risk Analysis = 36 hr (3 x 12 x 1, Bauman, Neyman, Velur)

3.1.3.2.5	Adopt Baseline Architecture = 48 hr (6 x 8 x 1)

3.1.3.3	Functional Requirements (subtotal = 400 hrs)

3.1.3.3.1	Draft Functional Requirements Document  = 20 hr Wizinowich

3.1.3.3.2	AO System Functional Requirements (subtotal = 240)

3.1.3.3.2.1		AO Functional Requirements Ver 1 = 160 hr (5 x 8 x 4 weeks, Johansson, Dekany, Gavel, Neyman, Wizinowich)

3.1.3.3.2.2		AO Functional Requirements Ver 2 = 80 hr (5 x 8 x 2 weeks, Johansson, Dekany, Gavel, Neyman, Wizinowich)

3.1.3.3.3	Laser System Requirements (subtotal = 140 hr)

3.1.3.3.3.1		Laser Functional Requirements Ver 1 = 92 hr (3 x 8 x 4 weeks, Chin, Velur, Johansson)

3.1.3.3.3.2		Laser Functional Requirements Ver 2 = 48 hr (3 x 8 x 2 weeks, Chin, Velur, Johansson)

      - Technical Risk Analysis (subtotal = 40 hrs)

        - Technical Risk Analysis Ver 1 = 20 hrs (Neyman)

        - Technical Risk Analysis Ver 2 = 20 hrs (Neyman)

(Editorial labor for SDM writing contained in 3.6.1)

Grand Total = 1,506 hours

Approvals:

| Control | Name | Date |
| --- | --- | --- |
| Authored by: | Richard Dekany | 5/16/07 |
| Approved by: |  |  |

Appendix:	▼	Example NGAO Functions

▼		Configure

Power On/Off

Record AO Status

Configure Calibration Source

Configure Pupil Sampling

▼			Configure HO Loops

Configure HO WFS Transmissions

Configure HO WFS Camera Settings

Configure HO WFS Servo Loops

Configure HO WFS Reconstructor

▼			Configure TT Loops

Configure TT WFS Transmissions

Configure TT WFS Camera Settings

Configure TT WFS Servo Loops

▼			Configure T WFS Loop

Configure T WFS Transmissions

Configure T WFS Camera Settings

Configure T WFS Servo Loops

▼		Calibrate

Calibrate WFS Zero Points

▼			Calibrate WFS Backgrounds

Dither Laser Wavelength

Calibrate WFS Centroid Gain Curves

Register DM and WFS Pupil Sampling

Measure Cn2(h,t)

Generate Reconstructors

▼		Acquire

▼			Acquire Guide Stars

▼			NGS mode

Acquire HO WFS NGS

Acquire calibration source

▼			LGS mode

Project Lasers

Compensate Uplink(s)

Acquire HO WFS LGS

Acquire TT WFS NGS's

Acquire T WFS NGS

Acquire Science Target(s)

▼			Sense Wavefronts

Sense Tip/Tilt

Sense Focus

▼				NGS Mode

Sense HO NGS Wavefront

▼				LGS Mode

Sense HO LGS Wavefront

Sense Truth Wavefront

▼				Compensate Wavefronts

Compensate HO Wavefronts

Record AO Telemetry

Offload DM’s

Compensate Tip/Tilt

Compensate Atmospheric Refraction

Compensate Field Rotation

Apply Static HO Corrections

Apply Static Tip/Tilt Corrections

▼		Science

Relay Science Light

Dither Science Light

Measure Science Light

Record Observational Parameters

Report Performance to Operator

▼		System Integration and Test

Calibrate WFS's

Calibrate DM's

Align Optical Relay

Align WFS's

Register DM's to One Another

Register DM's to WFS's

Check Vignetting

Table 1.  Example function definitions for NGAO Observations.