NGAO System Design Phase: Work Scope Planning Sheet

WBS Element Title:	AO Real-time Controls

WBS Element Number:	3.2.5

Work Package Lead:	Don Gavel

Work Package Participants:	Erik Johansson, Mark Reinig

# Work Scope

WBS Dictionary Entry:

    - Real-time Control

- Based on system requirements, operations requirements, and error budgets, develop an architecture for the real-time controller, including both hardware and software configuration. Input to this process includes candidate wavefront sensing, tomography, tip/tilt, and DM control and signal processing algorithms as provided by the system engineering group as a result of trade studies. Design work includes specification of hardware interface requirements, hardware processor speed, data rate, and storage requirements, design of the data flow, design of the algorithm implementation software, and design of the diagnostic and telemetry streams. Work includes analysis and modeling of performance at the low-level of implementation, e.g. taking into account data transmission delays, processor delays, and data resolution.

      - RTC Architecture Analysis and Design Study

- Based on system requirements, operations requirements, and error budgets, develop an architecture for the real-time controller, including both hardware and software configuration. Input to this process includes candidate wavefront sensing, tomography, tip/tilt, and DM control and signal processing algorithms as provided by the system engineering group as a result of trade studies. Output of this process is an analysis of candidate architectures, simulations of expected real-time performance, and guidance (in the form of strawman designs) for the RTC software module definition and RTC hardware module definition tasks.

      - RTC Software Module Definition

- Given the architectural design and results of the RTC design study, specify the software development environment tools required (& analyze vendors of such), develop a software top level block diagram, define software data structures and data flow paths, define software command language for interface to the system controller/user interface, design diagnostic and telemetry streams, specify software module functions at a detailed level. Develop a real-time software implementation and test plan.

      - RTC Hardware Module Definition

- Given the architectural design and results of the RTC design study, perform a rough initial specification of the hardware platform (or platform options, through PDR phase), the hardware interfaces and the required cabling.  In consideration of real-time data flow and diagnostic/telemetry streams, determine the overall size, mounting, and power requirements. If specifying custom processor boards (likely, with a transputer/FPGA architecture) design the board layout in conformance with fab-house design rules, specify the component processors and all other components needed to enable assembly of the boards. Develop a hardware acceptance test plan. Specify test equipment needed.

Requirements:

# Inputs:

- Functional requirements documents

- NGAO System Architecture Definition (KAON 499)

- Science Requirements Summary spreadsheet

- Relevant outputs from the system engineering phase trade studies and performance budgets – as needed to fill in functional requirements iteratively

# Products:

# Revised WBS dictionary definitions for these task that is consistent with the scope of the system design phase (we see problems with providing overly specific details for the hardware at this early stage).

- A SW architecture design.

# A top-level block diagram showing the SW architecture of the RTC.

# A top-level data-flow diagram for the RTC, showing data paths, descriptions, sizes, and expected data rates.

# A draft of an interface control document describing all the SW interfaces of the RTC, both internal and external.

# A top-level description of all the RTC component SW modules.

# A diagram showing the partitioning of the RTC SW modules across the processing elements defined in WBS 3.2.5.1, 3.2.5.2, and 3.2.5.3.

# A block level context diagram showing how the RTC is connected to the rest of the AO system (this will be part of the ICD). This diagram will describe the data interface and will contain a description of electrical/electronic interfaces needed to support input/output.

# Inputs to appropriate sections of FRD version 2 (A revision of the functional requirements pertaining to the RTC.)

# A high-level description of the command, control, and status interfaces and functions of the RTC.

# A report summarizing all the above items. (***outline needed***)

# Inputs to the preliminary design phase work breakdown structure

# Inputs to the System Design Manual

# Methodology:

- From the functional requirements, system architecture definition, and error budgets for the various science cases, determine the basic processing requirements for real-time control. (2 MW)

- Considering all the subsystem interactions, develop a signal flow concept that can be supported at the required real-time rates. (2 MW)

- Work with the calibration, alignment, and acquisition teams to build in the appropriate hooks for diagnostics and telemetry of the real-time system (1.5 MW)

- Draft ICD and edit FRD. (3 MW)

# Estimate of effort:	Total 8.5 MW = 340 hours. The allocated amount is 340 hours (about 2 man-months) (refer to NGAO_system_design_personnel_v2.xls)

# Approvals:		340 hours

| Control | Name | Date |
| --- | --- | --- |
| Authored by: | Donald Gavel | 9/6/2007 rev: 10/10/2007 |
| Approved by: | WBS 3.2 Lead |  |
|  | NGAO EC Chair |  |