## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1: 06/03/06 - AB
12 - 14 June 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2006-06-12 |  |  |  | 20:05 | 21:01 | 17:39 | 4:33 | 5:29
1 | 8:00 | 12:00 |  | Install AO system & LLT |  |  |  |  | closed | zen |  | 1 | 4 |  | N | N
2 | 12:00 | 14:00 |  | Demo BTO control 1 |  |  |  |  | closed | slew | Demo open-loop alignment and control while slewing. | 2 | 2 | CS | N | HeNe
3 | 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
4 | 14:30 | 16:00 |  | Demo BTO control 1 |  |  |  |  | closed | slew | Demo open-loop alignment and control while slewing. | 2 | 1.5 | CS | N | HeNe
5 | 16:00 | 18:30 |  | Demo BTO control 2 |  |  |  |  | closed | slew | Demo control with Na laser on/off. | 1 | 2.5 | CS | N | Na
| 18:30 | 20:30 |  | dinner | [8 empty] | 2
6 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
7 | 21:00 | 23:00 |  | LLT boresighting |  |  |  |  | NGS | V=3 | Boresigh to 200". Check repeatability vs. elevation. | 1 | 2 | HP | N | N
8 | 23:00 | 24:00 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
9 | 24:00 | 25:00 |  | Laser polarization |  |  |  |  | LGS | zen | Measure effect of laser polarization on return. | 2 | 1 | CS | Y | Na
10 | 25:00 | 27:00 |  | LGS off-zenith acquisition |  |  |  |  | LGS | V=12 | Demonstrate LGS off-zenith acquisition procedure. | 1 | 2 | AB | N | Na
11 | 27:00 | 28:45 |  | LGS science demo observations |  |  |  |  | LGS | V=15 | Image one science target (V~15), no dithering. | 1 | 1.75 | AB | Y | Na
2006-06-13 |  |  |  | 20:06 | 21:02 | 17:42 | 4:33 | 5:29
12 | 12:00 | 14:00 |  | Measure UTT FSM noise |  |  |  |  | closed |  |  | 2 | 2 | MT | N | N
13 | 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
14 | 14:30 | 18:30 |  | contingency | [8 empty] | 4
| 18:30 | 20:30 |  | dinner | [8 empty] | 2
15 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
16 | 21:00 | 22:30 |  | Demo LOWFS dithering |  |  |  |  | NGS | V=8 | Demonstrate dithering with LOWFS on NGS. | 2 | 1.5 | JR | N | N
17 | 22:30 | 23:30 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
18 | 23:30 | 25:00 |  | HO loop performance optimization |  |  |  |  | LGS | V=12 | Optimize HO loop performance on LGS. | 2 | 1.5 | JR | Y | Na
19 | 25:00 | 27:00 |  | LGS science demo observations |  |  |  |  | LGS | V=15 | Image one science target (V~15), with dithering. | 1 | 2 | AB | Y | Na
20 | 27:00 | 28:45 |  | Performance vs. NGS magnitude |  |  |  |  | LGS | V<18 | Measure LGS performance on R~12,14,16,18 stars. | 2 | 1.75 | AB | Y | Na
2006-06-14 |  |  |  | 20:06 | 21:02 | 17:46 | 4:33 | 5:29
21 | 12:00 | 18:30 |  | contingency |  |  |  |  | closed |  |  | 2 | 6.5 |  | N | N
| 18:30 | 20:30 |  | dinner | [8 empty] | 2
22 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 1 | 0.5 | AB | N | N
23 | 21:00 | 22:00 |  | HOWFS-laser TT correlation |  |  |  |  | LGS | V=8 |  | 1 | 1 | MB | Y | Na
24 | 22:00 | 28:45 |  | contingency | [8 empty] | 6.75
NGS backup experiments
1 | 0:00 | 1:00 |  | Flatmap test |  |  |  |  | NGS | stars |  | 3 | 1 | CS | N | N
2 | 1:00 | 2:00 |  | Acquisition camera sensitivity |  |  |  |  | NGS | stars |  | 2 | 1 | AB | Y | N
3 | 2:00 | 4:00 |  | LOWFS bandwidth vs. NGS mag. |  |  |  |  | NGS | 8-18 |  | 2 | 2 | AB | Y | N