## actions
action | who | when | status | closure | comments
update PFI configuration with new information | braun | 2011-02-10 | closed
Provide feedback on review objectives by Thursday for first telecon | Kirk, Roger, Dave | 2011-10-13 | closed
Talk to Rick Denzin – proposal requirements for money from Caltech w/ japan as the original source | robin | 2011-10-14 | closed
Work w/ Rich on proposal preparation and identify schedule items to complete | robin | 2011-10-14 | closed
udpate review template | Robin | 2011-10-17 | closed
Comments/questions on technical design description & schedule to Mike/robin for Marseille meeting or next weeks telecon | all | 2011-10-18 | closed
pfi & positioner schedule update | robin/dave/mike | 2011-10-26 | closed
define bridge funding for JPL effort | robin | 2011-10-28 | closed | need cost inputs
proposal outline | robin | 2011-10-28 | closed |  | started w/ Mike's task plan
identify opportunities for schedule acceleration - identify 3/2014 milestones | robin | 2011-11-02 | closed | n/a
schedule feedback | dave, larry, roger, mike | 2011-11-29 | closed
comment on conceptual phase contract mod | rich | 2011-11-29 | closed | look to Japan to identify fastest path
request extended conceptual phase funding | robin | 2011-11-29 | closed | email 11/29
confirm process on request for bridge/full funding | robin | 2011-11-29 | closed | requested info email 11/29
provide list of items needed for the PFI | dave | 2011-12-01 | closed | email 11/30
submit request for requirements to the project/SE team | robin | 2011-12-01 | closed
cost inputs, preliminary | dave, larry, rich, mike | 2011-12-02 | closed
Schedule to produce review material | robin | 2011-12-05 | closed | sent out calender 'PFS Calender thru CoDR.xlsx' | udpate w/ Feb/March date
get ROM from New Scale | dave | 2012-01-17 | closed |  | discussion scheduled for 2/2
reconcile cabling costs | larry/dave/robin | 2012-01-17 | closed | written up in cost document
I&T cost estimate | rich | 2012-01-17 | closed |  | first version done. Needs more refinement
get positioner sw costs | robin | 2012-01-17 | closed
deliver/post updated SW block diagram | dekany | 2012-02-06 | closed
develop plan for having the design and analysis of the PFI structure elements started at JPL and fabrication and test done by ASIAA | bruno | 2012-02-10 | closed
solid model of the PFI allowable volume | shimono | 2012-02-10 | closed
Need to have a metrology system, preferably the metrology system, for pfi/positioned testing in Pasadena prior to delivery – include in assumptions in review package | Dave | first draft | closed
send report for first contract to IPMU (thru caltech) | robin |  | closed
request structure for design defintion documents - locations, control, owners, etc (from 7/26 se mtg) | robin | 2012-07-30 | closed |  | requested, discussions occurring
post - update and distribute PSF trade document and metrology system document | peter | 2012-07-31 | closed | posted on twiki
post on the twiki. presentation on fiber routing apporach and list interface features/requirements that are needed | roger | 2012-07-31 | closed | posted under system architecture
need LNA & project office inputs on size and interface info on strain relief box and connectors and recommendations on where these should be located | dave | 2012-08-16 | closed |  | in schedule rec/dels
post comments on Naoyuki's requirements document | all | 2012-08-03 | closed | submitted and reviewed w/ naoyuki
request instrument integration story board - (CIT-JPL provides PFI piece) | robin | 2012-08-03 | closed | requested via schedule items list to Management group
get baseline flow for microlens/fiber fabrication and integration - feeds into PFI integration storyboard | robin | 2012-08-04 | closed | requested via schedule items list to Management group
provide draft or storyboard of I&T flow - entire PFI I&T with focus on interface w/ POpt2 | dave | 2012-08-03 | closed | presented at collab mtg - posted on sumire
list deliverables for design transfer at PDR, include short description: ICDs, requirements, CAD model, prelim analysis, etc | Dave, Charlie | 2012-08-03 |  |  | part of bigger hand off/ working relationship documebt - robin
obtain the project response and request formal documentation from the SE group on the fiber routing approach | robin | 2012-08-05 | closed |  | now led by J. Gunn
include ICD PFI/fiber system in ICD list | charlie | 2012-08-10 | closed
model update | charlie | 2012-04-13 | closed
determine if the configuration can support the masking options for the PSF characterization (smith document option 3) | braun | 2012-04-15 | closed | done by asiaa
update icd list | charlie, larry | 2012-08-10 |  |  | mech section is updated
develop positioner specs for New Scale contract | Dave,Ron,Mike, charlie | 2012-07-26 | closed
review EAR guidelines | robin | 2012-07-26 | closed
Propose a test at JPL to assess the change in sky subtraction | mike | 2012-08-16 | closed | test proposed and fudning requested from Gerber
preliminary scheme for shutter | roger | 2012-08-10 |  |  | change to provide info on dots size, placement
draft approach for number, location, type of fiducial fibers | mike | 2012-08-25 | closed |  | draft out 8-23
determine if there's a requirement to be able to use the metrology system during the day | mike | 2012-08-16 | closed | mike has made a request to naoyuki that the metrology system can be used during the day
obtain the microlens system characterization/error budget to confirm mechanical approach to fiber integration and alignment and measurement | robin | 2012-08-16 | closed | requested via schedule items list to Management group
provide analysis on size and details on the dots option for the fiber mask | roger | 2012-08-29 | closed |  | just send whatever you already have
propose split on PDS system. Define needs | charlie | 2012-08-31 | closed | propose each subsystem has tehir own PDS and JPL only provides the psoitioner system
respond to ASIAA proposal on who does the power distribution system | robin | 2012-08-16 | closed |  | transferred to charlie
draft document on JPL/ASIAA work split before and after PDR (bugzilla action) | robin | 2012-08-23 |  | closed | sent out 8/23 for comments
provide example or template for SW requirements, PDR products | hrand | 2012-08-31 | closed
udpate and organize open issues list (requests to the project) | Robin | 2012-08-31 | closed
follow up on request for HSC documents - next management telecon | robin | 2012-08-31 | closed
update rec/dels for pfi & positioner | dave | 2012-08-10
Determine the sensitivity of the positioner bench – is additional cooling needed. | dave | 2012-09-01 |  |  | need requirements from the project - no extra cooling is needed if wfmos assumptions are still good
define the raster scan calibration process to help clarify the JPL/CIT role | dan | 2012-09-07 |  |  | work w/ roger
draft document that describes the software functions of the PFI system | peter | 2012-09-07
draft procedure of removal, maintenance & repair and re-installation of Cobra positioner module needs to be followed on a story board for further discussion. | dave | 2012-09-15 |  |  | project action item - need more info from LNA on connectors, etc
characterize positioner tilt | joel | 2012-09-15
get info on telescope connector to instrument - Circuit data sheet with wire size, conductor count, connector type, | ron | 2012-09-15 |  |  | discussed at collab meeting - may be to PFI
Rename the PFI sequencer | peter | 2012-09-19 |  |  | from sept mmr
Decide if its useful to use the current prototype testbed software to exercise any of the production software or if it just really makes sense to wait for the EM | Peter, hrand | 2012-09-26 |  |  | from sept mmr
Propose a transfer standard – a test that can be run often as a benchmark against an absolute measurement | mike | Dec 15 2012
throughput change with tilt, defocus | ron | 2012-09-17 |  |  | from norm
provide more details on fibers needed for the EM build | charlie | 2012-09-25
send model to LNA for cable wrap info after the 9/20 telecon w/ ASIAA | charlie/olivia | 2012-09-24
reconcile critical schedule items w/ schedule, update critical items. Included dels for ASIAA requested items | robin | 2012-09-26
udpate fixed fiducial fiber interace issues document | robin | 2012-09-27
schedule updates on V&V design thru V&V test equipment analysis, lines 175-184 on Aug 30 schedule | dan | 2012-09-26
review and update caltech rec-dels in the schedule | dan | 2012-09-26
schedule inputs for the FPGA task | larry | 2012-09-26