Keck Adaptive Optics Note 595

Next Generation Adaptive Optics:

Preliminary Design Phase Replan -- DRAFT

P. Wizinowich, R. Dekany, E. Johansson, D. Le Mignant

August 26, 2008

1. Introduction

The NGAO Preliminary Design (PD) phase plan presented in the Systems Engineering Management Plan (SEMP; KAON 574) included a replan to address changes from the System Design Review (SDR) and Observatory FY09 planning, plus recent new guidelines from the Directors.  This KAON summarizes the changes to the SEMP for the PD phase.

Remaining Action Items:

- Complete incorporation of items identified in section 3 in MS Project Plan.

- Incorporate new directions from Directors (section 2.5)

- Incorporate Erik’s 8/15 input.

- Incorporate items from 8/15 discussion with David & get more input.

- Get Rich’s schedule input.

- Incorporate Don’s schedule input.

- Get science team input.

- Develop a new plan for laser (section 2.4).

- Need a plan (separate or incorporated) for science instruments.

- Incorporate ME/FE changes from Bell.

2. Required Changes

2.1 Changes in Response to the SDR Panel Report

The SDR panel report and the NGAO team response are documented in KAONs 588 and 593, respectively.   The following numbered items refer to the numbered items in KAON 593.  The responses that require a change to the plan are shown in italics.

- Complete the science cases.  Already part of the plan.

- Requirements development.

  - Further evaluate d-IFS spaxel size and ensquared energy requirements.  Already part of the plan, especially the high-z galaxy science case.

  - PSF requirements.  Already part of the plan.

- Consider L’ imaging.  Add a WBS element to WBS 3.1 Science Case Development to determine if L’ imaging should be given a higher priority.

- Performance modeling and validation.

  - Determine what additional performance modeling, evaluation and anchoring of assumptions should be performed during the PD.  Add a WBS element to WBS 3.3 Systems Engineering Analysis after 4b, plus some resources to work on the identified items.

  - Compare the NFIRAOS and NGAO error budgets.  Add a WBS element to WBS 3.3 Systems Engineering Analysis.

  - Learn from Villages and LAO experiments.  Add a WBS element to define and agree on a plan for what we need under WBS 3.9 Technical Risk Assessment and Mitigation.

- Component performance assumptions.

  - Refine assumption of laser return for laser type given the known variations in the sodium abundance.  Add a WBS element under WBS 3.3.1.3.2 WFE/EE Performance Analysis.

  - Evaluate several proven LGS WFS detector options.  Already part of the plan.

  - Further demonstrate and document candidate LOWFS detector performance.  Already part of the plan.

  - Follow MEMS demonstration and characterization at LAO.  Include in item 4c above.

  - Be in a position to place long lead procurements by PDR.  Add a WBS element under WBS 2.5 Programmatic Risk to identify long lead procurements and when they need to be procured.

- More systems engineering.

  - Examine whether other activities can be reduced to increase systems engineering.

  - Consider further development of assembly, integration and testing plan. There are already 870h assigned to WBS 4.6, 5.6 and 8.x for this purpose.  Could look at shifting more resources to this task.

  - Implement full-time systems engineer by PDR.  Add a WBS element to identify a full time systems engineer prior to PDR under WBS 2.2.1 Executive Committee.

- Re-evaluate benefit/cost of d-IFS.  Re-evaluate d-IFS science case, including potential trades between number of IFUs and more sensitive IFU(s).  Add a WBS element to WBS 3.1 Science Case Development and WBS 3.4.1 System Hardware Architecture.

- Perform science instrument conceptual designs.  Note that the ATI proposal to develop the d-IFS conceptual design was not funded and the Observatory was unable to fund the start of a NIR imager conceptual design in FY09.  Some work on the science cases, requirements and interfaces is already in the PD plan.  Need to determine, in consultation with the Directors, if any NGAO funds can be used toward instrument conceptual designs during the PD phase.  There is a risk mitigation task under WBS 2.5 Programmatic Risk Assessment and Mitigation with only 40h.  Look at applying more resources.

- Complete the risk register and develop a risk mitigation plan.

  - Develop detailed risk mitigation plan.

  - Identify and implement collaborations.

  - Further address MOAO performance risk.

- Produce a staged implementation and descopes plan.  KAON 594 describes our plans to develop this plan.  This activity needs to be added under WBS 2.1 Planning, 3.1 Science Case Development and 3.3 Systems Engineering Analysis.

- Re-examine the cost and develop a schedule.

  - Develop another level of cost estimation.  Already in the plan.

  - Comparison to NGAO cost estimate.  Add a WBS element to WBS 2.1.3 Systems Engineering Management Plan.

  - Develop an implementation schedule.  Already in the plan.

  - Re-evaluate the contingency.  Already in the plan.

- Implement management structure changes.

  - Clearly identify roles.  Already part of plan for SEMP for future phases.

  - Develop management structure for the post-PD phases.  Already in the plan.

2.2 Keck Personnel Changes

The Observatory FY09 planning process resulted in a number of changes to the available versus planned hours for Keck personnel.  These changes are summarized in the following table.  The overall change is a reduction by 34 hours.  The plan needs to be made consistent with these changes.

| Name | KAON 574 Plan (hrs) | WMKO FY09 Plan (hrs) | New – Old Plan (hrs) |
| --- | --- | --- | --- |
| Adkins | 524 | 524 | 0 |
| Bell | 608 | 781 | 173 |
| Chin | 238 | 438 | 200 |
| Chock | 121 | 121 | 0 |
| Contract Admin | 44 | 44 | 0 |
| Johnson | 0 | 300 | 300 |
| Johansson | 2070 | 1200 | -870 |
| Kissner | 141 | 141 | 0 |
| Le Mignant | 1841 | 1710 | -131 |
| Medeiros | 508 | 315 | -193 |
| Mogenson | 30 | 198 | 168 |
| Morrison | 760 | 1067 | 307 |
| Nance | 488 | 120 | -368 |
| New Facilities Eng | 0 | 340 | 340 |
| Neyman | 1763 | 1950 | 187 |
| Panteleev | 200 | 200 | 0 |
| Tyau | 430 | 430 | 0 |
| Wetherell | 935 | 858 | -77 |
| Wizinowich | 933 | 983 | 50 |

In addition some changes will need to be made for the actual availability of personnel in FY08 as shown in the following table.

| Name | KAON 574 Plan (hrs) | Actual Availability (hrs) | Availability – Old Plan (hrs) |
| --- | --- | --- | --- |
| Adkins | 292 |  |  |
| Bell | 0 | 0 |  |
| Chin | 0 | 0 |  |
| Chock | 29 |  |  |
| Contract Admin | 18 |  |  |
| Johnson | 0 |  |  |
| Johansson | 432 | 330 |  |
| Kissner | 57 |  |  |
| Le Mignant | 603 | 360 | -243 |
| Medeiros | 0 | 0 |  |
| Mogenson | 0 | 0 |  |
| Morrison | 55 |  |  |
| Nance | 0 | 0 |  |
| New Facilities Eng | 0 | 0 |  |
| Neyman | 609 | 609 |  |
| Panteleev | 0 | 0 |  |
| Tyau | 69 | 69 |  |
| Wetherell | 0 | 0 |  |
| Wizinowich | 376 | 376 |  |

2.3 Caltech Personnel Changes

Jeff Zolkower was to have been the mechanical engineer for the wavefront sensor assembly design work at COO, but his recent promotion no longer makes him available.  He will be replaced with a TBD new hire at COO.

Matthew Britton was to have played roles in the wavefront sensor assembly design as well as in systems engineering.  His recent departure requires that we consider redistributing his work to others at COO including Dekany, Velur, Hale and Bouchez, and potentially others at WMKO or UCO.  In addition, COO will be looking at whether a new hire is appropriate.

The plan needs to be updated to take into account the above changes.

2.4 UCO Changes

Michael Peck has been hired to perform the Real-Time Control EE/Programmer tasks.  The number of hours was reduced on these tasks by 10% to reflect his seniority.  The RTC tasks were not started on the original schedule pending the placement of the UC contract (completed in late July) and the hiring of Peck.

New hourly rates were provided by UCO.

The UCSC Office of Sponsored Projects required the addition of 800 hours of a financial analyst at a cost of $46k.

2.5 New Laser Procurement Options

Subsequent to our SEMP plan for the development of the laser several recent changes have occurred: a company is incorporating to commercialize the SOR laser for astronomical LGS applications, ESO will be putting out a request for tender for their four LGS system.  A mutual desire has been expressed between ESO, TMT, GMT and Keck to collaborate on laser procurement and a white paper has been submitted to the NSF.  Our plan needs to be reviewed and likely changed in light of these developments.

The following is the outline for a new laser schedule:

- PM Risk Reduction

- Collaboration discussions (PW)

- Submit NSF white paper (PW)

- Determine collaborative path forward

- Maintain collaboration

- ESO laser contract milestones

- Laser PD contract RFQ issued

- Laser PD quotes received

- Laser PD kick-off meetings Dec/08

- Laser PDR Aug/08

- Laser system contract kick-off meeting Dec/09

- WMKO laser PD activities (presumably similar activities at collaborators)

- Provide input to ESO requirements

- Review RFQ responses (PW,SA,JC)

- Determine whether US-funded PD through ESO or WMKO (PW)

- Place US PD contract (PW,SA)

- US PD kick-off meeting

- ESO PD kick-off meeting

- US PDR participation (PW,SA,JC,KG)

- ESO PDR participation (PW,SA,JC,KG)

- Contracting recommendation (PW,SA,JC)

2.6 New Guidelines and Directions

The Directors and SSC co-chairs met on 7/31/08 to develop guidelines and direction for the NGAO team.  The resultant document was provided to the NGAO Project Manager on 8/14/08.  The directions provided a cost cap of $60M for the project including science instruments and contingency (in then year dollars) from the start of the system design through completion.  The directions also requested a NFIRAOS cost comparison report at the 11/3/08 SSC meeting and an internal review of the build to cost concept no later than the April 2009 SSC meeting.

The following implications on the PD phase can be derived from these new directions and additional discussions:

- A phased implementation report is no longer required at the 11/3/09 SSC meeting.  However, we will still need to do some of this work to respond to the SDR reviewer and SSC concerns.

- We already have the NFIRAOS cost comparison in the replan prior to the November SSC meeting, as a result of the SDR reviewer recommendations.

- A new internal build to cost review is required prior to April 2009.

  - The cost cap is lower than the combined cost of the $1.2M actual cost of the system design, the $42.2M (in FY08$) NGAO budget presented at the SDR and the proposal instrument budget of $20M (in FY06$).  Verbal guidance from the Directors is that we should assume 5% inflation.

  - The cost cap will require additional work during the PD phase to identify ways to reduce costs including science based reductions in requirements and capabilities.

  - The science return versus dollars will be evaluated within the cost capped system.  A complete system should therefore be provided within the cost cap and the scientific capabilities of the system should not depend on future upgrades.

- We need to develop better costs for the instruments and therefore designs.  This will require some of our preliminary design resources.

- We can assume the funding is there when we need it when developing “then year dollar” budgets.  Funding contingency does not need to be included in our capped budget.

We could (and may have to) consider extending the PD phase in order to have enough funds or schedule to address these new directions.  However, the impact of such delays is more serious given the “then year dollars” cap.

3. Changes to Plan

WBS 1.3.2 PD Phase Management

| WBS 1.3.2. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 1.1.1 | Replan based on SDR | Insufficient hours assigned? | Extend end from 5/9 to 8/20/08. Increase Wizinowich from 18 to 58h overall |
| 1.1.1.1 | Response to SDR Report | New sub-task | 8h Wizinowich, 2h Dekany, 2h Gavel |
| 1.1.1.2 | Response to SSC Minutes | New sub-task | 4h Wizinowich |
| 1.1.1.3 | Replan KAON | New sub-task | 24h Wizinowich, 4h Dekany, 4h Gavel |
| 1.1.1.4 | Replan MS Project Plan | New sub-task | 22h Wizinowich |
| 1.1.2 | Phased Implementation Planning | SDR panel recommendation response 10 (from section 2.1) | New task & sub-tasks inserted between |
| 1.1.2.1 | Plan to address Phasing & Descope Options | Define approach & get approval | New task inserted. 16h Wizinowich, 2h Dekany, 2h Gavel |
| 1.1.2.2 | SDR Proposed System | Proposed task | New task inserted. 16h Wizinowich |
| 1.1.2.3 | SDR Proposed System Staged Implementation | Proposed task | New task inserted. 16h Wizinowich |
| 1.1.2.4 | Keck AO Upgrade Option | Proposed task | New task inserted. 8h Wizinowich |
| 1.1.2.5 | Descope Options | Proposed task | New task inserted. 16h Wizinowich. |
| 1.1.2.6 | Cost Savings Options | Proposed task | New task inserted. 8h Wizinowich, 8h Gavel |
| 1.1.2.7 | Phased Implementation WFE budgets | Proposed task | New task inserted. Add 40h Dekany from 7/21 to 8/30/08 |
| 1.1.2.8 | Phased Implementation Report | Written report & presentation to Directors & SSC | New task inserted. 16h Wizinowich, 4h Dekany, 4h Gavel |
| 2.2.1 | Meeting Participation | Zolkower availability | Replace Zolkower 100h with new ME |
| 1.3 | Cost Estimation | Needs to be addressed earlier in some ways & needs a higher profile | New task inserted. |
| 1.3.1 | Cost Estimation: NFIRAOS Cost Comparison | SDR panel recommendation response 11b. | New task inserted. Add 48h for Dekany; 8h each for Johansson, Neyman, Velur; 16h each for Gavel, Wizinowich. Period = 8/15 to 9/30/08. |
| 1.3.2 | Cost Estimation: SEMP |  | Moved from 1.3.1.2 |
| 1.3.4 | Cost Estimation: SEMP | Britton & Zolkower availability | Replace Britton 15h & Zolkower 15h with new ME |
| 2.1 | Executive Committee | EC replaced with senior management team | Replace “Executive” with “Senior Management” at this level and sub-levels |
| 2.1.1.3 | Implement Full-time Systems Engineer | SDR panel recommendation response 6c. | New task inserted. 10/1/09-1/29/10. Wizinowich 24h. |
| 2.3.2 | Director Telecon #2 | Extra telecon | Inserted June 9 telecon |
| 5.2.4 | Identify Long Lead Procurements | SDR panel recommendation response 5e. | New task inserted. Wizinowich 20h. 10/5-11/27/09. |
| 6.8 | PDR | Britton & Zolkower availability | Assign Britton 8h to new ME; remove Zolkower 8h. |
| 7.1 | Admin/Contract Support | UCO requirement | Add 800h of UC financial analyst |

WBS 1.3.3 Systems Engineering

| WBS 1.3.3. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 1.1.1.5 | L’-band Imaging | SDR panel recommendation response item 3. | New task inserted. |
| 1.1.2.10 | D-IFS Science Case & Trades | SDR panel recommendation response item 7. | New task inserted. |
| 1.3.4 | Science Implications of Phased Implementation | To support phased implementation per SDR panel recommendation response item 10. | New task inserted. |
|  |  | Cancel or postpone something to allow Max to work on the above |  |
| 2.3.1 | FRD release 1 | Transfer to make Dekany available elsewhere | Reassign Dekany 30h to ? |
| 2.3.3 | Compliance Matrix | Not needed so early | Move from 10/6-11/17/08 to 11/23-12/18/09 |
| 2.5 | Software Standards | Personnel availability | Move dates from 10/6-11/17 to 9/2-9/30/08 |
| 3.1.3.1.2 | Improved Bandwidth Model | Britton unavailable | Reassign to Gavel |
| 3.1.3.1.3 | Improved Atmospheric Dispersion Model | Britton unavailable | Reassign to Bouchez |
| 3.1.3.1.4 | Other | SDR panel recommendation response item 4b. | Replace “Other” with “NFIRAOS Budget Comparison” Reduce Dekany 76h to 48h & add 32h Neyman. Period = 10/1 to 11/14/08 (was 5/4-6/24/09) |
| 3.1.3.1.5 | Determine Additional Performance Modeling or Anchoring | SDR panel recommendation response item 4a. | New task inserted with 10h of Dekany. 11/17-11/21/08. |
| 3.1.3.1.6 | Perform Additional Performance Modeling or Anchoring | SDR panel recommendation response item 4a. | New task inserted. 40h Neyman & 20h Dekany. 10/5-11/27/09. |
| 3.2.2 | Performance vs TT NGS Report | Descope to make Dekany available elsewhere | Reduce Dekany 80h to 40h |
| 3.1.3.2.2 | Additional Science Case Analysis | Descope to cover WFE analysis for phased implementation | Reduce Dekany 48h to 8h. |
| 3.1.3.2.3 | Evaluate Performance Implications of Phased Implementation | To support phased implementation per SDR panel recommendation response 10. Consider replacing 3.1.3.2.2 Additional Science Case Analysis with this. | Covered under Phased Implementation Plan. |
| 3.1.3.2.4 | Laser Return Evaluation | SDR panel recommendation response 5a. | New task inserted. 16h Dekany. 12/1-12/12/08. |
| 3.1.4.1 | Develop Astrometric Budget Tool | Britton unavailable | Transfer to Jessica Lu |
| 3.1.5.1 | Observing Efficiency Tool | Le Mignant availability | Postpone or transfer task. |
| 4.1.3 | D-IFS Number versus Sensitivity Trade Study | SDR panel recommendation response item 7. |  |
| 4.2 | Software Architecture | Johansson availability | Change start from 7/28 to 10/1/08 |
| 4.2 | Software Architecture | Wrong WBS number | Change to 4.3 |
| 4.3 | Controls Systems Architecture | Wrong WBS number | Change to 4.2 |
| 4.3 | Control Systems Architecture | Johansson availability |  |
| 4.4 | Operations Sequences Architecture | Le Mignant availability | Shift the start date from 5/5 to 10/1/08. Move the start date of all 4 subtasks accordingly, but keep the end date of the 4th task fixed. |
| 5.1.3 | Science Tools ICD | Timing | Move from 10/6/08 start to start no later than 1 month after MCS infrastructure |
| 5.2.2 | Generic Science Instrument ICD to NGAO Science Tools | Instrument & Science Tools readiness | Move from 10/6-10/31/08 to 2/1-2/28/09. |
| 9.1.1 | Risk Assessment v1 | Descope/transfer to make Dekany available elsewhere | Transfer Dekany 20h to Gavel |
| 9.2.1.1 | Support/Monitor Profiler Implementation | Transfer to make Neyman available elsewhere | Look at transferring some of Neyman 180h to others? |
| 9.2.2.1 | Prototype NIR TT sensor | Britton & Zolkower availabilty | Assign Britton 140h & Zolkower 130h to new ME |
| 9.2.3 | On-Sky and Lab Demonstration Coordination | SDR panel recommendation response item 4c. | New task inserted. Gavel lead. |
| 9.2.3.1 | Define Demonstrations |  | New task inserted. 12h Gavel, 4h Wizinowich. 7/15-8/29/08. |
| 9.2.3.2 | Analyze & Document Demonstration Results |  | New task inserted. 20h Gavel, 20h Wizinowich. 10/1/08-9/30/09. |

WBS 1.3.4 AO System Design

| WBS 1.3.4. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 1 | AO Enclosure | ME personnel changes | Transfer Bell 30h to Mogenson |
| 2.5.1 | LGS WFS Assembly – review concept | Zolkower, Britton & Johansson availability | Assign Britton 40h & Zolkower 40h to new ME |
| 2.5.2 | LGS WFS – develop WFS O-M |  | Assign Britton 140h & Zolkower 140h to new ME |
| 2.5.3 | LGS WFS – identify issues |  | Assign Britton 72h to new ME |
| 2.5.4 | LGS WFS – develop OSM OM |  | Assign Zolkower 20h to new ME |
| 2.5.5 | LGS WFS – pkg & model |  | Assign Zolkower 80h to new ME |
| 2.5.6 | LGS WFS – background model |  | Assign Britton 80h to Velur |
| 2.5.7 | LGS WFS – motion control |  | Assign Johansson 80h to Wetherell |
| 2.5.8 | LGS WFS – risks |  | Assign Britton 26h & Zolkower 27h to new ME |
| 2.5.9 | LGS WFS – integration plan |  | Assign Britton 25h & Zolkower 25h to new ME |
| 2.5.10 | LGS WFS – document |  | Assign Zolkower 80h to new ME |
| 2.6 | NGS WFS/TWFS Assembly | Velur & other availability | Delay start from 4/16 to 9/15/08 |
| 2.6.1 | NGS WFS/TWFS Assembly – review concept | Zolkower & Johansson availability | Assign Britton 20h & Zolkower 20h to new ME |
| 2.6.2 | NGS assly – WFS OM |  | Assign Zolkower 100h to new ME |
| 2.6.3 | NGS assly – FSM compliance |  | Assign Zolkower 50h to new ME |
| 2.6.4 | NGS assly – pkg &model |  | Assign Zolkower 58h to new ME |
| 2.6.5 | NGS assly – motion control |  | Assign Johansson 28h to Wetherell |
| 2.6.7 | NGS assly – alignment compliance |  | Assign Zolkower 16h to new ME |
| 2.6.8 | NGS assly - document |  | Assign Zolkower 28h to new ME |
| 2.7.1 | LOWFS Assembly – review concept | Zolkower, Britton, Dekany & Johansson availability | Assign Zolkower 32h to new ME |
| 2.7.2 | LOWFS – optimum dithering |  | Assign Britton 40h to Velur. Reduce Dekany from 36h to 0h; increase Hale by 4h. |
| 2.7.3 | LOWFS – unit OM design |  | Assign Zolkower 96h to new ME |
| 2.7.4 | LOWFS – OSM OM design |  | Assign Zolkower 80h to new ME |
| 2.7.6 | LOWFS – pkg & model |  | Assign Zolkower 80h to new ME |
| 2.7.7 | LOWFS – thermal model |  | Assign Zolkower 40h to Bouchez |
| 2.7.8 | LOWFS – motion control |  | Asign 120h Johansson to Wetherell |
| 4.2.1 | AO Sequencer: Architecture | Johansson availability | Transfer 20h of Johansson 80h to Morrison |
| 4.2.3 | AO Sequencer SW Module Design | Johansson availability | Transfer 15h of Johansson 30h to Morrison |
| 4.8 | Acq, Guiding & Offloading Control | Johansson availability | Transfer all 140h of Johansson to Stomski |
| 5.1 | RTC Processor | EE hired | Change EE to Peck & reduce hours by 10% & shift tasks to start in FY09 with some rebalance of Peck. |
| 5.1.1 | RTC Technical Management | Gavel recommendation in response to late start | Shift start from 5/12 to 8/18/08. No change in end date. |
| 5.1.2 | Centroid/WF Reconstruction Processing Requirements |  | Shift start from 5/12 to 8/25/08. |
| 5.1.3 | Centroid/WF Reconstruction Test Definition |  | Shift start from 9/8 to 8/25/08. |
| 5.1.4 | Precon. & Scaling Proc Requirements |  | Shift start from 10/6 to 11/17/08. |
| 5.1.5 | Precon. & Scaling Proc Test Definition |  | Shift from 12/29-2/6/09 to 12/22-2/13/09 |
| 5.1.6 | LOWFS Proc Requirements |  | Shift start from 2/9 to 3/9/09. |
| 5.1.7 | LOWFS Proc Test Definition |  | Shift start from 5/18 to 4/27/09. |
| 5.1.8 | Layer Comb & DM Proc Requirements |  | Shift start from 6/1 to 6/15/09. |
| 5.1.9 | Camera Data Transfer Issues |  | Shift start from 7/27 to 8/10/09. |
| 5.1.10 | Radial vs Rectilinear Voxels Trade Study |  | Shift from 11/3-2/11/09 to 12/22-6/26/09. |
| 5.1.11 | Define Required Bit Resoln |  | Shift start from 5/19 to 8/25/08. |
| 5.1.15 | Diagnostic Control & I/O Requirements |  | Shift start from 2/2 to 2/16/09 |

WBS 1.3.5 Laser System Design

| WBS 1.3.5. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 1.2 | LE Mechanical Design | ME personnel changes | Transfer 20h of Medeiros to Mogenson |
| 2 | Laser | New laser options |  |
| new 2.1 | ESO Laser Contract Milestones | Collaboration with ESO efforts | Insert milestones from section 2.5 |
| 3.4 | LLF Mechanical Design | ME personnel changes | Transfer 50h of Medeiros to Mogenson |
| 3.5 | LLF Electrical Design | Personnel availability | Transfer Wetherell 100h to Chin |
| 4.1.2 | Safety Algorithms, Diagrams & Dataflow | Personnel availability | Transfer Wetherell 20h to Chin |
| 4.1.3 | Safety Communication Protocols & Methods | Personnel availability | Transfer Wetherell 20h to Chin |
| 4.1.4 | Safety Performance Estimate | Personnel availability | Transfer Wetherell 20h to Chin |
| 5.1.1 | LSC Software requirements & interfaces | Johansson availability | Transfer Johansson 40h to Morrison |
| 5.1.2 | LSC Sequencer Software | Johansson availability | Transfer 60h of Johansson 80h to Morrison |
| 5.1.3 | LSC Motion Control SW | Only Morrison on task | Put Morrison as lead |
| 5.1.4 | LSC Device Control Software | Personnel availability | Shift start date from 8/3 to 9/14/09. Put Morrison as lead |
| 5.2.3 | LSC Device Control Hardware | Wetherell availability | Shift start date from 5/25 to 10/1/09 |

WBS 1.3.6 Science Operations Tools Design

| WBS 1.3.6. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 1.1 | MCS Infrastructure | Personnel availability | Move from 7/7-10/24/08 to |
| 1.4.1 | Alarm Handler & Troubleshooting Common Structure | Johansson availability | Transfer Johansson 50h to Morrison |
| 2. | User Interfaces | Le Mignant availability & science instrument readiness | Move to be complete by the end of FY09 |
| 2. | User Interfaces | Le Mignant availability | Identify others to take tasks from Le Mignant |
| 2.1.2 | UI Command Interface to MCS | Johansson availability | Transfer Johansson 40h to Morrison |
| 2.1.3 | UI Command Interface to Pre- & Post-Obs Tools | Johansson availability | Transfer Johansson 20h to Morrison |
| 2.2.2 | Setup UI Common Structure | Johansson availability | Transfer Johansson 30h to Morrison |
| 2.3.1 | Observations UI Common Structure | Johansson availability | Transfer Johansson 60h to Morrison |
| 2.3.2 | Acquisition & AO Control UI | Johansson availability | Transfer Johansson 10h to Morrison |
| 3. | Pre- & Post-Observing Science Support Tools | Le Mignant availability | Identify others to take tasks from Le Mignant |
| 3.2 | Science Observations Planning Tools | Non-unique names | Change WBS names two levels down to reflect higher level task name |
| 3.2.1 | NGS Star Finder Functional Requirements & Use Case Definitions | Le Mignant availability | Replace 40 hrs of Le Mignant with 40 hrs of McGrath |
| 3.3 | Data Products | Non-unique names | Change WBS names 2 or 3 levels down to reflect higher level task name |

WBS 1.3.7 Telescope & Summit Engineering Design

| WBS 1.3.7. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 2.2 | Infra. Mechanical Mods | ME personnel changes | Transfer 40h Medeiros to Mogenson |
| 2.4 | Infra. Glycol Cooling Mods | Transfer from FE to ME | Transfer 40h Nance to Bell |
| 2.5 | Infra. CCR Mods | Transfer from FE to ME | Transfer 40h Nance to Bell |
| 3.2 | Infra. Mechanical Mods | ME personnel changes | Transfer 25h Medeiros to Mogenson |
| 3.4 | Infra. Glycol Cooling Mods | Transfer from FE to ME | Transfer 50h Nance to Bell |
| 4 | OSIRIS Modifications | Wetherell availability | Transfer Wetherell 40h to Tolleth |
| 4 | OSIRIS Modifications | ME personnel changes | Transfer Medeiros 40h to Bell |

WBS 1.3.8 Telescope Integration & Test

| WBS 1.3.8. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 1.2 | Laser Removal Plan | ME personnel changes | Transfer Medeiros 20h & Nance 12h to Bell |

WBS 1.3.9 Operations Transition

| WBS 1.3.9. | Task Name | Reason for Change | Change |
| --- | --- | --- | --- |
| 1.1 | Operations Support Plan | Le Mignant availability & need to descope | Reduce Le Mignant from 40 to 20h, & shift task form 9/1-11/30/09 to 11/1-11/30/09. |
| 2.1 | Operations Personnel Training Plan | Le Mignant availability & need to descope | Cancel task & remove 10 hrs of Wizinowich & 40 hrs of Le Mignant. |
| 2.2 | Documentation Transition Plan | Le Mignant availability & need to descope | Cancel task & remove 20 hr of Le Mignant. |