Keck Next Generation Adaptive Optics

Real-Time Controller (RTC)

Rebaseline Planning. Taken from the meeting notes of April 16, 2009

The following is the present WBS structure under RTC Processor 1.4.5.1.x :

- Technical Management

- Centroid/Wavefront Reconstruction Processing Requirements

- Centroid/Wavefront Reconstruction Processing Test Definition

- Preconditioning and Scaling Processing Requirments

- Preconditioning and Scaling Processing Test Definition

- Low Order WFS Processing Requirements

- Low Order WFS Processing Test Definition

- Layer Combining and DM Processing Requirements

- Camera Data Transfer

- Radial Versus Rectilinear Voxels Trade Study

- Define Required Bit Resolution

- Analyze Single Event Upset

- Analyze Power Use and Requirements

- Voxel Communication Parameters

- Diagnostics Design and I/O Requirements

- Monitoring Design and I/O Requirements

- Define Testing Procedures

- Documentation

The following is a re-organization of work based on the “to-do” items we discussed. Parenthesized numbers indicate the corresponding original WBS item.

- Technical Management (1)

- Develop Internal Budgets

  - Wavefront error budget - contributors: word size (11), voxel sampling (10), latencies (14)

  - Power budget (13)

  - Volume budget

  - Error rate (12)

- Algorithm development support

  - MPP off-line simulator

  - Split tomography development

  - Woofer-tweeter algorithm

- RTC Hardware Architecture, Layout, and Design

  - Number and Function of boards

  - Layout of processors on boards

  - Interconnect of processors on-board (14)

  - Interconnect of boards to each other (14)

  - Clock distribution and synchronization

  - Trade chip processing capacity with power dissipation capacity and manage generated heat (13)

- Program Architecture and Programming - Time-critical tasks (HRT-PE):

  - Program the wavefront reconstructor (2)

  - Program the tomography algorithm (2, 4)

  - Program the DM control (inverse DM response function and open-loop control) (8)

  - Program the pseudo-open loop control for the woofer

  - Program the Split Tomography algorithm (incorporation of tip/tilt sensors) (6)

  - Telemetry and Diagnostic Streams

    - Diagnostics data  streaming to archive (15)

    - Monitoring and telemetry (16)

      - Self-monitoring (“heartbeat”, health status, operating within normal bounds)

      - Periodic status and data output to operator

- Program Architecture and Programming - Non-time-critical tasks (HRT-PE/CP):

  - Parameter loader

  - Real-time Control sequencer (HRT CP)

- Internal Interfaces Design

  - HRT to SRT

  - WFS Camera interfaces

    - HOWFS cameras (including camera control and high-speed data transfer)

    - LOWFS cameras

  - DM driver interface (DACs)

- External Interfaces Design

  - SRT to non-real-time supervisory system

  - Diagnostic/Telemetry output – interfaces to non-RTC and to data capture system

- RTC integration and testing plan

  - Hardware test plan (17)

  - Software test plan

    - Centroider/Wavefront reconstructor test (3)

    - Tomography test (5)

    - LOWFS processing test (7)

    - DM processing test

    - Hybrid control loop test

    - External interfaces test

- Documentation (18)

  - Summary of documents

  - Comprehensive control loop diagram

  - Hard Real Time (HRT) design – description of time-critical RTC hardware unit

  - Hard Real Time (HRT) algorithms – description of the time-critical RTC software tasks

  - Soft Real Time (SRT) / Hart Real Time (HRT) interface – description of parameter loading, RTC sequencing, interface to user command processor

  - Hardware interface document – methods of connecting to the WFS cameras, DMs, and diagnostic capture system

  - Integration and testing plan

Notes: acronyms:

RTC = Real-time controller

MPP = Massively Parallel Processing – the paradigm adopted for the Keck RTC architecture that enables compute-intensive tomography to be practical in real-time.

HRT = Hard Real Time processor – does the time-critical compute tasks in the AO controller

SRT = Soft Real Time processor – coordinates operator commands to change the state of the HRT

HRT CP = the HRT’s on-board Control Processor – coordinates the timing and sequence of FPGA programs

HRT PE = the HRT’s on-board Processing Engine – the actual processors implementing the real-time tomography etc.

FPGA = Field Programmable Gate Arrays – a building-block computer chip that, in replication on circuit boards,  can implement the HRT PE using the massive parallel processing approach

GPU = Graphics Processing Unit – an alternative digital signal processor that could be used to implement some portions of the HRT PE (perhaps in processing video input from cameras) and also fits within the MPP architectural approach

Program plan and milestones

Milestones:

- Version 0.1 of documentation (outline, roughed in or placeholder contents) – May 15

- Draft versions of internal allocation budgets – April 30

- Control loop diagrams complete – May 30

- Off-line simulator completed and running – June 30

- Algorithms mapped to processors (board architecture and software architecture defined) – July 30

- Version 0.2 of documentation – Aug 30

- Flow-down of latency assignments to internal interfaces complete – Sept 30

- Board layouts version 1 complete (functional block diagram and space allocation on boards) – Sept 30

- Version 1.0 of documentation – Oct 30

- Update 1 to cost estimate – Nov 30

- Design iteration 1 – Jan 30,’10

- Update 2 to cost estimate – Feb 28,’10