Keck Adaptive Optics Note 512

Keck Next Generation Adaptive Optics

System Design Phase Project Report #4 - DRAFT

P. Wizinowich, R. Dekany, D. Gavel & C. Max + NGAO team

September 14, 2007

# Narrative

This report provides an update to Project Report #3 that was submitted to the Observatory Directors on June 19, 2007.  The next project report will be submitted in November.

## Summary

The system architecture phase had just begun at the time of the last report and this has been the primary focus of our activities during this reporting period.  We are pleased to report that this phase has largely been completed.  In particular, a system architecture was selected as the result of a process that evaluated and compared five different architectures.  We refer to the selected architecture as a “cascaded relay” since it consists of two optical relays.  A wide field lower order correction relay that feeds the LGS wavefront sensors, tip/tilt sensors and near-IR multi-object IFU and a narrow field high order correction relay that feeds the narrow field science instruments.  The other major product of this phase is a functional requirements document (version 1 is nearing completion).

All of the work to date (performance budgets, trade studies, architecture and subsystem evaluations, and the functional requirements) provides the basis for the next stage of the system design phase which has recently begun.  This is the system design phase where conceptual designs are developed for all the major subsystems and the functional requirements (version 2) are further refined.  So far, six teams have been set-up with subsystem level design responsibilities (i.e., opto-mechanics, controls, etc.) and work scope planning sheets have been developed for each major WBS element.

Additional work during this period has included: Completion of two performance budget reports (background and transmission, and companion sensitivity); additional atmospheric characterization data has been used to update our atmospheric model assumptions; and summary reports have been written for the performance budgets and trade studies.

A decision was made by Observatory management to submit an NSF TSIP proposal for the NGAO preliminary design phase.  Sean Adkins took the lead in producing a very nice proposal using the materials developed by the NGAO team and in consultation with Observatory management and the NGAO EC.  The management and budget sections of this proposal were based on the currently available information, and do not represent commitments on the part of the EC.  The NGAO team still needs to develop a detailed systems engineering management plan as part of the system design phase.

## Technical Status

The technical status reported below is organized according to the major WBS elements in the SEMP.  Only the currently scheduled WBS elements are included.

### System Design Phase Management (WBS 1)

The NGAO Twiki site (http://www.oir.caltech.edu/twiki_oir/bin/view.cgi/Keck/NGAO/WebHome) continues to be heavily utilized to manage and document the project.

Two team meetings have been held since the last report and our next team meeting will occur in September.

Emphasis during this period …

TSIP proposal …

Keck Science Meeting …

### System Requirements (WBS 2)

### Performance Budgets (WBS 3.1.1)

The progress and status of each of the performance budget elements is summarized below.

Model Assumptions (WBS 3.1.1.1).

Model/Tool Validation (WBS 3.1.1.2).

Transmission and Background Budgets (WBS 3.1.1.3 & 3.1.1.4).

Wavefront Error and Encircled Energy Budgets (WBS 3.1.1.5 & 3.1.1.6).

Photometric Precision Error Budget (WBS 3.1.1.7).  Complete as KAON 474, as reported in progress report #2.

Astrometric Accuracy Error Budget (WBS 3.1.1.8).  Complete as KAON 480 as reported in progress report #3.

Polarimetric Accuracy (WBS 3.1.1.9).  No progress.  Still unable to find a scientist to assist in the development of a polarimetric accuracy technical report.

High-contrast Error Budget (WBS 3.1.1.10).

Observing Efficiency Performance Budget (WBS 3.1.1.11).  No work currently scheduled.

System Uptime Performance Budget (WBS 3.1.1.12).   No work currently scheduled.

### Trade Studies (WBS 3.1.2)

A series of trade studies were initiated at the start of the Keck NGAO System Design phase in order to help solidify system requirements and to give us a perspective on the feasible system architectures.  The progress and status of these trade studies is described below.

MOAO versus MCAO (WBS 3.1.2.1.1). Complete as KAON 452 as reported in Progress Report #3.

NGAO versus Keck AO Upgrades (WBS 3.1.2.1.2).  Complete as KAONs 461 and 462, as reported in Progress Report #2.

Adaptive Secondary Mirror Option (WBS 3.1.2.1.3).  Complete as KAON 485, as reported in Progress Report #3.

Keck Interferometer Support (WBS 3.1.2.1.5).  Complete as KAON 483, as reported in Progress Report #3.

GLAO for non-NGAO Instruments (WBS 3.1.2.1.7).  Complete as KAON 472, as reported in Progress Report #2.

Science Instrument Re-use (WBS 3.1.2.1.8).  Complete as KAON 493, as reported in Progress Report #3.

Telescope Wavefront Error (WBS 3.1.2.1.9).  Complete as KAON 482, as reported in Progress Report #3.

Observing Model (WBS 3.1.2.1.10). Complete as KAON 476, as reported in Progress Report #3.

Optical Relay (WBS 3.1.2.2.2) & Field Rotation Strategy (WBS 3.1.2.2.2.3).  Cancelled.  Initial results used in system architecture phase.

Rayleigh Rejection (WBS 3.1.2.2.5).  Complete as KAON 490, as reported in Progress Report #3.

LGS Wavefront Sensor Type (WBS 3.1.2.2.6) & LGS Wavefront Sensor Number of Subapertures (WBS 3.1.2.2.7).  Complete as KAON 465, as reported in Progress Report #3.

Low Order Wavefront Sensor Architecture (WBS 3.1.2.2.9).  Complete as KAON 487, as reported in Progress Report #3.

Number and Type of Low Order Wavefront Sensors (WBS 3.1.2.2.10). Complete as KAON 470, as reported in Progress Report #2.

d-IFU and LOWFS AO and Object Selection (WBS 3.1.2.2.16).  In process.

LGS Asterism and Geometry (WBS 3.1.2.3.3).  Complete as KAON 429, as reported in Progress Report #1.  Additional analysis in KAON 492, as reported in Progress Report #3.

Variable versus Fixed Laser Asterism (WBS 3.1.2.3.4). Complete as KAON 427, as reported in Progress Report #1.

Uplink Compensation (WBS 3.1.2.3.5).  In process.

### System Architecture (WBS 3.1.3)

A subset of the NGAO team has been tasked with determining the subsystem candidates for the NGAO system.  Group attention directed to key subsystems that are seen as large drivers of system performance, cost and risk.  Preliminary candidates have been identified and evaluated.  System architecture will be built up from the evaluation of these subsystems.   The core team will meet for one week of intensive work at UCSC in July.  Goals of this workshop include:

- Propose candidate architectures as combinations of top ranked subsystems

- Develop architecture system-level cost estimation

- Assign and begin drafting initial subsystems functional requirements

### AO System and Laser Facility Design (WBS 3.2 & 3.3)

### Science Operations (WBS 3.4)

Four work scope planning sheets have recently been produced for the top-level WBS elements in this category.  Review and approval is pending.

### Science Instruments (WBS 3.5)

A draft report on proposed and under development deployable near-IR IFU work at other observatories is nearing completion, as well as a report on the simple versions of the two imagers.

### Keck Adaptive Optics Notes

The following KAONs have been produced since the last report:

- 484 Optical Design Practices for NGAO

- 491 NGAO Performance Budget Summary

- 495 Summary of NGAO Trade Studies

- 496 Mauna Kea Turbulence Statistics

- 497 NGAO High-Contrast and Companion Sensitivity Performance Budget

- 499 NGAO System Architecture Definition

- 500 Keck AO Upgrade Feasiblity

- 501 NGAO Background and Transmission Budgets

- 502 Keck AO Upgrade Engineering Cost Basis

- 503 Mauna Kea Ridge Turbulence Models

- 504 Performance vs Technical Field of View for LOWFS Guide Stars

- 506 Split Relay Architecture Evaluation

- 509 Uplink Compensation Trade Study

- 510 Preliminary Technical Risk Evaluation

- 511 System Design Manual

All of the NGAO KAONs can be found at http://www.oir.caltech.edu/twiki_oir/bin/view.cgi/Keck/NGAO/NewKAONs

## Schedule and Budget Status

### Milestones

The SEMP milestones through September are shown in the table below along with their status.    One milestone has been completed since the last report.

| # | MILESTONE | DATE | DESCRIPTION | STATUS |
| --- | --- | --- | --- | --- |
| 1 | SD SEMP Approved | 10/9/06 | Approval of this plan by the Directors. Initial SEMP version released to Directors for comment on 9/12 & final version on 9/29/06. | Verbal approval received from individual Directors. Written approval requested. |
| 2 | SD phase contracts in place | 10/27/06 | Contracts issued to Caltech & UCSC for the system design phase. | Complete |
| 3 | Science Case Requirements Summary v1.0 Release | 10/27/06 | Initial Release of the Science Requirements as input to trade studies and performance budgeting | Complete |
| 4 | System Requirements Document (SRD) v1.0 Release | 12/8/06 | Initial release of System Requirements with emphasis on the science requirements | Complete |
| 5 | Performance Budgets Summary v1.0 Release | 6/15/07 | First round of all performance budgets complete & documented | Complete |
| 6 | SRD v2.0 Release | 5/22/07 | Second release of System Requirements Document | Good progress |
| 7 | Trade Studies Complete | 6/22/07 | All trade studies complete & documented (as a series of KAONs); with one new trade study excepted | 15 complete, 1 cancelled & 2 remaining (including exception) |
| 8 | SRD v3.0 Release | 9/7/07 | Third release of System Requirements |  |
| 9 | System Design Manual v1.0 Release | 9/21/07 | First release of System Design Manual | Some work as part of system architecture |
| 10 | Technical Risk Analysis v1.0 Release | 9/21/07 | First round of project risk analysis complete & documented | Some work as part of system architecture |

### Schedule

The following discussion focuses on the WBS elements for which major work should have occurred through mid-March.  Overall we are behind schedule.

SD Phase Management (WBS 1).  We are generally on track with the management items.  The planning and contracting is complete to date and meetings are being held on schedule.   The mid-year replan was completed in May.

System Requirements (WBS 2).    The first versions of the science case and systems requirements documents (SRD) are complete, and good progress has been made on the second version of the SRD.  This category is behind schedule.  By not having these sufficiently defined we assume more risk that the performance budgets and the AO system and science instrument decisions may need to change.

Performance Budgets (WBS 3.1).  The performance budgets are behind the replanned schedule.  The switch from understanding the budgets to documenting the budgets should help in bringing these budgets to closure.

Trade Studies (WBS 3.2).  Fifteen of the 18 trade studies planned for completion through the end of June are complete; and one additional study has begun.

Science Instruments (WBS 3.5).  This effort is behind the replanned schedule; this is in part due to the need to complete the development of the science requirements in the SRD.  Additional and more rapid progress is expected with the completion of the initial sets of science requirements.

### Budget

As mentioned in Progress Report #2 the total FY07 budget is $818k.

The total budget spent through July, 2007 is $k.  This represents % of the FY07 budget and % of the total System Design Phase budget.

## Anticipated Accomplishments in Next Period

The next project report will be distributed prior to the November Keck Science Meeting.  The priority during this period will be on the design and functional requirements.  We will also need to complete the science and system requirements.  We anticipate all project milestones through milestone 8 (see Milestone table in section 1.3.1) to be complete by the next report.

# Schedule

A high level snapshot of the tracked version of the schedule through August is shown below with 44% complete.  Note that the % of work completed is 49%.

# Financial Summary

The schedule shows 44% of the system design phase activities complete, and 49% of the work complete, through August.  The budget shows 49% of the system design phase budget ($1142.8k including contingency) spent through July.

The average number of FTEs working on the NGAO system design tasks at our three institutions was 5.3 in the first ten months of FY07 versus the ~ 6 FTE level in the SEMP.  The total expenditure through the end of July is $564k.  This represents 69% of the $818k FY07 budget versus the ~ 83% level planned in the SEMP.

WMKO Report: The following table lists the WMKO FTEs and total costs through July, along with the year to date (YTD) total and the FY plan from the SEMP (not from the replan).   WMKO is slightly below the ~83% level expected in both FTEs and personnel costs.

| Category | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | YTD | FY Plan | % Spent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel (FTEs) | 2.1 | 2.5 | 1.4 | 3.2 | 3.7 | 2.5 | 3.2 | 2.6 | 3.0 | 2.2 | 2.2 | 2.8 | 79% |
| Personnel ($k) | 16.1 | 27.1 | 11.0 | 31.8 | 27.3 | 22.4 | 29.5 | 26.4 | 23.8 | 20.2 | 235.7 | 305.5 | 77% |
| Travel, phone ($k) | 0.1 | 2.5 | 0.1 | 0.6 | 0.1 | 0.1 | 2.7 | 1.7 | 1.8 | 3.8 | 13.3 | 13.3 | 100% |
| Total ($k) | 16.2 | 29.5 | 11.1 | 32.4 | 27.4 | 22.4 | 32.2 | 28.1 | 25.6 | 23.9 | 248.9 | 318.8 | 78% |

COO Report: The following table lists the COO FTEs and total personnel costs through July.   COO is significantly (~20%) below the expected number of FTEs however this has apparently been compensated with higher level FTEs as seen by the personnel dollars.

| Category | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | YTD | FY Plan | % Spent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel (FTEs) | 0.3 | 1.1 | 0.7 | 1.3 | 1.8 | 1.3 | 1.8 | 1.1 | 1.4 | 2.1 | 1.1 | 1.6 | 67% |
| Personnel ($k) | 6.9 | 15.1 | 11.4 | 22.2 | 26.5 | 16.0 | 33.5 | 15.7 | 20.5 | 30.4 | 198.2 | 232.5 | 85% |
| Travel, phone ($k) | 0.0 | 0.2 | 0.1 | 4.3 | 0.3 | 0.0 | 0.0 | 0.0 | 0.4 | 1.3 | 6.6 | 13.3 | 50% |
| Total ($k) | 6.9 | 15.3 | 11.5 | 26.5 | 26.8 | 16.0 | 33.5 | 15.7 | 20.8 | 31.7 | 204.8 | 245.8 | 83% |

UCO/Lick Report: The following table lists the UCO/Lick FTEs and total personnel costs through May.  UCO is low in both FTEs and personnel costs versus the plan.  The FTEs are higher than the personnel costs because the no-cost LAO personnel were not in the MS project plan.

| Category | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | YTD | FY Plan | % Spent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel (FTEs) | 1.7 | 1.7 | 1.3 | 1.2 | 1.4 | 1.6 | 1.6 | 1.6 | 0.6 | 1.0 | 1.1 | 1.7 | 66% |
| Personnel ($k) | 6.8 | 7.8 | 7.0 | 8.1 | 8.6 | 10.6 | 10.6 | 10.6 | 11.8 | 18.9 | 100.9 | 162.6 | 62% |
| Travel, phone ($k) | 0.0 | 0.0 | 0.0 | 0.7 | 4.4 | 0.0 | 0.4 | 0.1 | 0.1 | 4.0 | 9.7 | 13.3 | 73% |
| Total ($k) | 6.8 | 7.8 | 7.0 | 8.9 | 13.0 | 10.6 | 11.0 | 10.7 | 11.9 | 22.9 | 110.6 | 175.9 | 63% |

A postdoc is included in the UCO budget.  The postdoc, Elizabeth McGrath, has started work at a 3 days/week level, but will not be charged to the project until late Aug. once she has completed her Ph.D. defense.

Science Case Requirements Report:  The SEMP does include 620 hours ($19k) for graduate students to support the science case development.  A student of F. Marchis was recently funded for the period of Aug. 1 through Nov. 30 for a total cost of $13.2k .  Project scientist and science community participation, which is “free” to the project, is not tracked.