NGAO System Design Phase: Work Scope Planning Sheet

WBS Element Title:	Observing Interfaces, Acquisition, Observing Sequences, Instrument, AO

& Telescope Observer Interfaces, Science Data Quality Monitoring

Simulation Tools

WBS Element Number:	3.4.1.2, 3.4.1.2.1, 3.4.1.2.2, 3.4.1.2.3, 3.4.1.2.4

Work Package Lead:	David Le Mignant

Work Package Participants:	E. Johansson, E. McGrath, TBD

# Work Scope

WBS Dictionary Entry: 	Observing Interfaces:  Specify and design the software tools and interfaces that the observer will require to perform the observations, including:

3.4.1.2.1  Acquisition:  Define method, information and design interfaces for acquiring guide stars and science object/field. Particularly, look into the requirements for the nature of the AO guide stars (extended objects?), the space command and laser traffic control clearance for the target, and for using telescope or other sub-system pointing information to register the science frames within the field of regard.

        - Observing Sequences: Define method, information and design interfaces for acquiring the science data (target, background emission and calibrations) including the ability to plan various observing sequences, save them and then execute them at the telescope.

        - Instrument, AO & Telescope Observer Interfaces:  Define the methods and design the interfaces required by the observer to perform and monitor the observations and observing conditions.  This topic has to be addressed very closely with the science instrument design.

        - Science Data Quality Monitoring:  Define method and design interfaces to estimate, record and monitor the quality of science data including suitable image quality metric (WF residual, EE, etc) at the science detector, seeing, photometry, astrometry, etc based on the NG AO science use cases.

# Inputs:	The key assumptions used as starting points for this WBS element will be derived from the FRD 1.0. Other references that may provide inputs for this WBS are KAON 463 (“Assessment on current LGS operations”), KAON 476 (“Observing Models Trade Study”), the Instrument Baseline Requirements document and the Observing Scenarios. We will also have topical discussions with current LGS observers, the Keck Observatory staff (software and operations), and the Instrument Working Group to explore the modules and details for the pre-observing interfaces. The interface specifications and design developed in this WBS should be fully consistent with both the architecture and the specifications designed (in parallel) for the tools and interfaces listed under WBS 3.4 (Operation Architecture, Observing Interfaces, Operations Optimizations) and some non-real-time aspects of WBS 3.2 (AO operations) and 3.3 (Laser operations).

# Products:	The products of this WBS element will include 1) outputs for the FRD 2.0, and 2) several Design Manuals that will present a conceptual design to demonstrate the feasibility of the tools, with an emphasis on the end-user point of view, and a flexible design approach to facilitate inclusion of new modules as the science instruments are defined. The manual will include a  summary of the interface requirements, and describe an architecture that will meet the requirements. We will provide a detailed list of the requirements, I/O parameters, algorithms, etc, for the functions and graphical tools. Particular attention will be given to the algorithm for the Acquisition Sequence as well as the level of expertise for the end user. We will also lay down  the requirements for tool portability, development for inclusion of science instrument modules, optimization and maintenance.

Doc reference: WMKO.NGAO.SD.WBS3.4.1.2

NGAO Pre-Observing Interfaces Design Manual:

We anticipate the following sections (see Adkins 2006):

- Introduction

- Scope and Applicability

- Related Documents

- Revision History

- Overall System Requirements

- Science Acquisition Requirements

  - Performance Requirements

    - Parametric

    - Operational

  - Implementation Requirements

    - Feature Implementation

    - Common Practices

    - Standards

  - Design Requirements

    - Technological

    - Standards Related

    - Integration Related

- Observing Sequence Requirements

  - Performance Requirements

    - Parametric

    - Operational

  - Implementation Requirements

    - Feature Implementation

    - Common Practices

    - Standards

  - Design Requirements

    - Technological

    - Standards Related

    - Integration Related

- Observer Interface Requirements

  - Performance Requirements

    - Parametric

    - Operational

  - Implementation Requirements

    - Feature Implementation

    - Common Practices

    - Standards

  - Design Requirements

    - Technological

    - Standards Related

    - Integration Related

- Science Data Quality Monitoring Requirements

  - Performance Requirements

    - Parametric

    - Operational

  - Implementation Requirements

    - Feature Implementation

    - Common Practices

    - Standards

  - Design Requirements

    - Technological

    - Standards Related

    - Integration Related

- Interface Requirements

- Reliability Requirements

  - Risk and Mitigation

- Service and Maintenance Requirements

- Documentation Requirements

- Glossary

# Methodology:	At this point, we propose the following procedure for meeting the goals of the WBS element.  1) Assemble and summarize the requirements from the referenced document above; 2) Document a preliminary design that will detail the architecture between tools from other WBS  and includes functions, graphical tools and user interfaces for this WBS; 3) Provide a detailed description and/or discussion for each function supported by the Observing Interfaces.

# Estimate of effort:	The bulk of the work will be performed by D. Le Mignant (~40 h) as WBS lead, in collaboration with E. McGrath (~10 h) for the “astronomer” point-of-view,  E. Johansson (~16 h) for interfacing with AO Operations tools and TBD (~16 h) for the interface with the science instrument tools. We would like the documents to be reviewed by C. Boyer from the TMT as well as by astronomers (or support astronomer) very familiar with using and building LGS observing tools for Keck, (e.g., Support Astronomers, astronomers sitting on the AOWG, etc).

# Approvals:			80 hours

| Control | Name | Date |
| --- | --- | --- |
| Authored by: | David Le Mignant | 10/05/07 |
| Approved by: | WBS X.X Lead |  |
|  | NGAO EC Chair |  |

# Footnotes

The Observing Scenarios are documented in http://www.oir.caltech.edu/twiki_oir/bin/view.cgi/Keck/NGAO/NGAOObservingScenarios