## Sheet1
D.Hale
2008-Aug-07
| TASK | TIME/COST | COMPLETE
I. Documentation
| make list of camera controller test routines/commands | 0.5d
| make list of all deliverables | 0.5d
| document usage of any test routine software | 1d
| think of problem scenarios and outline disaster recovery steps | 1.5d
| document image combiner and backup procedure (part of ICD?) | 1d
| document low level filter changer control | 0.5d
| document high-level filter changer control (part of ICD) | 0.5d
| document final cooldown checkout process/procedure | 0.5d
II. Programming
| Marco fix PANDEV or, more likely I write my own | 5d
| fix controller sync (DSP code) -- syncs read but not expose | 2d | x
| fix clocks not always running (DSP code) | 2d
| write DSP mode for ultra-rapid readout (for focussing) | 2d / PEND
| write ArcVIEW module for filter changer | 3d
| write low-level control software for filter changer | 1.5d | x
| write image combiner software | 1d | x
| hook image combiner into ArcVIEW | 2d
| write test / troubleshooting routines | 5d
| unscrambling corrections | 0.5d | x
III. Lab Testing
| troubleshoot "bad" detector w/Roger | 1-3d
| continued testing (with Marco) of ArcVIEW stability | 1-5d | x
| connect and test all six cables simultaneously | 1d | x
| reassemble one cable to correct connector orientation | <0.5d
| final checkout image acquisition (includes shutter checkout) | 1d
| checkout filter changer | 0.5d
| checkout temperature controller | 0.5d
| checkout vacuum gauge | 0.5d
| re-test dual PCI card operation | 1-3d | x
| fabricate mask | 1d
| acquire/analyze full-array images with mask | 0.5d
IV. Procurement
| if dual PCI card still unstable, procure 2nd 3U server | 7d/$2000 | x
| procure remote power server | 5d/$900 | n/a
| procure optical fiber barrel connectors | 5d?/?? (TBC)