## SCRD Requirements
# | Science Performance Requirement | AO Derived Requirements | Instrument Requirements | Discussion
1 | High redshift galaxies |  | NIR imager, NIR IFU or d-IFU
1.1 | Sensitivity. SNR ≥ 10 for a z = 2.6 galaxy in an integration time ≤ 3 hours for a spectral resolution R = 3500 with a spatial resolution of 70 mas [SCRD §2.1.4] | Sufficiently high throughput and low emissivity of the AO system science path to achieve this sensitivity. Background due to emissivity less than 30% of unattenuated (sky + telescope). [SCRD §2.1.5.1 and SCRD Figure 1] |  | Cost driver
1.2 | Target sample size of ≥ 200 galaxies in ≤ 3 years (assuming a target density of 4 galaxies per square arcmin) [SCRD §2.1.3] | Multi-object AO system: one DM per arm, or an upstream MCAO system correcting the entire field of regard. 6-12 arms on 5 square arc minutes patrol field. | Multiple (6-12) IFUs, deployable on the 5 square arc minute field of regard | Not met. Descoped to 1 IFU
1.3 | Spectroscopic & imaging observing wavelengths = J,H & K (to 2.4mm). z&Y are of interest as well; the importance of including these bands is being assessed. [SCRD §2.1.4, §2.1.5.3] | AO system must transmit J, H, and K bands | Infrared imager and IFUs designed for J, H, and K. Each entire wavelength band should be observable in one exposure. | z&Y could drive dichroic choices
1.4 | Spectral resolution = 3000 to 4000 [SCRD §2.1.5.1, §2.1.5.3] |  | Spectral resolution of >3000 in IFUs | R=3000-4000. Ok.
1.5 | Narrow field imaging: diffraction limited at J, H, K [SCRD §2.1.5.3] | Wavefront error 170 nm or better | Nyquist sampled pixels at each wavelength | 170 nm wfe
1.6 | Encircled energy at least 50% in 70 mas for sky coverage of 30% (see 1.11) [SCRD §2.1.5.2] | Wavefront error sufficiently low (~170 nm) to achieve the stated requirement in J, H, and K bands. | IFU spaxel size: either 35 or 70 mas, to be determined during the design study for the multiplexed IFU spectrograph | 50% EE in 70 mas
1.7 | Velocity determined to ≤ 20 km/sec for spatial resolutions of 70 mas | PSF intensity distribution known to ≤ 10% per spectral channel.
1.8 | IFU field of view ≥ 1” x 3” in order to allow sky background measurement at same time as observing a ~1” galaxy [SCRD §2.1.5.1] | Each MOAO IFU channel passes a 1”x3” field. | Each IFU unit’s field of view is 1” x 3” | 1"x3" IFU
1.9 | Simultaneous sky background measurements within a radius of 3” with the same field of view as the science field [SCRD §2.1.5.1] | See #1.8
1.10 | Relative photometry to ≤ 5% for observations during a single night | Knowledge of ensquared energy in IFU spaxel to 5%. Telemetry system that monitors tip/tilt star Strehl and other real-time data to estimate the EE vs. time, or other equivalent method to determine PSF to the required accuracy.
1.11 | Sky coverage ≥30% at 170 nm wavefront error, to overlap with data sets from other instruments and telescopes [SCRD §2.1.5.2] | Infrared tip/tilt sensors with AO correction of tip/tilt stars |  | 30% sky coverage
1.12 | Should be able to center a galaxy to ≤ 10% of science field of view
1.13 | Should know the relative position of the galaxy to ≤ 20% of spaxel size
1.14 | Target drift should be ≤ 10% of spaxel size in 1 hr
1.15 | The following observing preparation tools are required: PSF simulation and exposure time calculator
1.16 | The following data products are required: calibrated spectral data cube [SCRD §2.1.5.3] |  |  | Calibrated data cubes
2 | Nearby AGNs |  | Vis & NIR imagers, NIR IFU
2.1 | Number of targets required: to be specified in future versions of the SCRD [SCRD §2.2.3]
2.2 | Required wavelength range 0.85 – 2.4 microns [SCRD §2.2.3] |  |  | 0.85-2.4 um
2.3 | Required spatial sampling at least two resolution elements across gravitational sphere of influence. [SCRD §2.2.2] | 50% enclosed energy radius < ½ gravitational sphere of influence. Wavefront error requirement to be specified in future versions of this document. | Spectral and imaging pixels/spaxels < ½ gravitational sphere of influence (in the spatial dimension) | Sampling?
2.4 | Required field of view for both spectroscopy and imaging > 10 radii of the gravitational sphere of influence. [e.g., SCRD §2.2.4 Figure 3] |  | Will need to get sky background measurement as efficiently as possible. For IR, consider using a separate d-IFU on the sky. | FOV?
2.5 | Required SNR for spatially resolved spectroscopy of the central black hole region using stellar velocities > 30 per resolution element [SCRD §2.2.3] | PSF stability and knowledge requirements will be discussed in future releases of the SCRD | Spectral resolution R ~ 3000-4000 with at least two pixels per resolution element; detector limited SNR performance. Spatial sampling at least two resolution elements across the gravitational sphere of influence
2.6 | Required observation planning tools: PSF simulation tools to plan for observations of Seyfert 1 galaxies which have strong central point sources
2.7 | Required data reduction pipeline for IFU
3a | GR effects in the Galactic Center - Astrometry |  | NIR imager
3a.1 | Astrometric accuracy ≤ 100 µas for objects ≤ 5” from the Galactic Center [SCRD §2.3.8.1] | High Strehl to reduce confusion limit: rms wavefront error ≤ 170 nm at G.C. IR tip/tilt sensors. Means of aligning and measuring position of tip-tilt sensors so that they permit astrometric accuracy of ≤ 100 µas. Means of preventing WFS-blind field-distortion modes (if multi-DMs are in series). Will require ADC. Need astrometric error budget in order to determine ADC requirements. | Nyquist sampling at H and K. Instrument distortion characterized and stable to ≤ 100 µas. | 0.1 mas astrometry
3a.2 | Observing wavelengths: H and K-band [SCRD §2.3.9] | Transmit H and K band to science instrument
3a.3 | Field of view ≥ 10” x 10” for imaging [SCRD §2.3.9] | Science path shall allow an unvignetted 10” x 10” field. |  | 10" FOV
3a.4 | Ability to construct 40’x40” mosaic to tie to radio astrometric reference frame [SCRD §2.3.5] Required accuracy needs to be determined
3a.5 | The following observing preparation tools are required: PSF simulation as function of wavelength and seeing conditions, exposure time calculator.
3a.6 | The following data products are required: Calibrated PSF, data reduction pipeline, accurate distortion map (see 3a.1) [SCRD §2.3.5] |  |  | Calibrated PSF
3b | GR effects in the Galactic Center - Radial Velocities |  | NIR IFU or d-IFU
3b.1 | Radial velocity accuracy ≤ 10 km/sec for objects ≤ 5” from the Galactic Center [SCRD §2.3.8.2] | 170nm wavefront error at G.C. PSF estimation sufficient to measure a radial velocity to 10 km/sec. [suggestions from SCRD §2.3.8.2] | Spectral resolution ≥ 4000 Calibration of one IFU relative to other ones sufficient to permit 10 km/sec radial velocity measurement | R>4000
3b.2 | Observing wavelengths H, K-band [SCRD §2.3.6] | Transmit H, K band to science instrument
3b.3 | Spatial sampling ≤ 20 mas (H) or 35 mas (K) to control confusion within IFU field of view [SCRD §2.3.6] |  | 20 and 35 mas spaxel scales at H and K respectively | Drives IFU sampling (20 mas at H)
3b.4 | Field of view ≥ 1” x 1” [SCRD §2.3.6] |  | Field of view ≥ 1” x 1” | >1"x1" IFU
3b.5 | The following observing preparation tools are required: PSF simulation as function of wavelength and seeing conditions, exposure time calculator.
3b.6 | The following data products are required: IFU pipeline for wavelength/flux calibration [SCRD §2.3.6]
4 | Planets around Low Mass Stars |  | NIR imager, NIR IFU
4.1 | Target sample 1: Old field brown dwarfs out to distance of 20 pc. Sample size several hundred, desired maximum survey duration 3 yrs (practical publication timescales). [SCRD §2.4.3] | Observe 20 targets per night (each with e.g. 20 min integration time). Guide on a tip-tilt star with H=14. Talk to Mike Liu re guide star magnitude. | Near infrared imager (possibly with coronagraph). Survey primary stars at J- and H‑band.
4.2 | Target sample 2: Young (<100 Myr) field brown dwarfs and low-mass stars to distance of 80 pc. Sample size several hundred, desired maximum survey duration 3 yrs. [SCRD §2.4.3] | Observe 20 targets per night (each with e.g. 20 min integration time). | Near infrared imager (possibly with coronagraph). Survey primary at J- and H‑band. Could benefit from dual- or multi-channel mode for rejecting speckle suppression, but not essential for this program.
4.3 | Target sample 3: solar type stars in nearby star forming regions such as Taurus and Ophiuchus, and young clusters @ 100 to 150 pc distance. Bright targets (on-axis tip-tilt generally possible: V=14-15, J=10-12). Sample size several hundred, desired maximum survey duration 3 yrs. | (May not require LGS if there is a good enough near-IR wavefront sensor available). | Possible dual- or multi-channel mode for speckle suppression. Alternatively an IFU would help, provided it is Nyquist sampled at H and has FOV > 1 arc sec. Min. IFU spectral resolution is R~100. May need IR ADC for imaging or coronagraphic observations (J or H bands); typical airmass is 1.7 for Ophiuchus.
4.4 | Companion Sensitivity Sample 1: assume no companions beyond 15 AU. Targets at 20 to 30 pc; companion distribution peaks at 4 AU = 0.2"; this yields 2 MJupiter planets at a 0.2" separation with contrast ÄH = 10. Planets have H=24, J=24.7. Parent stars are 2MASS Brown Dwarfs with H=14. [SCRD §2.4.2.1] | Excellent (<10nm) calibration of both initial LGS spot size and quasi-static non-common path aberrations, especially at mid-spatial-frequencies. Needs algorithms such as phase retrieval or speckle nulling (on a fiber source + good stability). Small servo-lag error (<30nm) to avoid scattered light at 0.2 arc sec. Source: Error budget and simulations by Bruce Macintosh. | Inner working angle of 6 λ/D general-purpose coronagraph with a contrast of 10-6. Detailed design of coronagraph will take place during PDR stage. Speckle suppression capability (multi-spectral imaging); dual-channel imager; stability of static errors ~5nm per sqrt(hr) for PSF subtraction or ADI. | If this is our only companion sensitivity requirement could we consider not providiing an IFU?
4.5 | Companion Sensitivity Sample 2: Parent stars are T Tauri, J=11. A 1 MJupiter planet is at 300K, J=22, (2 MJupiter is J=19.5). This distribution could have a wider distribution of binaries a) 0.1" separation, ÄJ = 8.5 (2MJ) b) 0.2" separation, ÄJ = 11 (1MJ) c) Goal ÄJ = 11 at 0.1" separation (1MJ) based on properties of the planets you want to look for. [SCRD §2.4.2.2] | Same as #4.4 | a) 6 λ/D general-purpose coronagraph b) 6 λ/D general-purpose coronagraph c) (Goal) Not achievable with a general purpose coronagraph. May need small inner working distance (2l/D) coronagraph (non-redundant aperture masking is an interesting approach for this, limits currently unknown, probably requires low read noise in science detector). Speckle suppression capability (multi-spectral imaging); dual-channel imager; stability of static errors ~5nm per sqrt(hr) for PSF subtraction or ADI. | Change to goal
4.6 | Goal: Companion Sensitivity Case 3: at 5 Myr , 1 Msun primary; a) goal ÄJ = 13.5 to see 1 MJupiter or b) goal ÄJ = 9 for 5 MJupiter. 0.07" is needed. For apparent magnitudes of parent stars see 4.3 | Excellent (10-20nm) calibration of both initial LGS spot size and quasi-static non-common path aberrations, at both low- and mid-spatial-frequencies. Needs algorithms such as phase retrieval or speckle nulling (on a fiber source + good stability). Small servo-lag error (<30nm) to avoid scattered light at 0.2 arc sec. Tomography errors 20-30nm. Source: error budget and simulations by Bruce Macintosh. | Requires multi- λ speckle suppression; very small inner working angle coronagraph (2 λ/D); static errors in 5-10nm range.
4.7 | Sensitivity of H=25 for 5-sigma detection in 20 minutes, at 1 arcsec separation from primary star. (Brown dwarf targets are limited by sky background at larger angles, of order ~1 arcsec). [SCRD §2.4.5.9] | Sufficiently high throughput and low emissivity to permit detecting H=25 in 20 minutes at 5 sigma above background.
4.8 | H-band relative photometry (between primary and companion): accuracy ≤ 0.1 mag for recovered companions (to estimate mass of the companion); goal of measuring colors to 0.05 mags (0.03 mag per band) to measure temperatures and surface gravities sufficiently accurately (to ~10%). [SCRD §2.4.5.4] | Diagnostics on AO data to measure Strehl fluctuations if it takes a while to move on and off the coronagraph (a possible more attractive solution is a specialized coronagraph that simultaneously images the primary) | Induced ghost images of primary; or rapid interleaving of saturated and unsaturated images; or a partially transparent coronagraph
4.9 | Requirement: Astrometric precision 2 mas (~1/10 PSF) relative between primary and planet, for initial rejection of background objects. [SCRD §2.4.5.5] Goal: For measuring orbits of nearby field objects, want 0.5 mas to measure masses to 10%. Note this gives you mass of primary star. Could be combined with Doppler measurements if that’s practical for the brighter objects. | Ways to do this: b) Induced ghost image method. Needs a wire grating ahead of the coronagraph, or use DM to induce ghost images. (papers by Marois et al. 2006, ApJ, 647, 612; Sivaramakrishnan & Oppenheimer 2006, ApJ, 647, 620). a) Position stability requirement for star behind coronagraph (e.g., stable to 0.5 or 2 mas over 10 min.). | Stability of distortion as required for 0.5 or 2 mas. Also want ghost images of primary (as for photometry #4.8) in order to locate it accurately relative to planet.
4.10 | Efficiency: 20 targets per night (30 goal) [SCRD §2.4.6.2] | AO system must be able to absolutely steer objects so they land on the coronagraph. This implies 5 mas reproducibility of field steering –or lock the tip/tilt to this accuracy relative to coronagraph field stop. Final requirement will depend on the details of the coronagraph (5 mas is consistent with GPI modeling).
4.11 | Observing wavelengths JHK bands (strong goal: Y and z for companion temperature characterization) [SCRD §2.4.4, §2.4.7] | Transmit JHK to science instrument. Goal: Y and z. | JHK filters. Methane band filters for rapid discrimination, Y and z, and/or a custom filter for early characterization. | JHK
4.12 | Able to register and subtract PSFs (with wavelength, time, etc.) for post-processing to get rid of residual speckles. Subtraction needs to be sufficient enough to meet req. #4.4. | PSF knowledge and/ or stability to meet req. #4.4. | At least 1.5 x better than Nyquist sampled at J (goal Y) | PSF calibration
4.13 | Field of view: must see companions at 100 AU scales at 30 pc (goal 20 pc) [SCRD §2.4.5.3] |  | Field of view 3" radius (goal 5" radius)
4.14 | Characterization of companion [SCRD §2.4.4] |  | a) R ~150 IFU, sub-Nyquist sampling spectrograph, or if above not available, b) Nyquist spatial sampling IFU, R ~ 4,000, OH suppressing). c) or narrow-band filters. All must be sensitive to J = 22 or 23 in ~3 hrs. | IFU or narrow band filters
4.15 | Sky Coverage >30%. (Survey several hundred Brown Dwarfs to H=15 of the ~1000 known targets.) [SCRD §2.4.7] | Technical field for low-order wavefront guidestar pickoff large enough to achieve 30% sky coverage at high galactic latitude. Ability to acquire and track 3 tip/tilt stars. (More lenient if parent star can be used as one of the three TT stars.) Or ability to measure everything sufficiently with a single H=15 TT star (pyramid sensors). |  | >30% sky coverage
4.16 | The following observing preparation tools are required: guide star finder for high proper-motion stars
5 | Asteroid Companions Survey |  | Vis & NIR imagers
5.1 | The companion sensitivity shall be ÄJ ≥ 5.5 mag at 0.5” separation for a V ≤ 17 asteroid (J≤ 15.9) (asteroid size < 0.2”) with a proper motion of ≤ 50 arcsec/hour [ScRD §2.5.4.6] | The asteroid can be used as tip/tilt guidestar (proper motion of ≤ 50 arcsec/hour). The AO system has sufficient field of view for objects and for their seeing disks (>3 arcsec, see # 5.6). The tip-tilt residual error will be less than 10 mas (limited by resolved primary) while guiding on one V=17 (J =15.9) object with relative motion of 50 arcsec/hr (14 mas/sec). The AO system has sufficient Strehl to achieve this contrast ratio and sensitivity in 15 min exposure time. KAON 529 suggests that 170nm wavefront error will suffice. | Near-IR imager
5.2 | J-band relative photometric accuracy (between primary and companion) of 5% at 0.6” for ÄJ = 3 for a V ≤ 17 (J≤ 15.9) asteroid (asteroid size < 0.2”) with a proper motion of ≤ 50 arcsec/hour [ScRD §2.5.4.4] |  | Near- IR imager (no coronagraph because many asteroids will be resolved)
5.3 | Target sample ≥ 300 asteroids in ≤ 4 yr. [SCRD §2.5.3 ¶4] Leads to requirement of ≥ 25 targets per 11 hour night. [SCRD §2.5.5.2] | Assumes 3 good nights per year. Needs high observing efficiency: Able to slew to new target and complete the entire observation within 26 minutes on average.
5.4 | Observing wavelengths I through H bands, for optimum companion sensitivity [Source: KAON 529]. J band is best when seeing is good. H band could be used when seeing is poor. [SCRD 2.5.6.6] |  | Visible and IR imagers.
5.5 | Spatial sampling ≤ Nyquist at each observing wavelength. [SCRD §2.5.6.4] Pixel sampling of l/3D optimal for photometry and astrometry [KAON 529]. |  | Spatial sampling ≤ Nyquist at the observing wavelength. Pixel sampling of l/3D is optimal at J through H-bands, and l/2D at I through z-band for both photometry and astrometry [see KAON 529].
5.6 | Field of view ≥ 3” diameter [SCRD §2.5.6.2] | AO system passes a >3” unvignetted field of view | Imager fields of view ≥ 3”
5.7 | The following observing preparation tools are required: guide star finder for asteroids too faint to use as the only TT star, PSF simulation as function of wavelength and seeing conditions. | Guide star finder tool. PSF simulation tool (predict energy and width of central core to within 10%).
5.8 | The following data products are required: Access to archive with proper identification in World Coordinate System (to within 1 arc sec or better) and with associated calibrated PSF. | Calibrated PSF capability. Accuracy requirement will be discussed in future releases of the SCRD document. Ability to collect AO telemetry data to support the required PSF calibration. | FITS header system capable of handling non-sidereal offsets in reporting object coordinates in the World Coordinate System to within 1 arc sec or better. | PSF calibration
5.9 | Observing requirements: Observer present either in person or via remote observing rooms, because real-time observing sequence determination is needed. | Classical observing mode or service mode with active observer participation. Remote observing capabilities must allow frequent real-time decisions by observer.
6 | Asteroid Companions Orbit Determination |  | Vis & NIR imagers
6.1 | Companion sensitivity in the near-IR. Same as #5.1 | Same as #5.1 | Near-IR imager.
6.2 | The companion sensitivity in the visible shall be ÄI ≥ 7.5 mag at 0.75” separation for a V ≤ 17 (I ≤ 16.1) asteroid (asteroid size < 0.2”) with a proper motion of ≤ 50 arcsec/hour [ScRD §2.5.4.6] |  | Visible Imager. Optimum visible wavelength is I through z bands per KAON 529. Note that if the near-IR imager extends down to I band, a separate visible imager would not be needed for this science case.
6.3 | Photometric accuracy: Same as #5.2 | Same as #5.2
6.4 | I-band relative astrometric accuracy of ≤ 1.5 mas for a V ≤ 17 (J ≤ 15.9) asteroid (asteroid size < 0.2”) with a proper motion of ≤ 50 arcsec/hour [SCRD §2.5.4.5] | Non-sidereal tracking accuracy sufficiently small to achieve I-band astrometric accuracy ≤ 1.5 mas for a V ≤ 17 (J ≤ 15.9) asteroid with a proper motion of ≤ 50 arcsec/hour | Uncalibrated detector distortion sufficiently small to achieve I-band astrometric accuracy ≤ 1.5 mas for a V ≤ 17 (J ≤ 15.9) asteroid
6.5 | Target sample size of ≥ 100 asteroids in ≤ 3 years. [SCRD §2.5.3 ¶4] Leads to requirement of ≥ 25 targets in an 11 hour night. [SCRD §2.5.5.2] | Needs high observing efficiency: Able to slew to new target and complete the entire observation within 25 minutes on average. Will generally only observe at one wavelength (the one that gives the best astrometric information).
6.6 | Observing wavelengths = I, z, J, H bands. (Note: R-band may become a future requirement if R-band Strehl > 15%) [SCRD §2.5.6.6] |  | Imager(s) covering range I, z, J, H bands. Note that if the near-IR imager extends down to I band, a separate visible imager would not be needed for this science case. | I-H bands
6.7 | Spatial sampling same as #5.5 |  | Same as #5.5
6.8 | Same as #5.6 | Same as #5.6 | Same as #5.6
6.9 | Same as #5.7 | Same as #5.7
6.10 | Same as #5.8 | See #5.8
6.11 | Observing requirements: 7 epochs per target [SCRD §2.5.3 ¶4] | Observing model needs to accommodate split nights or some level of flexibility.
7 | QSO Host galaxies |  | Vis & NIR imagers, NIR IFU
7.1 | Number of targets required: to be specified in future versions of the SCRD | Sky coverage fraction >30% for 50% enclosed energy within 0.05 arc sec at J band
7.2 | Required wavelength range: 0.85 – 2.4 microns |  | Near IR IFU spectrograph; near IR and visible imagers. | 0.85-2.4 um
7.3 | Required spatial resolution will be discussed in a future release of this document. Will be determined by considerations of PSF subtraction accuracy. Hence required resolution will be higher than in the high-z galaxy science case. | Desirable to use central QSO point source as one of the tip-tilt reference stars, if possible. | PSF must be oversampled in order to achieve required subtraction accuracy. Quantitative requirements will be discussed in future releases of the SCRD.
7.4 | Photometric accuracy and PSF knowledge required for subtracting the central point source in order to characterize the host galaxy must be adequate to obtain host galaxy colors to 20% for a contrast ratio of up to 200 at a distance of ½ arc sec from the point source. | Requires excellent PSF stability and knowledge; future releases of the SCRD will discuss the quantitative requirements. Will have implications for required AO wavefront error, AO stability, and required signal to noise ratio. | Required calibration stability and accuracy, zero-point stability and knowledge, quality of flat-fielding will be discussed quantitatively in future releases of the SCRD. PSF must be oversampled in order to achieve required subtraction accuracy. Quantitative requirements will be discussed in future releases of the SCRD. | PSF knowledge
7.5 | SNR for spatially resolved spectroscopy of the host galaxy will be determined by accuracy of PSF subtraction and by minimization of scattered light from the central point source. |  | May benefit from specialized coronagraph design to block light from central point source.
7.6 | Required observation planning tools (e.g. guide stars); PSF simulation tools to plan for whether PSF subtraction will be good enough to see the host galaxy
7.7 | Required data reduction pipeline for IFU
8a | Distant galaxies lensed by galaxies - imaging studies |  | Vis & NIR imagers
8a.1 | Sensitivity: SNR ≥ 3 per pixel (100 per source) for a z = 1 – 2 galaxy in an integration time ≤ 1/2 hour. | Background due to emissivity less than 30% of unattenuated (sky + tel).
8a.2 | Target sample size of ≥ 200 galaxies, with density on the sky of 10 per square degree. Survey time ~ 3 years. | Overhead less than 10 min between targets. | 10 per square degree implies that you will only be able to observe one target at a time – average of 1 in every ~19’x19’ patch.
8a.3 | Observing wavelengths = I through K (to 2.4 µm). Emphasis is on shorter wavelengths. Thermal part of K band less important. [SCRD §3.2.6.5] |  |  | I-K band
8a.4 | Spatial resolution better than 50 mas at J band, for 30% sky coverage. | Need a good model of the PSF or a simultaneous image of a PSF star. Need a figure of merit for goodness of the PSF: how well the model fits the “real” PSF in two dimensions. Will quantify in future releases of the SCRD. | Nyquist sampling of pixels at each wavelength. | 50 mas at J
8a.5 | Field of view > 15” diameter for survey. Bigger is better. Some degradation between center and edge of field is tolerable. Will quantify in future releases of the SCRD. [SCRD §3.2.6.2] |  |  | 15" FOV
8a.6 | Relative photometry to ≤ 0.1 mag for observations during a single night [SCRD §3.2.4.4]
8a.7 | Absolute photometry ≤ 0.3 mag [SCRD §3.2.4.4]
8a.8 | Sky coverage at least 30% with enclosed energy radius within 0.07 arc sec at H or K. [SCRD §3.2.4.9] |  |  | 30% sky coverage
8a.9 | Dithering and offset considerations: 1) Initially should be able to center a galaxy to ≤ 10% of science field of view. 2) Should know the relative position of the galaxy after a dither to ≤ 20% of pixel size.
8a.10 | The following observing preparation tools are required: PSF simulation and exposure time calculator
8a.11 | The following data products are required: accurate distortion map (to 1% of the size of the galaxy, or 0.01 arc sec rms) |  |  | Distortion map
8b | Distant galaxies lensed by galaxies - spectroscopic studies |  | NIR IFU or d-IFU
8b.1 | SNR ≥ 10 for a z = 1 – 2 galaxy in an integration time ≤ 3 hours for a Gaussian width 20 km/sec Gaussian width (50 km/sec FWHM) with a spatial resolution of 50 mas | Background due to emissivity less than 30% of unattenuated (sky + tel). | R ~ 5000 (or whatever is needed to achieve 20 km/sec sigma on these targets) | R~5000
8b.2 | Target sample size of ≥ 50 galaxies, with density on the sky of 10 per square degree. Survey time ~ 3 years. | Number of IFUs: at least one, plus preferably one to monitor the PSF and one to monitor the sky. The extra two IFUs could be dispensed with if there were other ways to monitor the PSF and the sky background.
8b.3 | Observing wavelengths = J, H and K (to 2.4 µm) required, with emphasis on J band. Goal: also use z and I bands. [SCRD §3.2.6.5] |  |  | J-K
8b.4 | Spectral resolution: whatever is needed to get 20 km/sec radial velocity Gaussian sigma
8b.5 | Spatial resolution 50 mas at J band |  |  | 50 mas at J
8b.6 | Velocity determined to ≤ 20 km/sec Gaussian sigma for spatial resolutions of 50 mas | Required level of PSF knowledge will be assessed in future releases of the SCRD.
8b.7 | Field of view: Typical lens is 2 to 6 arc sec diameter. For IFU fields of view smaller than the lens size, one would use mosaicing. Desirable to take in blank sky in addition to the lens (if possible). Requirement: FOV ³ 3” diameter. Goal: ³ 4” diameter. [SCRD §3.2.6.2] |  | Requirement: IFU FOV ³ 3” diameter. Goal: ³ 4” diameter. | 3" FOV IFU
8b.8 | Simultaneous sky background measurements |  | Preferably sky determination within the field of view of the IFU. Less preferably, through use of offsetting to sky or via a separate IFU looking at sky.
8b.9 | Relative photometry to ≤ 0.1 mag for observations during a single night [SCRD §3.2.4.4]
8b.10 | Absolute photometry ≤ 0.3 mag [SCRD §3.2.4.4]
8b.11 | Sky coverage at least 30% with enclosed energy radius within 50 mas at J band. [SCRD §3.2.4.9] |  |  | 30% sky coverage
8b.12 | Dithering and offset considerations: 1) Initially should be able to center a galaxy to ≤ 10% of science field of view. 2) Should know the relative position of the galaxy after a dither to ≤ 20% of spaxel size.
8b.13 | Target drift should be ≤ 10% of spaxel size in 1 hr
8b.14 | The following observing preparation tools are required: PSF simulation and exposure time calculator
8b.15 | The following data products are required: calibrated spectral data cube
9a | Distance galaxies lensed by clusters - imaging studies
9b | Distant galaxies lensed by clusters - spectroscopic studies
10 | Astrometry science in sparse fields
11 | Resolved stellar populations in crowded fields
12 | Debris disks
13 | Young stellar objects
14 | Asteroid size, share & composition |  | Vis & NIR Imagers, NIR IFU
14.1 | Target sample size of ≥ 300 asteroids in ≤ 3yrs years. < 10 targets in an 11 hour night [SCRD §3.6.3] | #6.5 is stricter requirement.
14.2 | Observing wavelengths 0.7 – 1.0 µm. Strong preference for R band because optimum to obtain shape of asteroid. [SCRD §3.6.6.6] | AO system must pass 0.7 to 1.0 micron wavelengths | Imagers (R through J band) with narrow-band filters or slit spectrograph (R~100), or possibly visible IFU (R~100). | 0.7-1.0 um
14.3 | Spatial sampling same as #5.5 | Same as #5.5 | Same as #5.5
14.4 | Field of view ≥ 3” diameter [SCRD §3.6.6.2] | Same as #6.8 | Same as #6.8 | 3" FOV
14.5 | Ability to measure the spectral slope with R ~ 100 at 0.85-1.0 mm [SCRD §3.6.6.7] |  |  | 0.85-1.0um
14.6 | Ability to measure the SO2 frost bands at R=1000 (R=5000 is acceptable) at 1.98 and 2.12 mm, crystalline ice band at 1.65 microns. [SCRD §3.6.6.7] |  | Spectroscopic imaging at R~1000 to 5000 in the H and K bands. | H&K R~1000
14.7 | Same as #5.7 | Same as #5.7
14.8 | Same as #5.8 | Same as #5.8
15 | Gas Giants |  | Vis & NIR imagers, NIR IFU or d-IFU
15.1 | Capability of tracking a moving target with rate up ≤ 50 arcseconds per hour (14 mas/second) [SCRD §3.7.5.1]
15.2 | Capability of using at least one tip-tilt star that is moving with respect to the (moving) target planet. (For example, a moon of Jupiter or Saturn) [SCRD §3.7.5.1] | Motion of low order wavefront sensor to track tip-tilt star. |  | Differential tracking
15.3 | Ability to acquire Io within 5” of Jupiter and to track it to within 2.5” of Jupiter. Note that this is a goal but perhaps not a rigid requirement: we know we can acquire within 10” today. | May require either a diaphragm or a filter to attenuate the light from Jupiter. | See AO derived requirement.
15.4 | Sensitivity: comparable to the current Keck system
15.5 | Absolute Photometric accuracy: comparable to the current Keck system (≤ 0.05 mag) [SCRD §3.7.4.4] | PSF knowledge | Detector flat-fielding requirements, linearity, etc will flow down from required photometric accuracy.
15.6 | Targets: Jupiter and Saturn systems, with special focus on Io and Titan | AO system capable of working in the presence of scattered light from nearby extended objects; NGS option for bright moons | Jupiter & Saturn: near-IR imager from 0.8-2.4 µm Io: IFU 0.8-2.4 µ Titan: IFU 0.8-2.4 µm
15.7 | Observing wavelengths I, z/Y, J, H, K [SCRD §3.7.6.5] | AO system must pass these wavelengths to science instruments. | Near- IR imager and IFU spectrometer, l= 0.8-2.4 µm | I-K band
15.8 | Spatial sampling: for imager, ≤ Nyquist at the observing wavelength |  | For imager, spatial sampling ≤ Nyquist at the observing wavelength. For IFU, spatial sampling ~l/D. | Nyquist
15.9 | Imager field of view ≥ 30” diameter at K band, ≥ 20” diameter at J and H bands (goal 30”) [SCRD §3.7.6.1] | AO system passes a >30” unvignetted field of view | Imager field of view ≥ 30” diameter at K band, ≥ 20” diameter at J and H bands (goal 30”) | 30" FOV at K
15.10 | IFU field of view as large as possible, up to 15” (Jupiter’s diameter is 30”, Great Red Spot is 13” diameter) [SCRD §3.7.6.1] |  | If IFU FOV is only a few arc sec, desirable to be able to place different IFUs as close together as possible. No firm numerical requirement. | Large IFU
15.11 | Moons are very bright: do not allow saturation. Typical brightness: 5 mag per square arc sec. |  | Either need to use neutral density filters, or have a fast shutter, or have a detector with large wells or very short exposure times (and low read noise). Note: these observations will have high overhead.
15.12 | The following observing preparation tools are required: PSF simulation, target ephemeris, exposure time calculator to enable choice of ND filter and exposure time.
15.13 | The following data products are required: Calibrated PSF. |  |  | PSF calibration
15.14 | Observing requirements: Io and Titan are time domain targets; Io requires ≤ 1 hr notification of volcano activity. Typical timescales for clouds on Titan are of order days to weeks.
16 | Ice Giants |  | Vis & NIR imagers, NIR IFU or d-IFU
16.1 | Capability of tracking a moving target with rate up ≤ 5.0 arcseconds per hour (1.4 mas/sec) [SCRD §3.8.5.1] | • The planet can be used as tip/tilt guidestar (proper motion of ≤ 5.0 arcsec/hour). • The AO system requires sufficient field of view for planets and for their seeing disks (>5 arcsec). • The tip-tilt residual error will be less than 10 mas (limited by resolved primary) while guiding on one planet at 5.0 arcsec/hr (1.4 mas/sec).
16.2 | Sensitivity: comparable to the current Keck system |  | Near-IR imager, 0.8 - 2.4 µm
16.3 | Photometric accuracy: comparable to the current Keck system [SCRD §3.8.4.5] |  | Near- IR imager
16.4 | Targets: Uranus and Neptune systems. Observations of atmospheric vertical structure will require a near-IR IFU, to be described in more detail in a future release of the SCRD. | AO system (both LGS and NGS) capable of correcting on extended objects. • Uranus = 3.4 arcsec • Neptune = 2.3 arcsec | Near-IR imager, 0.8 – 2.4 µm, Near-IR IFU 1.0 – 2.4 µm | 0.8-2.4 um imaging 1.0-2.4 um IFU
16.5 | Observing wavelengths: J, H, K [SCRD §3.8.6.5] |  | Near- IR imager, Near-IR IFU | J-K
16.6 | Spatial sampling: ≤ Nyquist at the observing wavelengths |  | Spatial sampling ≤ Nyquist at the observing wavelength | Nyquist
16.7 | Imager field of view: ≥ 15” diameter [SCRD §3.8.6.2] | AO system passes a >15” unvignetted field of view | Imager fields of view ≥ 15” | 15" FOV
16.8 | IFU field of view: as large as possible, up to ≥ 15” diameter [SCRD §3.8.6.2] |  | If IFU FOV is only a few arc sec, desirable to be able to place different IFUs as close together as possible. No firm numerical requirement. | Large IFU
16.9 | Spectral resolution: R ≥ 3000 to resolve methane absorption features. [SCRD §3.8.6.6] |  | Near-IR IFU with R~3000 | R>3000
16.10 | Observing requirements: one run per semester with at least 4 contiguous (partial) nights; both targets can be studied during one run
16.11 | The following observing preparation tools are required: PSF simulation, target ephemeris, exposure time calculator to enable choice of ND filter and exposure time.
16.12 | The following data products are required: Calibrated PSF. |  |  | PSF calibration
16.13 | Observing requirements: some science goals would be well suited to queue or service observing modes
17 | Backup Science - NGS |  | NIR imager, NIR IFU
17.1 | NGS mode. NGS as a backup observing mode for when conditions restrict propagation of the lasers.
17.2 | Sky coverage ≥5% to ensure at least one-sixth of the off-axis LGS targets will still be observable if it is necessary to go to an NGS backup mode. | Assuming b=30º, For 5% sky coverage: R=14 mag guide star with 60” diameter field of regard (FOR) R=15 mag guide star with 45” diameter FOR [Keck Observatory Report No. 208, p. 4-100] |  | 5% sky coverage
17.3 | Capability to switch between NGS and LGS modes in ≤ 15 minutes (not including target acquisition) to enable flexibility if conditions change.
17.4 | Sensitivity. SNR ≥ 10 for a z = 2.6 galaxy in an integration time ≤ 3 hours for a spectral resolution R = 3500 with a spatial resolution of 50 mas | Sufficiently high throughput and low emissivity of the AO system science path to achieve this sensitivity. Background due to emissivity less than 30% of unattenuated (sky + tel).
17.5 | Observing wavelengths = J, H and K (to 2.4 µm) | AO system must transmit J, H, and K bands | Infrared single IFU and imager designed for J, H, and K. | J-K
17.6 | Spectral resolution = 3000 to 4000 |  | Spectral resolution of >3000 in IFU | R=3000-4000
17.7 | Imaging: Nyquist sampled at H-band |  | Nyquist sampled IR imager (at H-band) | Nyquist
17.8 | Encircled energy 50% in 70 mas for a bright NGS guide star within 10 arc sec | Wavefront error sufficiently low (~170 nm) to achieve the stated requirement in J, H, and K bands. | Optimum spaxel size will be determined during a detailed study of the IFU instrument. | 50% EE in 70 mas
17.9 | If a new instrument: IFU field of view ≥ 1” x 3” to allow simultaneous background measurements while observing a 1” galaxy. OSIRIS FOV would be adequate. | Narrow relay passes 1”x3” field | If a new instrument: IFU field of view ≥ 1” x 3” to allow simultaneous background measurements while observing a 1” galaxy. OSIRIS FOV would be adequate. | 1x3" IFU
17.10 | Imager FOV ≥ 10” x 10” for galactic center and gravitational lensing science |  | Imager FOV ≥ 10” x 10” | 10" FOV
17.11 | Relative photometry to ≤ 5% for observations during a single night, provided the night is photometric | Knowledge of ensquared energy in IFU spaxel to 5%.
17.12 | Should be able to initially center a galaxy to ≤ 10% of science field of view
17.13 | Should know the relative position of the galaxy to ≤ 20% of spaxel or pixel size
17.14 | Target drift should be ≤ 10% of spaxel size in 1 hr
17.15 | The following observing preparation tools are required: NGS guide star finding tool; PSF simulation and exposure time calculator
17.16 | The following data products are required: calibrated spectral data cube

## Cost Est (then-yr)
|  |  |  | Actuals ($k) |  | Plan (Then-Year $k)
NGAO System | Start | End | Months | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | Total
System Design | 2007-10-01 | 2008-04-30 | 19 | 738.85 | 494.98 | [7 empty] | 1233.83
Preliminary Design | 2008-05-01 | 2010-04-30 | 24 |  | 214.171 | 1800 | 1634.4115 | [5 empty] | 3648.5825
Detailed Design | 2010-05-01 | 2012-04-30 | 24 |  |  |  | 1600 | 5500 | 3036.103 |  |  |  | 10136.103
Full Scale Development | 2012-05-01 | 2014-04-30 | 24 | [5 empty] | 7467.7962 | 13912.5042 | 9599.6279 |  | 30979.9283
Delivery & Commissioning | 2014-05-01 | 2015-02-28 | 10 | [7 empty] | 2222.8814 | 2300.6823 | 4523.5637
Additional Contingency = | [9 empty] | 300 | 400 | 444.6976 | 1144.6976
NGAO Total = |  |  | 101 | 738.85 | 709.151 | 1800 | 3234.4115 | 5500 | 10503.8992 | 14212.5042 | 12222.5094 | 2745.3799 | 51666.7052
NIR Imager | [5 empty] | 200 | 482.3164 | 907.0773 | 1044.4402 | 977.9293 | 156.8927 |  | 3768.6559
NIR IFU | [5 empty] | 50 | 239.7 | 606.22 | 1300 | 1400 | 1404.08 |  | 5000
Visible Imager | [7 empty] | 499.1975 | 1160.5686 | 948.1637 | 879.3249 | 162.3839 | 3649.6387
Contingency | [6 empty] | 50 | 300 | 600 | 1000 | 533.6589 |  | 2483.6589
NGAO Instrument Total = | [5 empty] | 250 | 772.0164 | 2312.4948 | 4105.0088 | 4326.093 | 2973.9565 | 162.3839 | 14901.9536
Overall Total = |  |  |  | 738.85 | 709.151 | 2050 | 4006.428 | 7812.4948 | 14608.908 | 18538.5973 | 15196.4659 | 2907.7638 | 66568.6587
Years of inflation | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Annual inflation = |  |  |  | 1.035
Note on A13: peterw: Put 20% of total in as a place holder
Note on A11: peterw: Used $189.7k for 1st yr & $206.2k for 2nd yr from ATI proposal. $4M total ROM from Peter until I get something better from Sean. 12/9/08 - increased from $4.3M to $5M per suggestion from Sean
Note on A4: peterw: 2 month slip vs SDR
Note on A12: peterw: Slipped by 2 yr vs SA plan.
Note on A10: peterw: Mostly shifted 1 yr later, except for $200k in FY09
Note on A8: peterw: Increased NGAO contingency from 22 to 25%

## Proposed Savings
Cost Savings
ID # | Idea | Rationale | Explanation | $M
1 | Implement a single NIR IFU (tbd whether this is deployable) instead of the deployable multi-IFU | Extragalactic community was not supportive of multi-IFUs at the Keck 2008 Strategic Planning Meeting. SDR reviewers asked us to revisit the cost vs benefit. This allows us to make a large step toward the build-to-cost guidelines. We should evaluate any work that would prevent implementation of more IFU units in the future. | $14M d-IFU ROM in FY06 becomes ~$18M with inflation by FY12. Not included in $M column since not included in current cost estimate.
2 | Design correction: No PSF monitor DM & no TT mechanism on TWFS | Error in SDR estimate | $75k for PSF monitor DM & $20k for TT mechanism on TWFS. Include 25% contingency. Inflate to FY12 | 0.13627
3 | Reduce total laser power from 100W to 75W. | Preliminary analysis performed for 75 vs 50W of fixed asterism laser power: in worst case (ExoJup science case, 25% seeing) rms wfe increases from 160 to 167nm (J-band SR reduced by 6%). Assumes 56 subaps --> Reduces RTC complexity. Could still use 64x64 MEMS for static error correction based on TWFS. Relatively easy upgrade back to 100W total & 64 subapertures (64x64 LGS WFS lenslets & RTC changes). Separately calculate tip/tilt error in mas to evaluate science impact (RD). Evaluate if laser return/W would likely change vs power (RD). 1/7/9: SOR data indicates that it is fairly linear from 2W to 40W. 1/7/9: RD also looking at asymmetric 4 beacon fixed asterisms without PNS & will check with Lianqi about sky coverage. | $7.3M (FY08) budgeted for 100W of laser power at SDR. Assume 15% savings. Inflated to FY12. Evaluation of additional infrastructure cost savings: Reuse of the Keck I laser lab hardware provides a savings of $80k in HW & 400h in labor for laser lab I&T. The original estimate of $75k for pumps & $100k for a chiller for 150W of laser can be reduced by 1/2 for 75W of laser. Both of the above should be inflated to FY12. | 1.4774
4 | Reduce the number of LGS beacons from 9 to 7 | Only a minor performance degradation. Reduces the number of beam transport optics, the number of LGS WFS, the number of motion control degrees of freedom & the RTC complexity. | During FSD ~$40k hardware budgeted per beam transport channel. During FSD ~$170k budgeted for the hardware for each LGS WFS + 209k for total labor + $804k contingency (total of $2632k). Assume can save the hardware cost + 25% contingency. Inflated to FY12. | 0.60245
5 | Fix the central four LGS beacons | The absence of the d-IFS makes this more feasible. Could identify the fixed asterism which best optimizes the on-axis science correction versus atmospheric conditions. The three remaining beacons could be used to directly provide sharpening information on the TT stars or to enhance the on-axis correction or a compromise betwen the two. This removes the need for 4 movable LGS beacons & 4 movable LGS WFS. Removes 16 degrees of freedom. May be a design challenge to implement 3 with pick-offs with 4 fixed. | During FSD ~$40k hardware budgeted per beam transport channel. Assume can save 1/2 of this. During FSD ~$33k budgeted for the OSM hardware for each LGS WFS + 209k for total labor + $804k contingency (total of $2632k). Assume can save the hardware cost. Assume can save 25% contingency. Inflated to FY12. | 0.30409
6 | Assume lasers are on the elevation moving part of the telescope | All laser proposals to ESO commit to this requirement. Removes need for a tracking beam transport system. Enclosure likely smaller, although complexity of installing on El ring larger. The existing K2 laser enclosure is 1818kg. The ESO requirement on the allowable weight for a 25W laser is 1000kg; so at least 50W of laser could be handled on a single El ring face. Further analysis would be required to determine if 3 or 4 lasers could be supported on a single El ring face. | Reduce $40k hardware budgeted per beam tranport channel by 50% (add 25% contingency) Reduce $117k budgeted for launch facility during FSD by 10%. Remove $50k for beam transport design (add 25% contingency). Remove $50k for telescope I&T (add 25% contingency). Inflated to FY12 | 0.35768
7 | Only refrigerate the NGAO science path optics. Don't refrigerate the LGS WFS assembly. | Dramatically reduces the volume to be cooled vs cooling much of the Nasmyth platform. Where possible, benefit from the NFIRAOS design that follows this approach. Implement the design so that at least the LGS WFS assembly is outside the refrigerated area; implies lower cost components & easier maintenance. Instruments should mate to ports to seal the refrigerated area. Could potentially reuse much of existing AO enclosure for larger room. | $769k budget for AO enclosure & $926k for infrastructure mods for AO. WAG = $150k less for enclosure, $150k less for mods & $50k less for LGS WFS. Inflated to FY12 | 0.40163
8 | Do not implement the TWFS in the narrow field relay. Change the wide field relay TWFS from NIR to visible. | Already have a NIR TWFS in the wide field relay & a NGS is more likely to be found in this wider field. Any static non-common path errors in the narrow field relay will already be calibrated out via image sharpening on the narrow field science instruments. The only dynamic part is what the narrow field MEMS is doing and this can be known from the commands sent to this MEMs. Will require some extra work on the operational software side. The change to vis assumes that visible light is available here. Confirm that visible light available at LOWFS (DG) & that no significant performance hit (RD). 1/7/09: DG confirms vis light available with new switchyard. RD does not have a TWFS error budget but is not particularly concerned about a vis TWFS. During PD need to verify that LOWFS optics transmit 500-1000 nm or could potentially use LOWFS NIR detector also for TWFS. | $527k budgeted for the NGS/TWFS assembly. $45k budgeted for vis TWFS detector vs $100k for NIR det. Assume that 35% of budget is for TWFS. Inflated to FY11 since includes design work. | 0.26548
9 | Use single level cascaded relay design, including existing 349 actuator DM | This approach had been favored for an MCAO upgrade option. Single level allows the use of our spare Xinetics DM, but hysteresis is 30% at -15C. Single level removes the 2nd tier cost. | ~$90k estimate for 2nd tier. Estimate $20k for larger optics. Add 25% contingency. Inflated to FY12. | 0.10041
10 | Do not implement OSIRIS with NGAO. | Assumes NIR IFU will be more capable. Places significant constraints on the design to reuse an existing instrument (physical layout + control). Lose ability to multiplex, but would have to add cost to make either OSIRIS or IFU deployable. Allows OSIRIS to be used on other telescope. NOTE: Reconsider this if can lower combined cost of NIR IFU & OSIRIS to meet the science needs. | $150k budget for OSIRIS mods. $60k estimate for opto-mechanical design & implementation, science ops tools design & implementation, & integrating with NGAO (add 25% contingency). Inflated to FY12. | 0.25819
11 | Do not implement visible imager | Can't afford within build-to-cost. Extend NIR imager coverage down to 850 nm. | $3727k in then-year dollars + 20% contingency. Add $400k in then-year dollars + 20% contingency of $400k to NIR imager. | 3.9924
12 | Only implement 2 instead of 3 LGS WFS lenslet arrays (different subaperture sizes) | Reduced flexibility in exchange for reduced procurement costs. Reduced RTC & operations complexity. Reduced implementation, calibration, I&T effort. Need to evaluate performance impact. Could we go to just one lenslet array? (RD to evaluate; did 56 subap case - also look at 48 & 64 vs laser power) | Assume $25k savings (no solid basis). Inflate to FY12. | 0.028688
13 | Do not implement an ADC for the NGS WFS | NGS WFS not used for primary science. | Assume $50k savings (no solid basis). Inflate to FY12. | 0.057376
14 | Reduced switchyard opto-mechanics | No vis imager or OSIRIS means two less dichroics/mirrors & mounts. Also need to investigate whether other reductions are possible (e.g., fewer dichroic mechanisms & options). Evaluate if switchyard mechanism needed for NIR IFU (DG). | $17k in HW for vis imager dichroic & $3k HW for OSIRIS mirror. Assume $30k + $10k labor. Inflate to FY12. | 0.068851
15 | Savings in project management & systems engineering | The above savings amount to an ~ $4M cost reduction on the NGAO system or ~7.5% of the cost. It might be reasonable to assume we can reduce the management & systems engineering costs at some level due to the resulting reduced complexity. | $7.56M budgeted for project management & systems engineering. Assume a 3% reduction in this amount. Inflate to FY10 since includes design work. | 0.24295
16 | Fewer devices & controlled degrees of freedom | The above items result in reduced number of devices/stages to control & reduced complexity. Fewer devices: No d-IFS or IFS DM/TT to control since on-axis. 2 less LGS WFS & UTT mirrors. Fewer DOF: NGS TWFS (3 dof). LGS WFS (21). Vis imager (5). OSIRIS (1). NGS WFS ADC (3). Laser (36 dof, but need to add 8 missed dof). Overall this represents 28% of the motion control. | $1.453M budgeted for AO non-real time control & $0.777M for laser system control. EJ estimates ~$74k HW & 1500 hrs. Inflate to FY12. | 0.21057
17 | Reduced RTC complexity | No d-IFS MEMS/TT to control. 48x48 instead of 64x64 subapertures. 2 fewer LGS WFS & UTT. Scale of problem reduced from 9x64x64x(9x32x32) to 7x48x48x(3x32x32) for IFS science or a factor of 7. Scale reduced from 9x64x64x(3x32x32+64x64) to 7x48x48x(3x32x32+48x48) for narrow field science or a factor of 3. | $2.241M budgeted for RTC. Assume 2% reduction. $364k for FPGAs. Assume $100k savings. $2.5k for LGS WFS interface boards. Assume 2 gone. Inflate to FY12. DG to review this estimate. | 0.17192
| Higher MEMS costs | Gavel reports that the MEMS costs may be going up | $150 instead of $75/actuator. Assume 3x1000 & 1x4000 actuators. Inflate to FY12. | -0.60245
|  |  | Total Savings ($M) = | 8.074
|  |  | Amount under $60M cap = | 1.5053
Cost Savings Groupings |  | ID #s
1a | LGS Wavefront Sensing & Correction | 3,4,5,6,12,17
1b | Sky Coverage | related to above
2 | Science Instruments | 10,11
3 | Opto-mechanical Emissivity & Throughput | 7,9,14
4 | Auxiliary Wavefront Sensing | 8,13
5 | Other | 15,16
Notes:
Each one of the above proposals would work in the direction of simplifying NGAO, which also reduces risk.
Would like to be at least $2M below the $60M cap to allow for likely estimate growth during PD & DD, &/or higher contingency (closer to 30% on NGAO as goal).
We should look at other design simplifications & cost savings during the PD.
Should proceed with MRI proposal to allow us to implement the launch facility early, but shouldn't count on cost savings.
Should pursue collaboration with TMT and COO on the tip/tilt sensors, but should not count on this cost savings yet
Should continue with laser vendor preliminary designs to reduce laser cost uncertainty.
If we could pull in the schedule by 1 year during the detailed design we could save 3.5% of $54M or $2M.
Look for opportunities to make procurements with other groups to save money.
Above assumes IFU is fixed. No $ included for deployable.
Above does not include separate 32x32 MEMS for NIR IFU. Instead assumes IFU after 64x64 MEMS. Better AO performance & no thruput/emissivity impact since would have needed relay optics & 32x32 MEMS.
Discussed a further reduction to 50W laser total. This allows a clear future upgrade path with cost savings. Decided against for now since increases performance risk for 1st science.
Additional Actions:
Consider no ADCs for TT sensors. Seems unlikely that no ADC will be adequate. (RD). Conclusion (1/7/09): assume LOWFS ADCs.
Could we get away without refrigeration if we do the following? (PW,DG,RD) Replace K-mirror w/ multiple vertical rotators (1 ea for HOWFS, LOWFS + NIR imager, NGS WFS, NIR IFU). Single relay w/ 48x48 or 56x56 DM instead of cascaded relay. Science path could potentially have only ~4 high quality reflections. Could this meet <30% unattenuated(sky+tel) spec? Throughput to science instrument would be significantly higher (~4 AO surfaces vs ~18 including windows). Throughput to LGS WFS would be higher (3 less surfaces; 7 less if include windows). Higher DM & rotator costs in exchange for no refrigeration & fewer optics. 1/7/09: RD estimated that a high actuator count Xinetics DM with drivers would be $1M. DG to evaluate emissivity & thruput for this case.
Determine what dichroic switchyard savings can be made (DG, PW). For example, cascade relay fed by 1st relay without a reflection; co-locating similar wavelength instruments. 1/7/09: Take multi-element decker out of cost estimate. PW to do.
Consider only using PNS lasers for tip/tilt stars (separate AO systems). Similarly fixed asterism is only used for laser tomography over the central science field. (DG,RD) Result: Simpler RTC, especially a reduction in the tomography volume (number of processors directly proportional to volume). Could also allow us to put some of PNS laser power back into central asterism.
Not a cost savings item but relevant to thought process: determine if we need windows on MEMS (possibly not if in clean room environment (but how do you handle them in earlier FSD & I&T?). (DG) 1/7/08: Voltage on MEMS with humidity > 40% can damage MEMS. Agreed on design change to assume no window on MEMS but will need a requirement on humidity.
Consider an asymmetric fixed LGS asterism with a rotator, instead of PNS. (RD)
Consider no NGS mode or reduced capability (PW). Only limited science cases would use NGS (Io, Titan) instead of LGS. Would get similar performance for fainter NGS that would get with K1 NGS system. Use other Nas instrument for backup science. NGS/TWFS assly total $527k (FY08) + SY optics. Already removed TWFS & ADC ($260k then-year). 1/7/09: Agreed to keep NGS WFS in baseline design. Also useful for high order calibration of the system (higher order than TWFS). Could be a spare for LGS WFS. Consider looking at whether one of the LGS WFS could act as an NGS WFS (would need to add a dichroic changer unless all visible light up to ~ 800 nm available to the LGS WFS).
Evaluate combining (or separating) science instrument capabilities for lower cost (SA). For example, combining NIR imager & IFU.
Evaluate feasible of extending NIR instruments, especially imager, to I-band (SA).
Confidence level in NIR IFU cost estimate is low. Develop better cost estimate (SA).
Need clarifications on science priorities from KSP & relative priorities (CM).
Determine if feasible to reuse existing Xinetics DM even if have 30% hysteresis (DG). 1/7/09: Decided to use a new DM as our baseline. It may be possible to use a lower BW TT stage for the woofer since have the MEMS on TT platforms. Should evaluated during PD (Telescope TT data in a Neyman KAON).
Consider proceeding with early launch telescope implementation even if not funded by MRI (PW).

## B2C Review tables
| SDR Design | B2C Baseline Design | Rationale | Savings ($M) | Science Case | NIR IFS | NIR Cam | Vis Cam | Vis IFS | MOSFIRE QE (from KAON 556)
Science Fields | Narrow & Wide | Narrow | No multi d-IFS |  | Galaxy assembly & star formation |  |  |  |  | Wavelength | MOSFIRE | H-4RG goal | e2V meas
Central LGS Asterism | 5 variable, 1 fixed | 4 fixed | Only narrow field | 0.90654 | Nearby AGNs |  |  |  |  | 0.7 |  | 0.7 | 0.88
Laser Location | Nasmyth platform | Elevation ring | ESO laser proposals | 0.35768 | GR effects in the Galactic Center |  |  |  |  | 0.8 | 0.76 | 0.7 | 0.93
Total Power | 100 W (~11W / LGS) | 75 W (50W center) | Only narrow field | 1.4774 | Extrasolar planets |  |  |  |  | 0.9 |  | 0.7 | 0.95
No. of subapertures | 64 | ? | Optimized for above |  | Minor planets multiplicity |  |  |  |  | 1 | 0.75 | 0.7 | 0.5
Number of devices | LGS WFS dof reduced from 62 to 41; laser from 89 to 61; UTT from 9 to 7 |  |  | 0.16846 | [5 empty] | 1 | 0.75 | 0.8
RTC | 2 less WFS & UTT; reduced subapertures & configurations |  |  | 0.17192 | [5 empty] | 1.25 | 0.78 | 0.8
Impact | No wide field science support; no on-sky narrow field optimization ~ nm rms |  |  | 3.082 | [5 empty] | 2 | 0.77 | 0.8
| SDR Design | B2C Baseline Design | Rationale | Savings ($M)
NIR IFS | 6 channel multi d-IFS | 1 channel fixed IFS | KSP08; SDR | baseline
NIR Imager | yes | Extends to 800 nm | To provide vis capability | -0.48
Visible Imager | yes | no | Cost; future upgrade? | 4.4829
Visible IFS | no | no
OSIRIS | yes | no | Provided by NIR IFS | 0.26872
Interferometer | yes | yes
Impact | Limited visible science capability; no multiplexing capability |  |  | 4.2716
| SDR Design | B2C Baseline Design | Rationale | Savings ($M)
Cooling | AO enclosure | Science path optics | Only science needs cold | 0.40163
Truth WFS | NIR after 1st relay Vis after 2nd relay | Vis after 1st relay | Few NGS in narrow field Similar performance | 0.27601
Optical design | 2-tier | 1-tier | Removes 2nd tier cost | 0.10041
2nd relay location | reflection off dichroic | transmitted, no dichroic | no d-IFS; lower cost
NGS WFS | ADC; 3 lenslets | no ADC; 2 lenslets | Cost | 0.067905
Impact |  |  |  | 0.84596

## Revised Est (then-yr)
|  |  |  | Actuals ($k) |  | Plan (Then-Year $k)
NGAO System | Start | End | Months | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | Total
System Design | 2007-10-01 | 2008-04-30 | 19 | 738.85 | 494.98 | [7 empty] | 1233.83
Preliminary Design | 2008-05-01 | 2010-04-30 | 24 |  | 214.171 | 1800 | 1634.4115 | [5 empty] | 3648.5825
Detailed Design | 2010-05-01 | 2012-04-30 | 24 |  |  |  | 1357.0462 | 5234.5175 | 3036.103 |  |  |  | 9627.6667
Full Scale Development | 2012-05-01 | 2014-04-30 | 24 | [5 empty] | 6406.7508 | 11312.5042 | 9599.6279 |  | 27318.8829
Delivery & Commissioning | 2014-05-01 | 2015-02-28 | 10 | [7 empty] | 2222.8814 | 2300.6823 | 4523.5637
Additional Contingency = | [9 empty] | 300 | 400 | 444.6976 | 1144.6976
NGAO Total = |  |  | 101 | 738.85 | 709.151 | 1800 | 2991.4577 | 5234.5175 | 9442.8538 | 11612.5042 | 12222.5094 | 2745.3799 | 47497.2235
NIR Imager | [5 empty] | 200 | 482.3164 | 907.0773 | 1044.4402 | 977.9293 | 156.8927 | 0 | 3768.6559
NIR IFU | [5 empty] | 50 | 239.7 | 606.22 | 1300 | 1400 | 1404.08 |  | 5000
Visible Imager | [7 empty] | 100 | 200 | 100 | 0 | 0 | 400
Contingency | [6 empty] | 50 | 300 | 600 | 700 | 183.7312 |  | 1833.7312
NGAO Instrument Total = | [5 empty] | 250 | 772.0164 | 1913.2973 | 3144.4402 | 3177.9293 | 1744.7039 | 0 | 11002.3871
Overall Total = |  |  |  | 738.85 | 709.151 | 2050 | 3763.4741 | 7147.8148 | 12587.294 | 14790.4335 | 13967.2132 | 2745.3799 | 58499.6106
Years of inflation | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Annual inflation = |  |  |  | 1.035
Note on A4: peterw: 2 month slip vs SDR
Note on A8: peterw: Increased NGAO contingency from 22 to 25%
Note on A10: peterw: Mostly shifted 1 yr later, except for $200k in FY09
Note on A11: peterw: Used $189.7k for 1st yr & $206.2k for 2nd yr from ATI proposal. $4M total ROM from Peter until I get something better from Sean. 12/9/08 - increased from $4.3M to $5M per suggestion from Sean
Note on A12: peterw: Slipped by 2 yr vs SA plan.
Note on A13: peterw: Put 20% of total in as a place holder

## SDR Cost Estimate (FY08)
|  | Total of all Phases | [9 empty] | PD Phase | [9 empty] | DD Phase | [9 empty] | FSD Phase | [9 empty] | DC Phase
|  | Labor |  | Trips | $k |  |  |  |  | % of NGAO |  | Labor |  | Trips | $k |  |  |  |  | % of WBS in this Phase |  | Labor |  | Trips | $k |  |  |  |  | % of WBS in this Phase |  | Labor |  | Trips | $k |  |  |  |  | % of WBS in this Phase |  | Labor |  | Trips | $k |  |  |  |  | % of WBS in this Phase
|  | hrs | PY |  | Labor | Non-labor | Travel | Conting | Total |  |  | hrs | PY |  | Labor | Non-labor | Travel | Conting | Total |  |  | hrs | PY |  | Labor | Non-labor | Travel | Conting | Total |  |  | hrs | PY |  | Labor | Non-labor | Travel | Conting | Total |  |  | hrs | PY |  | Labor | Non-labor | Travel | Conting | Total
2 | Management | [8 empty] | 11.07% | 4673.8614 | [9 empty] | 925.6431 | [9 empty] | 1310.7494 | [9 empty] | 1738.9443 | [9 empty] | 698.5246
2.1 | Planning | 4390 | 2.4389 | 5 | 420.611 | 0 | 18.8587 | 21.9735 | 461.4432 |  |  | 1570 | 0.87222 | 0 | 157.8079 | 0 | 0 | 7.8904 | 165.6983 | 35.91% |  | 1900 | 1.0556 | 1 | 186.2131 | 0 | 3.7717 | 9.4992 | 199.4841 | 43.23% |  | 760 | 0.42222 | 4 | 61.7891 | 0 | 15.0869 | 3.8438 | 80.7198 | 17.49% |  | 160 | 0.088889 | 0 | 14.8009 | 0 | 0 | 0.74005 | 15.541 | 3.368%
2.2 | Project Management & Meetings | 8358 | 4.6433 | 85 | 766.0624 | 0 | 231.8889 | 56.8353 | 1054.7866 |  |  | 2170 | 1.2056 | 22 | 198.7807 | 0 | 66.0188 | 13.24 | 278.0394 | 26.36% |  | 3300 | 1.8333 | 37 | 309.266 | 0 | 108.0582 | 20.8662 | 438.1904 | 41.54% |  | 2414 | 1.3411 | 26 | 207.2747 | 0 | 57.8119 | 21.2069 | 286.2935 | 27.14% |  | 474 | 0.26333 | 0 | 50.741 | 0 | 0 | 1.5222 | 52.2632 | 4.955%
2.3 | Tracking & Reporting | 5412.2 | 3.0068 | 49 | 535.4451 | 0 | 121.9724 | 37.9229 | 695.3404 |  |  | 829 | 0.46056 | 7 | 94.0495 | 0 | 13.7011 | 5.3875 | 113.1381 | 16.27% |  | 1339.2 | 0.744 | 11 | 134.9142 | 0 | 22.2225 | 7.8568 | 164.9935 | 23.73% |  | 1890 | 1.05 | 18 | 173.7858 | 0 | 50.6474 | 17.9547 | 242.3879 | 34.86% |  | 1354 | 0.75222 | 13 | 132.6955 | 0 | 35.4015 | 6.7239 | 174.8209 | 25.14%
2.4 | Proposals & Fundraising | 80 | 0.044444 | 0 | 9.9825 | 0 | 0 | 0.99825 | 10.9807 |  |  | 40 | 0.022222 | 0 | 4.9912 | 0 | 0 | 0.49912 | 5.4904 | 50% |  | 40 | 0.022222 | 0 | 4.9912 | 0 | 0 | 0.49912 | 5.4904 | 50% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.5 | Programmatic Risk Assessment & Mitigation | 460 | 0.25556 | 2 | 53.2407 | 0 | 7.5435 | 8.206 | 68.9902 |  |  | 180 | 0.1 | 0 | 20.8611 | 0 | 0 | 2.0861 | 22.9472 | 33.26% |  | 180 | 0.1 | 2 | 20.8611 | 0 | 7.5435 | 5.6809 | 34.0855 | 49.41% |  | 60 | 0.033333 | 0 | 6.9537 | 0 | 0 | 0.34769 | 7.3014 | 10.58% |  | 40 | 0.022222 | 0 | 4.5647 | 0 | 0 | 0.091294 | 4.656 | 6.749%
2.6 | Project Reviews | 3544 | 1.9689 | 104 | 376.1531 | 0 | 382.6277 | 69.3944 | 828.1752 |  |  | 456 | 0.25333 | 13 | 48.2368 | 0 | 32.7256 | 4.0481 | 85.0106 | 10.26% |  | 548 | 0.30444 | 16 | 57.9423 | 0 | 63.8374 | 9.7424 | 131.5221 | 15.88% |  | 1524 | 0.84667 | 43 | 161.9844 | 0 | 158.3898 | 32.0374 | 352.4116 | 42.55% |  | 1016 | 0.56444 | 32 | 107.9896 | 0 | 127.6749 | 23.5664 | 259.2309 | 31.3%
2.7 | Project Support | 20066 | 11.1478 | 23 | 1010.1489 | 354.024 | 66.9699 | 123.0023 | 1554.1451 |  |  | 3361 | 1.8672 | 4 | 165.5886 | 59.171 | 11.6469 | 18.9125 | 255.319 | 16.43% |  | 3990 | 2.2167 | 5 | 191.678 | 105.785 | 14.5587 | 24.9617 | 336.9834 | 21.68% |  | 9250 | 5.1389 | 12 | 483.1627 | 181.742 | 34.9408 | 69.9845 | 769.83 | 49.53% |  | 3465 | 1.925 | 2 | 169.7197 | 7.326 | 5.8235 | 9.1435 | 192.0126 | 12.35%
3 | Systems Engineering | [8 empty] | 6.835% | 2886.0621 | [9 empty] | 908.6678 | [9 empty] | 1186.0424 | [9 empty] | 553.8553 | [9 empty] | 237.4966
3.1 | Science Case Development
3.1.1 | Science Requirements | 3460 | 1.9222 | 17 | 158.5935 | 2.016 | 15.6224 | 12.3362 | 188.5682 |  |  | 2260 | 1.2556 | 5 | 108.4602 | 2.016 | 4.5948 | 8.055 | 123.126 | 65.3% |  | 680 | 0.37778 | 6 | 28.4089 | 0 | 5.5138 | 2.3746 | 36.2973 | 19.25% |  | 520 | 0.28889 | 6 | 21.7244 | 0 | 5.5138 | 1.9067 | 29.1449 | 15.46% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3.1.2 | Science Observing Planning and Execution | 1800 | 1 | 0 | 100.776 | 0 | 0 | 19.2487 | 120.0247 |  |  | 420 | 0.23333 | 0 | 22.477 | 0 | 0 | 2.0229 | 24.4999 | 20.41% |  | 920 | 0.51111 | 0 | 50.4532 | 0 | 0 | 11.0997 | 61.5529 | 51.28% |  | 300 | 0.16667 | 0 | 21.1614 | 0 | 0 | 4.6555 | 25.8169 | 21.51% |  | 160 | 0.088889 | 0 | 6.6844 | 0 | 0 | 1.4706 | 8.155 | 6.794%
3.1.3 | Science Input to Other WBS Elements Affecting Science Performance | 670 | 0.37222 | 22 | 27.9911 | 0 | 32.3311 | 10.624 | 70.9463 |  |  | 130 | 0.072222 | 7 | 5.4311 | 0 | 11.2783 | 3.0077 | 19.7171 | 27.79% |  | 180 | 0.1 | 8 | 7.52 | 0 | 12.1973 | 3.5491 | 23.2664 | 32.79% |  | 220 | 0.12222 | 7 | 9.1911 | 0 | 8.8555 | 3.2484 | 21.295 | 30.02% |  | 140 | 0.077778 | 0 | 5.8489 | 0 | 0 | 0.81884 | 6.6677 | 9.398%
3.1.4 | Science Competitiveness | 312 | 0.17333 | 12 | 13.0347 | 0 | 65.5988 | 4.718 | 83.3515 |  |  | 104 | 0.057778 | 4 | 4.3449 | 0 | 21.8663 | 1.5727 | 27.7838 | 33.33% |  | 104 | 0.057778 | 4 | 4.3449 | 0 | 21.8663 | 1.5727 | 27.7838 | 33.33% |  | 104 | 0.057778 | 4 | 4.3449 | 0 | 21.8663 | 1.5727 | 27.7838 | 33.33% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3.1.5 | User Community Liason | 280 | 0.15556 | 8 | 11.6978 | 0 | 7.3517 | 1.143 | 20.1925 |  |  | 70 | 0.038889 | 2 | 2.9244 | 0 | 1.8379 | 0.28574 | 5.0481 | 25% |  | 70 | 0.038889 | 2 | 2.9244 | 0 | 1.8379 | 0.28574 | 5.0481 | 25% |  | 70 | 0.038889 | 2 | 2.9244 | 0 | 1.8379 | 0.28574 | 5.0481 | 25% |  | 70 | 0.038889 | 2 | 2.9244 | 0 | 1.8379 | 0.28574 | 5.0481 | 25%
3.1.6 | Science Advisory Team Meetings | 640 | 0.35556 | 32 | 31.6681 | 0 | 29.4069 | 3.6645 | 64.7395 |  |  | 160 | 0.088889 | 8 | 7.917 | 0 | 7.3517 | 0.91613 | 16.1849 | 25% |  | 160 | 0.088889 | 8 | 7.917 | 0 | 7.3517 | 0.91613 | 16.1849 | 25% |  | 160 | 0.088889 | 8 | 7.917 | 0 | 7.3517 | 0.91613 | 16.1849 | 25% |  | 160 | 0.088889 | 8 | 7.917 | 0 | 7.3517 | 0.91613 | 16.1849 | 25%
3.2 | Requirements | 3699 | 2.055 | 0 | 286.3904 | 0 | 0 | 22.9112 | 309.3016 |  |  | 1094 | 0.60778 | 0 | 83.5009 | 0 | 0 | 6.6801 | 90.1809 | 29.16% |  | 990 | 0.55 | 0 | 75.696 | 0 | 0 | 6.0557 | 81.7516 | 26.43% |  | 1135 | 0.63056 | 0 | 90.0515 | 0 | 0 | 7.2041 | 97.2556 | 31.44% |  | 480 | 0.26667 | 0 | 37.1421 | 0 | 0 | 2.9714 | 40.1134 | 12.97%
3.3 | Systems Engineering Analysis
3.3.1 | Performance Budgets | 2800 | 1.5556 | 13 | 284.4084 | 0 | 11.9466 | 66.4738 | 362.8288 |  |  | 748 | 0.41556 | 4 | 81.742 | 0 | 3.6759 | 17.0836 | 102.5015 | 28.25% |  | 1120 | 0.62222 | 4 | 109.2825 | 0 | 3.6759 | 28.2396 | 141.1979 | 38.92% |  | 620 | 0.34444 | 2 | 62.5937 | 0 | 1.8379 | 7.7318 | 72.1634 | 19.89% |  | 312 | 0.17333 | 3 | 30.7902 | 0 | 2.7569 | 13.4189 | 46.966 | 12.94%
3.3.2 | Modeling & Analysis | 2000 | 1.1111 | 14 | 186.9356 | 0 | 24.9794 | 66.9454 | 278.8603 |  |  | 880 | 0.48889 | 4 | 80.5816 | 0 | 8.5214 | 17.8206 | 106.9236 | 38.34% |  | 760 | 0.42222 | 5 | 73.9581 | 0 | 7.0176 | 32.3903 | 113.366 | 40.65% |  | 240 | 0.13333 | 3 | 20.5535 | 0 | 5.1797 | 10.2933 | 36.0264 | 12.92% |  | 120 | 0.066667 | 2 | 11.8424 | 0 | 4.2607 | 6.4412 | 22.5443 | 8.084%
3.3.3 | PSF Calibration | 1440 | 0.8 | 4 | 112.1921 | 0 | 11.8042 | 33.6046 | 157.6009 |  |  | 0 | 0 | 2 | 0 | 0 | 5.1207 | 0 | 5.1207 | 3.249% |  | 1400 | 0.77778 | 2 | 109.2884 | 0 | 6.6835 | 32.4721 | 148.4441 | 94.19% |  | 40 | 0.022222 | 0 | 2.9037 | 0 | 0 | 1.1324 | 4.0361 | 2.561% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3.4 | System Architecture
3.4.1 | System Hardware Architecture | 1016 | 0.56444 | 0 | 94.8124 | 0 | 0 | 28.4437 | 123.2561 |  |  | 264 | 0.14667 | 0 | 24.9734 | 0 | 0 | 7.492 | 32.4655 | 26.34% |  | 304 | 0.16889 | 0 | 27.8321 | 0 | 0 | 8.3496 | 36.1817 | 29.35% |  | 304 | 0.16889 | 0 | 27.8321 | 0 | 0 | 8.3496 | 36.1817 | 29.35% |  | 144 | 0.08 | 0 | 14.1748 | 0 | 0 | 4.2524 | 18.4273 | 14.95%
3.4.2 | Motion Control / Electronics Architecture | 310 | 0.17222 | 0 | 30.4182 | 0 | 0 | 9.1255 | 39.5437 |  |  | 80 | 0.044444 | 0 | 7.8499 | 0 | 0 | 2.355 | 10.2048 | 25.81% |  | 200 | 0.11111 | 0 | 19.6247 | 0 | 0 | 5.8874 | 25.5121 | 64.52% |  | 30 | 0.016667 | 0 | 2.9437 | 0 | 0 | 0.88311 | 3.8268 | 9.677% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3.4.3 | System Software Architecture | 830 | 0.46111 | 0 | 102.0483 | 0 | 0 | 22.4506 | 124.4989 |  |  | 304 | 0.16889 | 0 | 29.8295 | 0 | 0 | 6.5625 | 36.392 | 29.23% |  | 320 | 0.17778 | 0 | 31.3995 | 0 | 0 | 6.9079 | 38.3073 | 30.77% |  | 240 | 0.13333 | 0 | 23.5496 | 0 | 0 | 5.1809 | 28.7305 | 23.08% |  | 176 | 0.097778 | 0 | 17.2697 | 0 | 0 | 3.7993 | 21.069 | 16.92%
3.4.4 | Operations Sequences Architecture | 776 | 0.43111 | 4 | 66.9525 | 0 | 13.3669 | 14.4575 | 94.7769 |  |  | 224 | 0.12444 | 1 | 17.8946 | 0 | 3.3417 | 3.8225 | 25.0589 | 26.44% |  | 360 | 0.2 | 1 | 30.2182 | 0 | 3.3417 | 6.0408 | 39.6007 | 41.78% |  | 96 | 0.053333 | 1 | 9.4198 | 0 | 3.3417 | 2.2971 | 15.0587 | 15.89% |  | 96 | 0.053333 | 1 | 9.4198 | 0 | 3.3417 | 2.2971 | 15.0587 | 15.89%
3.5 | External Interface Control | 524 | 0.29111 | 0 | 45.1343 | 0 | 0 | 3.1975 | 48.3318 |  |  | 284 | 0.15778 | 0 | 24.6123 | 0 | 0 | 1.2306 | 25.8429 | 53.47% |  | 140 | 0.077778 | 0 | 11.506 | 0 | 0 | 1.1506 | 12.6566 | 26.19% |  | 80 | 0.044444 | 0 | 7.3089 | 0 | 0 | 0.73089 | 8.0398 | 16.63% |  | 20 | 0.011111 | 0 | 1.7072 | 0 | 0 | 0.085358 | 1.7925 | 3.709%
3.6 | Internal Interface Control | 1672 | 0.92889 | 14 | 140.7778 | 0 | 28.2621 | 31.1668 | 200.2068 |  |  | 280 | 0.15556 | 4 | 22.9811 | 0 | 8.5214 | 4.4103 | 35.9128 | 17.94% |  | 832 | 0.46222 | 4 | 71.4262 | 0 | 6.0986 | 10.8535 | 88.3783 | 44.14% |  | 416 | 0.23111 | 4 | 35.9173 | 0 | 6.0986 | 10.504 | 52.52 | 26.23% |  | 144 | 0.08 | 2 | 10.4533 | 0 | 7.5435 | 5.399 | 23.3958 | 11.69%
3.7 | Configuration Management | 684 | 0.38 | 0 | 33.9287 | 0 | 0 | 13.9108 | 47.8394 |  |  | 218 | 0.12111 | 0 | 11.622 | 0 | 0 | 4.765 | 16.3871 | 34.25% |  | 180 | 0.1 | 0 | 8.6163 | 0 | 0 | 3.5327 | 12.149 | 25.4% |  | 208 | 0.11556 | 0 | 9.9566 | 0 | 0 | 4.0822 | 14.0388 | 29.35% |  | 78 | 0.043333 | 0 | 3.7337 | 0 | 0 | 1.5308 | 5.2646 | 11%
3.8 | Documentation Control | 253 | 0.14056 | 0 | 13.1158 | 0 | 0 | 1.8362 | 14.952 |  |  | 20 | 0.011111 | 0 | 1.9625 | 0 | 0 | 0.27475 | 2.2372 | 14.96% |  | 90 | 0.05 | 0 | 4.3081 | 0 | 0 | 0.60314 | 4.9113 | 32.85% |  | 104 | 0.057778 | 0 | 4.9783 | 0 | 0 | 0.69696 | 5.6753 | 37.96% |  | 39 | 0.021667 | 0 | 1.8669 | 0 | 0 | 0.26136 | 2.1282 | 14.23%
3.9 | Technical Risk Assessment & Mitigation | 2000 | 1.1111 | 1 | 196.6973 | 262.65 | 3.7717 | 32.4948 | 495.6138 |  |  | 700 | 0.38889 | 0 | 71.3521 | 108.15 | 0 | 8.9751 | 188.4772 | 38.03% |  | 800 | 0.44444 | 1 | 83.8302 | 154.5 | 3.7717 | 19.3682 | 261.4701 | 52.76% |  | 500 | 0.27778 | 0 | 41.515 | 0 | 0 | 4.1515 | 45.6665 | 9.214% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3.10 | System Manual | 340 | 0.18889 | 0 | 38.6935 | 0 | 0 | 1.9347 | 40.6282 |  |  | 120 | 0.066667 | 0 | 13.9074 | 0 | 0 | 0.69537 | 14.6028 | 35.94% |  | 100 | 0.055556 | 0 | 11.4118 | 0 | 0 | 0.57059 | 11.9824 | 29.49% |  | 80 | 0.044444 | 0 | 8.9162 | 0 | 0 | 0.44581 | 9.362 | 23.04% |  | 40 | 0.022222 | 0 | 4.4581 | 0 | 0 | 0.2229 | 4.681 | 11.52%
4 | AO System Development | [8 empty] | 39.15% | 16532.5402 | [9 empty] | 938.6864 | [9 empty] | 2820.0942 | [9 empty] | 12770.2502 | [9 empty] | 3.5093
4.1 | AO Enclosure | 520 | 0.28889 | 0 | 34.6665 | 618 | 0 | 116.2604 | 768.9269 |  |  | 300 | 0.16667 | 0 | 21.7777 | 0 | 0 | 3.0489 | 24.8265 | 3.229% |  | 120 | 0.066667 | 0 | 8.7111 | 0 | 0 | 1.2195 | 9.9306 | 1.291% |  | 100 | 0.055556 | 0 | 4.1778 | 618 | 0 | 111.992 | 734.1698 | 95.48% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2 | Optomechanical
4.2.1 | AO Support Structure | 1920 | 1.0667 | 0 | 104.8649 | 113.3 | 0 | 65.4495 | 283.6144 |  |  | 160 | 0.088889 | 0 | 11.6148 | 0 | 0 | 3.4844 | 15.0992 | 5.324% |  | 480 | 0.26667 | 0 | 34.8443 | 0 | 0 | 10.4533 | 45.2975 | 15.97% |  | 1280 | 0.71111 | 0 | 58.4059 | 113.3 | 0 | 51.5118 | 223.2176 | 78.7% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.2 | Rotator | 740 | 0.41111 | 0 | 44.4739 | 45.423 | 0 | 23.3732 | 113.2701 |  |  | 120 | 0.066667 | 0 | 8.7111 | 0 | 0 | 2.2649 | 10.9759 | 9.69% |  | 270 | 0.15 | 0 | 19.5999 | 0 | 0 | 5.096 | 24.6959 | 21.8% |  | 350 | 0.19444 | 0 | 16.1629 | 45.423 | 0 | 16.0123 | 77.5983 | 68.51% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.3 | Optical Relays | 6720 | 3.7333 | 0 | 399.0741 | 265.74 | 0 | 199.4442 | 864.2584 |  |  | 533 | 0.29611 | 0 | 38.6917 | 0 | 0 | 11.6075 | 50.2992 | 5.82% |  | 2827 | 1.5706 | 0 | 205.2182 | 0 | 0 | 61.5655 | 266.7837 | 30.87% |  | 3360 | 1.8667 | 0 | 155.1643 | 265.74 | 0 | 126.2713 | 547.1756 | 63.31% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.4 | Optical Switchyard | 4640 | 2.5778 | 0 | 277.6642 | 271.92 | 0 | 164.8753 | 714.4594 |  |  | 400 | 0.22222 | 0 | 29.0369 | 0 | 0 | 8.7111 | 37.748 | 5.283% |  | 2000 | 1.1111 | 0 | 145.1844 | 0 | 0 | 43.5553 | 188.7398 | 26.42% |  | 2240 | 1.2444 | 0 | 103.4428 | 271.92 | 0 | 112.6089 | 487.9717 | 68.3% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.5 | LGS Wavefront Sensor Assembly | 7450 | 4.1389 | 3 | 494.7581 | 1618.24 | 4.0469 | 905.4387 | 3022.4838 |  |  | 1520 | 0.84444 | 0 | 111.3614 | 0 | 0 | 38.9765 | 150.3379 | 4.974% |  | 2480 | 1.3778 | 3 | 174.1596 | 0 | 4.0469 | 62.3723 | 240.5787 | 7.96% |  | 3450 | 1.9167 | 0 | 209.2372 | 1618.24 | 0 | 804.0899 | 2631.5671 | 87.07% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.6 | NGS WFS / TWFS Assembly | 3384 | 1.88 | 0 | 193.8183 | 237.205 | 0 | 95.7207 | 526.744 |  |  | 628 | 0.34889 | 0 | 35.4017 | 0 | 0 | 7.0803 | 42.482 | 8.065% |  | 1812 | 1.0067 | 0 | 105.1465 | 0 | 0 | 18.9264 | 124.0728 | 23.55% |  | 944 | 0.52444 | 0 | 53.2701 | 237.205 | 0 | 69.714 | 360.1891 | 68.38% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.7 | Low Order Wavefront Sensor Assembly | 9520 | 5.2889 | 5 | 592.0717 | 1007.085 | 4.5948 | 686.5274 | 2290.2789 |  |  | 1596 | 0.88667 | 2 | 108.2724 | 0 | 1.8379 | 42.943 | 153.0534 | 6.683% |  | 4220 | 2.3444 | 3 | 269.5975 | 0 | 2.7569 | 106.2182 | 378.5725 | 16.53% |  | 3704 | 2.0578 | 0 | 214.2018 | 1007.085 | 0 | 537.3662 | 1758.653 | 76.79% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.8 | Tip/Tilt Vibration Mitigation | 3180 | 1.7667 | 0 | 209.8894 | 51.5 | 0 | 57.7888 | 319.1783 |  |  | 80 | 0.044444 | 0 | 5.8074 | 0 | 0 | 0.58074 | 6.3881 | 2.001% |  | 1100 | 0.61111 | 0 | 74.3048 | 0 | 0 | 11.8888 | 86.1936 | 27% |  | 2000 | 1.1111 | 0 | 129.7772 | 51.5 | 0 | 45.3193 | 226.5965 | 70.99% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.9 | Acquisition Cameras | 577.5 | 0.32083 | 0 | 37.6142 | 69.3311 | 0 | 17.1112 | 124.0565 |  |  | 127.5 | 0.070833 | 0 | 8.8846 | 0 | 0 | 1.4215 | 10.3062 | 8.308% |  | 187.5 | 0.10417 | 0 | 12.6839 | 0 | 0 | 2.0294 | 14.7133 | 11.86% |  | 262.5 | 0.14583 | 0 | 16.0456 | 69.3311 | 0 | 13.6603 | 99.037 | 79.83% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.2.10 | Atmospheric Dispersion Correctors | 2240 | 1.2444 | 0 | 128.0944 | 41.2 | 0 | 44.0165 | 213.3109 |  |  | 240 | 0.13333 | 0 | 17.4221 | 0 | 0 | 4.5298 | 21.9519 | 10.29% |  | 720 | 0.4 | 0 | 52.2664 | 0 | 0 | 13.5893 | 65.8557 | 30.87% |  | 1280 | 0.71111 | 0 | 58.4059 | 41.2 | 0 | 25.8975 | 125.5034 | 58.84% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.3 | Alignment, Calibration, and Diagnostics
4.3.1 | Simulator | 1865 | 1.0361 | 2 | 137.7364 | 134.9 | 9.6935 | 42.3495 | 324.6794 |  |  | 250 | 0.13889 | 0 | 19.1774 | 0 | 0 | 2.8766 | 22.054 | 6.793% |  | 870 | 0.48333 | 0 | 64.7597 | 0 | 0 | 9.714 | 74.4737 | 22.94% |  | 745 | 0.41389 | 2 | 53.7993 | 134.9 | 9.6935 | 29.7589 | 228.1517 | 70.27% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.3.2 | System Alignment Tools | 1695 | 0.94167 | 2 | 125.0495 | 1 | 9.6935 | 20.3614 | 156.1044 |  |  | 255 | 0.14167 | 0 | 19.668 | 0 | 0 | 2.9502 | 22.6182 | 14.49% |  | 850 | 0.47222 | 0 | 63.8024 | 0 | 0 | 9.5704 | 73.3727 | 47% |  | 590 | 0.32778 | 2 | 41.5791 | 1 | 9.6935 | 7.8409 | 60.1135 | 38.51% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.3.3 | Atmospheric Profiler | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4 | Non-real-time Control
4.4.1 | AO Controls Infrastructure | 180 | 0.1 | 0 | 16.1529 | 0 | 0 | 5.1689 | 21.3218 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 140 | 0.077778 | 0 | 12.7386 | 0 | 0 | 4.0763 | 16.8149 | 78.86% |  | 40 | 0.022222 | 0 | 3.4143 | 0 | 0 | 1.0926 | 4.5069 | 21.14% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.2 | AO Sequencer | 980 | 0.54444 | 0 | 77.7785 | 0 | 0 | 24.8891 | 102.6676 |  |  | 140 | 0.077778 | 0 | 11.5671 | 0 | 0 | 3.7015 | 15.2686 | 14.87% |  | 420 | 0.23333 | 0 | 33.1695 | 0 | 0 | 10.6142 | 43.7837 | 42.65% |  | 420 | 0.23333 | 0 | 33.0418 | 0 | 0 | 10.5734 | 43.6152 | 42.48% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.3 | Motion Control SW | 4560 | 2.5333 | 0 | 265.5218 | 0 | 0 | 100.8983 | 366.4201 |  |  | 230 | 0.12778 | 0 | 18.611 | 0 | 0 | 7.0722 | 25.6832 | 7.009% |  | 650 | 0.36111 | 0 | 51.3976 | 0 | 0 | 19.5311 | 70.9287 | 19.36% |  | 3680 | 2.0444 | 0 | 195.5132 | 0 | 0 | 74.295 | 269.8082 | 73.63% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.4 | Device Control SW | 3755 | 2.0861 | 0 | 223.1987 | 0 | 0 | 84.8155 | 308.0143 |  |  | 240 | 0.13333 | 0 | 19.8476 | 0 | 0 | 7.5421 | 27.3897 | 8.892% |  | 495 | 0.275 | 0 | 35.9332 | 0 | 0 | 13.6546 | 49.5877 | 16.1% |  | 3020 | 1.6778 | 0 | 167.418 | 0 | 0 | 63.6188 | 231.0368 | 75.01% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.5 | Motion Control Electronics | 760 | 0.42222 | 0 | 57.4546 | 179.735 | 0 | 87.3866 | 324.5762 |  |  | 60 | 0.033333 | 0 | 5.1215 | 0 | 0 | 1.6389 | 6.7603 | 2.083% |  | 500 | 0.27778 | 0 | 40.6364 | 0 | 0 | 13.0036 | 53.64 | 16.53% |  | 200 | 0.11111 | 0 | 11.6968 | 179.735 | 0 | 72.7441 | 264.1758 | 81.39% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.6 | Non-RTC Electronics | 760 | 0.42222 | 0 | 56.561 | 49.44 | 0 | 37.5885 | 143.5896 |  |  | 160 | 0.088889 | 0 | 13.2743 | 0 | 0 | 4.2478 | 17.522 | 12.2% |  | 400 | 0.22222 | 0 | 31.59 | 0 | 0 | 10.1088 | 41.6988 | 29.04% |  | 200 | 0.11111 | 0 | 11.6968 | 49.44 | 0 | 23.232 | 84.3687 | 58.76% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.7 | Lab I&T System | 320 | 0.17778 | 0 | 25.4906 | 52.53 | 0 | 28.2445 | 106.2651 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 280 | 0.15556 | 0 | 23.3896 | 0 | 0 | 7.4847 | 30.8742 | 29.05% |  | 40 | 0.022222 | 0 | 2.1011 | 52.53 | 0 | 20.7598 | 75.3909 | 70.95% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.8 | Acquisition, Guiding, and Offloading Control | 760 | 0.42222 | 0 | 60.6916 | 0 | 0 | 19.4213 | 80.1129 |  |  | 160 | 0.088889 | 0 | 13.019 | 0 | 0 | 4.1661 | 17.185 | 21.45% |  | 480 | 0.26667 | 0 | 39.4399 | 0 | 0 | 12.6208 | 52.0606 | 64.98% |  | 120 | 0.066667 | 0 | 8.2327 | 0 | 0 | 2.6345 | 10.8672 | 13.56% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.5 | Real-time Control
4.5.1 | Real-time Control Processor | 13778.8 | 7.6549 | 5 | 667.3106 | 1067.322 | 15.8787 | 490.1432 | 2240.6544 |  |  | 3036.6 | 1.687 | 0 | 146.7298 | 15.862 | 0 | 45.5257 | 208.1176 | 9.288% |  | 10154.2 | 5.6412 | 1 | 484.9717 | 28.84 | 2.9117 | 144.6826 | 661.406 | 29.52% |  | 588 | 0.32667 | 4 | 35.6091 | 1022.62 | 12.9669 | 299.9349 | 1371.1309 | 61.19% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.5.2 | DM's and Tip/Tilt Stages | 3040 | 1.6889 | 2 | 211.5234 | 1483.2 | 5.6235 | 331.5325 | 2031.8793 |  |  | 320 | 0.17778 | 1 | 25.272 | 0 | 2.8117 | 3.37 | 31.4538 | 1.548% |  | 960 | 0.53333 | 1 | 75.816 | 0 | 2.8117 | 9.4353 | 88.0631 | 4.334% |  | 1760 | 0.97778 | 0 | 110.4354 | 1483.2 | 0 | 318.7271 | 1912.3625 | 94.12% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.6 | AO System Lab I&T | 8480 | 4.7111 | 12 | 689.7959 | 112.7 | 82.6708 | 200.5068 | 1085.6736 |  |  | 200 | 0.11111 | 0 | 20.1578 | 0 | 0 | 1.0079 | 21.1657 | 1.95% |  | 1200 | 0.66667 | 0 | 107.2326 | 0 | 0 | 10.7233 | 117.9558 | 10.86% |  | 7000 | 3.8889 | 12 | 559.0633 | 112.7 | 82.6708 | 188.6085 | 943.0427 | 86.86% |  | 80 | 0.044444 | 0 | 3.3422 | 0 | 0 | 0.16711 | 3.5093 | 0.3232%
5 | Laser System Development | [8 empty] | 25.85% | 10915.2851 | [9 empty] | 339.2498 | [9 empty] | 2291.7931 | [9 empty] | 8139.052 | [9 empty] | 145.1902
5.1 | Laser Enclosure | 1224 | 0.68 | 0 | 81.4522 | 51.47 | 0 | 29.2429 | 162.165 |  |  | 160 | 0.088889 | 0 | 11.6309 | 0 | 0 | 2.5588 | 14.1897 | 8.75% |  | 544 | 0.30222 | 0 | 39.4365 | 0 | 0 | 8.676 | 48.1125 | 29.67% |  | 520 | 0.28889 | 0 | 30.3848 | 51.47 | 0 | 18.0081 | 99.8628 | 61.58% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.2 | Laser | 3440 | 1.9111 | 29 | 328.979 | 5690.851 | 109.3803 | 1159.9989 | 7289.2092 |  |  | 820 | 0.45556 | 4 | 85.8859 | 0 | 15.0869 | 10.0973 | 111.0701 | 1.524% |  | 998 | 0.55444 | 6 | 97.6385 | 1438.124 | 22.6304 | 264.9268 | 1823.3197 | 25.01% |  | 1562 | 0.86778 | 19 | 137.9678 | 4131.727 | 71.663 | 868.2716 | 5209.6293 | 71.47% |  | 60 | 0.033333 | 0 | 7.4869 | 121 | 0 | 16.7033 | 145.1902 | 1.992%
5.3 | Laser Launch Facility | 3900 | 2.1667 | 2 | 266.0708 | 1340.46 | 7.3435 | 516.4398 | 2130.314 |  |  | 856 | 0.47556 | 0 | 60.6664 | 20 | 0 | 25.8132 | 106.4796 | 4.998% |  | 1220 | 0.67778 | 0 | 88.2133 | 0 | 0 | 28.2283 | 116.4416 | 5.466% |  | 1824 | 1.0133 | 2 | 117.1911 | 1320.46 | 7.3435 | 462.3982 | 1907.3928 | 89.54% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4 | Laser Safety Systems | 1812 | 1.0067 | 0 | 133.2959 | 36.05 | 0 | 27.0954 | 196.4413 |  |  | 170 | 0.094444 | 0 | 13.1066 | 0 | 0 | 2.0971 | 15.2037 | 7.74% |  | 647 | 0.35944 | 0 | 49.4437 | 0 | 0 | 7.911 | 57.3547 | 29.2% |  | 995 | 0.55278 | 0 | 70.7456 | 36.05 | 0 | 17.0873 | 123.883 | 63.06% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.5 | Laser System Control | 8105 | 4.5028 | 0 | 543.2381 | 126.3944 | 0 | 107.1412 | 776.7737 |  |  | 910 | 0.50556 | 0 | 75.2501 | 0 | 0 | 12.04 | 87.2901 | 11.24% |  | 2610 | 1.45 | 0 | 208.2311 | 0 | 0 | 33.317 | 241.548 | 31.1% |  | 4585 | 2.5472 | 0 | 259.7569 | 126.3944 | 0 | 61.7842 | 447.9355 | 57.67% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.6 | Laser System Lab I&T | 3126 | 1.7367 | 0 | 192.8866 | 72.1 | 0 | 95.3952 | 360.3818 |  |  | 48 | 0.026667 | 0 | 3.6887 | 0 | 0 | 1.3279 | 5.0166 | 1.392% |  | 48 | 0.026667 | 0 | 3.6887 | 0 | 0 | 1.3279 | 5.0166 | 1.392% |  | 3030 | 1.6833 | 0 | 185.5093 | 72.1 | 0 | 92.7393 | 350.3486 | 97.22% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6 | Science Operations | [8 empty] | 4.266% | 1801.3828 | [9 empty] | 185.4127 | [9 empty] | 849.7564 | [9 empty] | 766.2137 | [9 empty] | 0
6.1 | Multi-System Command Sequencer
6.1.1 | Sequencer Infrastructure | 2120 | 1.1778 | 0 | 182.3847 | 0 | 0 | 23.842 | 206.2267 |  |  | 180 | 0.1 | 0 | 17.6622 | 0 | 0 | 1.9428 | 19.605 | 9.507% |  | 1120 | 0.62222 | 0 | 101.7282 | 0 | 0 | 11.1901 | 112.9183 | 54.75% |  | 820 | 0.45556 | 0 | 62.9943 | 0 | 0 | 10.709 | 73.7033 | 35.74% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.1.2 | Setup Sequences: Configurations & Calibrations | 980 | 0.54444 | 0 | 83.9059 | 0 | 0 | 11.1533 | 95.0592 |  |  | 100 | 0.055556 | 0 | 9.8123 | 0 | 0 | 1.0794 | 10.8917 | 11.46% |  | 470 | 0.26111 | 0 | 42.033 | 0 | 0 | 4.6236 | 46.6566 | 49.08% |  | 410 | 0.22778 | 0 | 32.0606 | 0 | 0 | 5.4503 | 37.5109 | 39.46% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.1.3 | Observing Sequences | 2520 | 1.4 | 0 | 212.0379 | 0 | 0 | 27.6328 | 239.6707 |  |  | 240 | 0.13333 | 0 | 23.5496 | 0 | 0 | 2.5905 | 26.1401 | 10.91% |  | 1340 | 0.74444 | 0 | 116.6772 | 0 | 0 | 12.8345 | 129.5117 | 54.04% |  | 940 | 0.52222 | 0 | 71.811 | 0 | 0 | 12.2079 | 84.0189 | 35.06% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.1.4 | System Health and Troubleshooting | 1230 | 0.68333 | 0 | 105.2674 | 0 | 0 | 17.3067 | 122.5741 |  |  | 100 | 0.055556 | 0 | 9.8123 | 0 | 0 | 1.0794 | 10.8917 | 8.886% |  | 600 | 0.33333 | 0 | 54.789 | 0 | 0 | 9.3141 | 64.1032 | 52.3% |  | 530 | 0.29444 | 0 | 40.666 | 0 | 0 | 6.9132 | 47.5792 | 38.82% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.2 | User Interfaces
6.2.1 | User Interface Infrastructure | 1110 | 0.61667 | 0 | 96.5563 | 0 | 0 | 10.6074 | 107.1637 |  |  | 180 | 0.1 | 0 | 17.6622 | 0 | 0 | 1.5896 | 19.2518 | 17.96% |  | 520 | 0.28889 | 0 | 46.9392 | 0 | 0 | 4.2245 | 51.1637 | 47.74% |  | 410 | 0.22778 | 0 | 31.9549 | 0 | 0 | 4.7932 | 36.7482 | 34.29% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.2.2 | Setup Operations: Configuration, Calibrations | 750 | 0.41667 | 0 | 64.4013 | 0 | 0 | 7.4867 | 71.888 |  |  | 80 | 0.044444 | 0 | 7.8499 | 0 | 0 | 0.70649 | 8.5564 | 11.9% |  | 310 | 0.17222 | 0 | 28.3757 | 0 | 0 | 2.5538 | 30.9296 | 43.02% |  | 360 | 0.2 | 0 | 28.1757 | 0 | 0 | 4.2264 | 32.402 | 45.07% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.2.3 | Observations User Interfaces for operator, observer, specialist | 1790 | 0.99444 | 0 | 152.4075 | 0 | 0 | 17.3284 | 169.7359 |  |  | 240 | 0.13333 | 0 | 23.5496 | 0 | 0 | 2.1195 | 25.6691 | 15.12% |  | 770 | 0.42778 | 0 | 68.6616 | 0 | 0 | 6.1795 | 74.8411 | 44.09% |  | 780 | 0.43333 | 0 | 60.1963 | 0 | 0 | 9.0294 | 69.2257 | 40.78% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.3 | Pre- & Post-Observing Support
6.3.1 | Users' Documentation | 300 | 0.16667 | 0 | 24.8414 | 0 | 0 | 1.4905 | 26.3319 |  |  | 20 | 0.011111 | 0 | 1.9625 | 0 | 0 | 0.11775 | 2.0802 | 7.9% |  | 100 | 0.055556 | 0 | 8.2805 | 0 | 0 | 0.49683 | 8.7773 | 33.33% |  | 180 | 0.1 | 0 | 14.5985 | 0 | 0 | 0.87591 | 15.4744 | 58.77% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.3.2 | Planning Tools | 3475 | 1.9306 | 5 | 287.8739 | 0 | 18.8587 | 35.2503 | 341.9828 |  |  | 340 | 0.18889 | 0 | 30.2982 | 0 | 0 | 2.7268 | 33.025 | 9.657% |  | 1570 | 0.87222 | 3 | 137.7137 | 0 | 11.3152 | 13.4126 | 162.4415 | 47.5% |  | 1565 | 0.86944 | 2 | 119.8619 | 0 | 7.5435 | 19.1108 | 146.5162 | 42.84% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.3.3 | Data Products | 3340 | 1.8556 | 0 | 249.2677 | 0 | 0 | 52.1718 | 301.4395 |  |  | 250 | 0.13889 | 0 | 18.1481 | 0 | 0 | 3.2667 | 21.4147 | 7.104% |  | 1390 | 0.77222 | 0 | 109.393 | 0 | 0 | 19.6907 | 129.0838 | 42.82% |  | 1700 | 0.94444 | 0 | 121.7266 | 0 | 0 | 29.2144 | 150.941 | 50.07% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.4 | Data Server | 680 | 0.37778 | 0 | 51.2468 | 39.14 | 0 | 28.9238 | 119.3105 |  |  | 70 | 0.038889 | 0 | 5.975 | 0 | 0 | 1.912 | 7.8871 | 6.611% |  | 370 | 0.20556 | 0 | 29.7952 | 0 | 0 | 9.5345 | 39.3297 | 32.96% |  | 240 | 0.13333 | 0 | 15.4765 | 39.14 | 0 | 17.4773 | 72.0938 | 60.43% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7 | Telescope & Summit Engineering | [8 empty] | 4.575% | 1931.6826 | [9 empty] | 116.1232 | [9 empty] | 505.129 | [9 empty] | 1289.9171 | [9 empty] | 20.5133
7.1 | Telescope Performance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7.2 | Infrastructure Mods for AO | 6270 | 3.4833 | 3 | 381.016 | 351.21 | 12.1752 | 181.7978 | 926.199 |  |  | 660 | 0.36667 | 1 | 45.3446 | 5 | 3.7717 | 14.0702 | 68.1865 | 7.362% |  | 2450 | 1.3611 | 0 | 164.9152 | 30 | 0.86 | 39.155 | 234.9303 | 25.36% |  | 3160 | 1.7556 | 2 | 170.7562 | 316.21 | 7.5435 | 128.5725 | 623.0822 | 67.27% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7.3 | Infrastructure Mods for Laser | 4423 | 2.4572 | 0 | 247.8126 | 354.002 | 0 | 132.3992 | 734.2138 |  |  | 280 | 0.15556 | 0 | 21.8577 | 0 | 0 | 4.8087 | 26.6664 | 3.632% |  | 1136 | 0.63111 | 0 | 78.208 | 70 | 0 | 32.6058 | 180.8138 | 24.63% |  | 3007 | 1.6706 | 0 | 147.7469 | 284.002 | 0 | 94.9848 | 526.7337 | 71.74% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
7.4 | OSIRIS Modifications | 1200 | 0.66667 | 0 | 89.5415 | 46.35 | 0 | 17.396 | 153.2875 |  |  | 100 | 0.055556 | 0 | 8.303 | 0 | 0 | 0.8303 | 9.1333 | 5.958% |  | 380 | 0.21111 | 0 | 32.8039 | 0 | 0 | 3.2804 | 36.0843 | 23.54% |  | 520 | 0.28889 | 0 | 29.7861 | 46.35 | 0 | 11.4204 | 87.5565 | 57.12% |  | 200 | 0.11111 | 0 | 18.6485 | 0 | 0 | 1.8648 | 20.5133 | 13.38%
7.5 | Interferometer and OHANA Mods | 1024 | 0.56889 | 0 | 74.6213 | 30.72 | 0 | 12.641 | 117.9823 |  |  | 61 | 0.033889 | 0 | 4.8366 | 6 | 0 | 1.3004 | 12.137 | 10.29% |  | 619 | 0.34389 | 0 | 47.5898 | 0 | 0 | 5.7108 | 53.3006 | 45.18% |  | 344 | 0.19111 | 0 | 22.1949 | 24.72 | 0 | 5.6298 | 52.5447 | 44.54% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
8 | Telescope Integration & Test | [8 empty] | 6.478% | 2735.4636 | [9 empty] | 50.2323 | [9 empty] | 114.6876 | [9 empty] | 136.369 | [9 empty] | 2434.1746
8.1 | Old AO/Laser Removal | 4040 | 2.2444 | 0 | 220.1483 | 20.6 | 0 | 85.313 | 326.0613 |  |  | 120 | 0.066667 | 0 | 7.6326 | 0 | 0 | 0.76326 | 8.3958 | 2.575% |  | 480 | 0.26667 | 0 | 26.7447 | 0 | 0 | 2.6745 | 29.4191 | 9.023% |  | 40 | 0.022222 | 0 | 2.2437 | 0 | 0 | 0.22437 | 2.4681 | 0.7569% |  | 3400 | 1.8889 | 0 | 183.5273 | 20.6 | 0 | 81.6509 | 285.7783 | 87.65%
8.2 | Laser Enclosure Integration | 1040 | 0.57778 | 0 | 46.774 | 40.17 | 0 | 17.3888 | 104.3327 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 1040 | 0.57778 | 0 | 46.774 | 40.17 | 0 | 17.3888 | 104.3327 | 100%
8.3 | AO Enclosure Integration | 1100 | 0.61111 | 0 | 51.8676 | 40.685 | 0 | 24.0637 | 116.6163 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 1100 | 0.61111 | 0 | 51.8676 | 40.685 | 0 | 24.0637 | 116.6163 | 100%
8.4 | AO System Install + I&T | 6850 | 3.8056 | 4 | 443.1758 | 10.3 | 27.5569 | 92.7978 | 573.8306 |  |  | 170 | 0.094444 | 0 | 10.8572 | 0 | 0 | 0.86858 | 11.7258 | 2.043% |  | 100 | 0.055556 | 0 | 6.7647 | 0 | 0 | 0.54118 | 7.3059 | 1.273% |  | 180 | 0.1 | 0 | 10.7842 | 0 | 0 | 0.86273 | 11.6469 | 2.03% |  | 6400 | 3.5556 | 4 | 414.7697 | 10.3 | 27.5569 | 90.5253 | 543.1519 | 94.65%
8.5 | Laser System Install + I&T | 3798 | 2.11 | 0 | 230.7276 | 0 | 0 | 58.7255 | 289.4531 |  |  | 212 | 0.11778 | 0 | 16.2065 | 0 | 0 | 1.2965 | 17.5031 | 6.047% |  | 176 | 0.097778 | 0 | 13.1847 | 0 | 0 | 1.0548 | 14.2395 | 4.919% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 3410 | 1.8944 | 0 | 201.3363 | 0 | 0 | 56.3742 | 257.7105 | 89.03%
8.6 | LGS AO System On-sky I&T | 5030 | 2.7944 | 12 | 401.1458 | 0 | 49.5608 | 89.5637 | 540.2703 |  |  | 40 | 0.022222 | 0 | 3.4143 | 0 | 0 | 0.30729 | 3.7216 | 0.6888% |  | 200 | 0.11111 | 0 | 18.6485 | 0 | 0 | 1.6784 | 20.3269 | 3.762% |  | 590 | 0.32778 | 0 | 46.2311 | 0 | 0 | 11.0955 | 57.3265 | 10.61% |  | 4200 | 2.3333 | 12 | 332.852 | 0 | 49.5608 | 76.4826 | 458.8954 | 84.94%
8.7 | Performance Characterization | 3760 | 2.0889 | 27 | 265.4908 | 0 | 148.0768 | 123.764 | 537.3316 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 40 | 0.022222 | 0 | 1.9147 | 0 | 0 | 0.26806 | 2.1828 | 0.4062% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 3720 | 2.0667 | 27 | 263.5761 | 0 | 148.0768 | 123.4959 | 535.1488 | 99.59%
8.8 | Science Verification | 2420 | 1.3444 | 17 | 150.49 | 0 | 64.1195 | 32.9581 | 247.5676 |  |  | 80 | 0.044444 | 0 | 8.383 | 0 | 0 | 0.50298 | 8.886 | 3.589% |  | 460 | 0.25556 | 2 | 31.337 | 0 | 7.5435 | 2.3328 | 41.2133 | 16.65% |  | 600 | 0.33333 | 5 | 36.1647 | 0 | 18.8587 | 9.9042 | 64.9276 | 26.23% |  | 1280 | 0.71111 | 10 | 74.6053 | 0 | 37.7174 | 20.2181 | 132.5407 | 53.54%
9 | Operations Transition | [8 empty] | 1.777% | 750.4973 | [9 empty] | 15.0267 | [9 empty] | 21.8383 | [9 empty] | 636.41 | [9 empty] | 77.2223
9.1 | Operations Plans | 636 | 0.35333 | 0 | 42.9582 | 515 | 0 | 80.7288 | 638.6869 |  |  | 96 | 0.053333 | 0 | 6.9689 | 0 | 0 | 0.20907 | 7.1779 | 1.124% |  | 108 | 0.06 | 0 | 7.84 | 0 | 0 | 0.2352 | 8.0752 | 1.264% |  | 216 | 0.12 | 0 | 14.691 | 504.7 | 0 | 77.9086 | 597.2996 | 93.52% |  | 216 | 0.12 | 0 | 13.4584 | 10.3 | 0 | 2.3758 | 26.1342 | 4.092%
9.2 | Operations Handover
9.2.1 | Operations Personnel Training | 520 | 0.28889 | 10 | 41.8555 | 0 | 37.7174 | 7.9573 | 87.5301 |  |  | 50 | 0.027778 | 0 | 5.1727 | 0 | 0 | 0.51727 | 5.69 | 6.501% |  | 90 | 0.05 | 0 | 9.0977 | 0 | 0 | 0.90977 | 10.0074 | 11.43% |  | 180 | 0.1 | 5 | 13.0666 | 0 | 18.8587 | 3.1925 | 35.1178 | 40.12% |  | 200 | 0.11111 | 5 | 14.5184 | 0 | 18.8587 | 3.3377 | 36.7148 | 41.95%
9.2.2 | Documentation & Spares Transition | 290 | 0.16111 | 0 | 22.073 | 0 | 0 | 2.2073 | 24.2803 |  |  | 20 | 0.011111 | 0 | 1.9625 | 0 | 0 | 0.19625 | 2.1587 | 8.891% |  | 40 | 0.022222 | 0 | 3.4143 | 0 | 0 | 0.34143 | 3.7557 | 15.47% |  | 50 | 0.027778 | 0 | 3.6296 | 0 | 0 | 0.36296 | 3.9926 | 16.44% |  | 180 | 0.1 | 0 | 13.0666 | 0 | 0 | 1.3067 | 14.3733 | 59.2%
| Total = | 231944.5 | 128.8581 | 549 | 16044.9769 | 16803.9635 | 1681.2938 | 7696.5409 | 42226.7751 | 100% | 42226.7751 | 34375.1 | 19.0973 | 95 | 2581.5572 | 216.199 | 223.711 | 457.575 | 3479.0421 | 8.239% | 3479.0421 | 75528.9 | 41.9605 | 136 | 5515.9272 | 1827.249 | 354.2244 | 1402.6898 | 9100.0904 | 21.55% | 9100.0904 | 88076.5 | 48.9314 | 195 | 5660.9188 | 14510.1345 | 625.5955 | 5234.3628 | 26031.0117 | 61.65% | 26031.0117 | 34174 | 18.9856 | 123 | 2286.5737 | 250.381 | 477.7629 | 601.9133 | 3616.631 | 8.565% | 3616.631

## NIR Imager ROM
| 1 FTE | 1824 | hours
| inflation | 3.5% | % per annum
|  | 2 |  | 3 |  | 4 |  | 5 |  | 6
|  | Calendar 2009 |  | Calendar 2010 |  | Calendar 2011 |  | Calendar 2012 |  | Calendar 2013 (delivery to NGAO 4/5/13)
Project Phase |  | PD |  | DD |  | FSD
Totals
Expenses | Notes | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | FY08 rates (see notes)
Labor
Optical Engineering | 1,2 | 912 | 58617.432 | 912 | 60669.0421 | 912 | 62792.4586 |  | 0 |  | 0 | 2736 | 182078.9327 | 60
Mechanical Engineering | 1,2 | 2736 | 175852.296 | 2736 | 182007.1264 | 912 | 62792.4586 | 912 | 64990.1946 | 228 | 16816.2129 | 7524 | 502458.2885 | 60
Electrical Engineering | 1,2 | 364.8 | 23446.9728 | 364.8 | 24267.6168 | 912 | 62792.4586 | 912 | 64990.1946 | 228 | 16816.2129 | 2781.6 | 192313.4558 | 60
Software Engineering | 1,2 | 364.8 | 23446.9728 | 364.8 | 24267.6168 | 912 | 62792.4586 | 912 | 64990.1946 | 228 | 16816.2129 | 2781.6 | 192313.4558 | 60
Support Astronomer/Project Scientist | 3 | 364.8 | 22274.6242 | 364.8 | 23054.236 | 364.8 | 23861.1343 | 364.8 | 24696.274 | 91.2 | 6390.1609 | 1550.4 | 100276.4293 | 57
Other (management, technical staff)
Management | 4 | 456 | 31751.109 | 456 | 32862.3978 | 456 | 34012.5817 | 456 | 35203.0221 | 114 | 9108.782 | 1938 | 142937.8926 | 65
Technicians | 5 |  | 0 |  | 0 | 2736 | 109886.8025 | 2736 | 113732.8406 | 912 | 39237.83 | 6384 | 262857.4732 | 35
Total Salaries and Wages |  |  | 335389.4068 |  | 347128.036 |  | 418930.3529 |  | 368602.7206 |  | 105185.4115 |  | 1575235.9278
Fringe Benefits | 6 |  | 100616.822 |  | 104138.4108 |  | 125679.1059 |  | 110580.8162 |  | 31555.6234 |  | 472570.7783
Total Salaries, Wages and Fringe Benefits |  |  | 436006.2288 |  | 451266.4468 |  | 544609.4588 |  | 479183.5368 |  | 136741.0349 |  | 2047806.7061
Procurements
Equipment and Fabrications |  |  |  |  | 600000 |  | 431250 |  | 431250 |  |  |  | 1462500
Misc. Supplies and Meeting Costs |  |  | 10000 |  | 10712.25 |  | 11087.1787 |  | 11475.23 |  | 2969.2158 |  | 46243.8745
Travel |  |  | 20000 |  | 21424.5 |  | 22174.3575 |  | 22950.46 |  | 11876.8631 |  | 98426.1806
Total Non-Labor Costs |  |  | 30000 |  | 632136.75 |  | 464511.5363 |  | 465675.69 |  | 14846.0788 |  | 1607170.0551
Project Total |  |  | 466006.2288 |  | 1083403.1968 |  | 1009120.995 |  | 944859.2268 |  | 151587.1137 |  | 3654976.7612
1. Labor cost based on a blended WMKO/mainland rate of $60 per hour in FY08.
2. Inflation at 3.5% per year applied to labor.
3. Labor cost based on a WMKO rate of $57 per hour in FY08, assume academic appointment (zero cost) for other science participation.
4. Management labor cost based on a WMKO senior management rate of $65 per hour in FY08
5. Technician labor cost based on a blended WMKO/mainland rate of $35 per hour in FY08.
6. Benefits at 30% rate.
7. Inflation applied at 4% per year.
Equipment and Fabrication Estimate
Dewar
Structure and shell | 200000
Optics | 600000
Filter wheel | 40000
Coronagraph | 80000
Detector (Hawaii-2RG) | 485000
Pulse tube cooler | 20000
Electronics
Motion control | 6000
Temperature and vacuum | 6500
Detector target computer | 3000
Host computer | 5000
Power control | 4000
Enclosure | 3000
Cables and interconnects | 10000
Total | 1462500

## Vis Imager ROM
| 1 FTE | 1824 | hours
| inflation | 3.5% | % per annum
|  | 2 |  | 3 |  | 4 |  | 5 |  | 6
|  | Calendar 2009 |  | Calendar 2010 |  | Calendar 2011 |  | Calendar 2012 |  | Calendar 2013 (delivery to NGAO 4/5/13)
Project Phase |  | PD |  | DD |  | FSD
Totals
Expenses | Notes | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | FY08 rates (see notes)
Labor
Optical Engineering | 1,2 | 912 | 58617.432 | 912 | 60669.0421 | 912 | 62792.4586 |  | 0 |  | 0 | 2736 | 182078.9327 | 60
Mechanical Engineering | 1,2 | 2736 | 175852.296 | 2736 | 182007.1264 | 912 | 62792.4586 | 912 | 64990.1946 | 228 | 16816.2129 | 7524 | 502458.2885 | 60
Electrical Engineering | 1,2 | 364.8 | 23446.9728 | 364.8 | 24267.6168 | 912 | 62792.4586 | 912 | 64990.1946 | 228 | 16816.2129 | 2781.6 | 192313.4558 | 60
Software Engineering | 1,2 | 364.8 | 23446.9728 | 364.8 | 24267.6168 | 912 | 62792.4586 | 912 | 64990.1946 | 228 | 16816.2129 | 2781.6 | 192313.4558 | 60
Support Astronomer/Project Scientist | 3 | 364.8 | 22274.6242 | 364.8 | 23054.236 | 364.8 | 23861.1343 | 364.8 | 24696.274 | 91.2 | 6390.1609 | 1550.4 | 100276.4293 | 57
Other (management, technical staff)
Management | 4 | 456 | 31751.109 | 456 | 32862.3978 | 456 | 34012.5817 | 456 | 35203.0221 | 114 | 9108.782 | 1938 | 142937.8926 | 65
Technicians | 5 |  | 0 |  | 0 | 2736 | 109886.8025 | 2736 | 113732.8406 | 912 | 39237.83 | 6384 | 262857.4732 | 35
Total Salaries and Wages |  |  | 335389.4068 |  | 347128.036 |  | 418930.3529 |  | 368602.7206 |  | 105185.4115 |  | 1575235.9278
Fringe Benefits | 6 |  | 100616.822 |  | 104138.4108 |  | 125679.1059 |  | 110580.8162 |  | 31555.6234 |  | 472570.7783
Total Salaries, Wages and Fringe Benefits |  |  | 436006.2288 |  | 451266.4468 |  | 544609.4588 |  | 479183.5368 |  | 136741.0349 |  | 2047806.7061
Procurements
Equipment and Fabrications |  |  |  |  | 600000 |  | 307250 |  | 307250 |  |  |  | 1214500
Misc. Supplies and Meeting Costs |  |  | 10000 |  | 10712.25 |  | 11087.1787 |  | 11475.23 |  | 2969.2158 |  | 46243.8745
Travel |  |  | 20000 |  | 21424.5 |  | 22174.3575 |  | 22950.46 |  | 11876.8631 |  | 98426.1806
Total Non-Labor Costs |  |  | 30000 |  | 632136.75 |  | 340511.5363 |  | 341675.69 |  | 14846.0788 |  | 1359170.0551
Project Total |  |  | 466006.2288 |  | 1083403.1968 |  | 885120.995 |  | 820859.2268 |  | 151587.1137 |  | 3406976.7612
1. Labor cost based on a blended WMKO/mainland rate of $60 per hour in FY08.
2. Inflation at 3.5% per year applied to labor.
3. Labor cost based on a WMKO rate of $57 per hour in FY08, assume academic appointment (zero cost) for other science participation.
4. Management labor cost based on a WMKO senior management rate of $65 per hour in FY08
5. Technician labor cost based on a blended WMKO/mainland rate of $35 per hour in FY08.
6. Benefits at 30% rate.
7. Inflation applied at 4% per year.
Equipment and Fabrication Estimate
Structure | 100000
Optics | 600000
Filter wheel | 25000
Coronagraph | 60000
Detector (LBNL 4K x 4K) | 300000
Detector dewar | 80000
Cryotiger cooler | 12000
Electronics
Motion control | 6000
Temperature and vacuum | 6500
Detector target computer | 3000
Host computer | 5000
Power control | 4000
Enclosure | 3000
Cables and interconnects | 10000
Total | 1214500

## Global
ID # | Idea | Current Estimate | Discussion | Cost Savings
1 | Upgrade existing Keck AO system |  | See KAON 500 & 502.
2 | Put NGAO on K1 instead of K2 |  | Reuse of launch telescope & laser enclosure at minimum
3 | Reduce the field size from 150" diameter to ? |  | Optics in first relay scale with the field size
4 | Reduce the number of subapertures from 64 to 48 or 40
5
6
7
8
9
10
11
12
13
14
15
16
17
18

## AO System
ID # | Idea | Current Estimate | Discussion | Cost Savings
1 | Single relay instead of cascaded relay |  | See KAON 628 | None
2 | Revisit single level optical relay option |  | At least one of the pros of the two-level approach (MCAO-upgrade path) could potentially be discounted. | Potentially ~$90k for 2nd tier structure
3 | Minimize the volume to be refrigerated | $0.77M in FY08 $ including contingency, excluding the effort to implement this large of a refrigeration unit | Only the science path optics to the IR instruments need to be cold. Development & operational cost savings could result from having as many of the other elements as possible at ambient temperature at the cost of interface flanges for the instruments and potentially windows for other elements. Having the LGS WFS unit at ambient temperature would be particularly advantageous. Potentially allows the reuse of some of the existing AO enclosure.
4 | Reduce the number of LGS WFS units | $3.0M in FY08 $ for the LGS WFS assembly | This is a byproduct of reducing the number of LGS
5 | Reduce the number of deployable LGS WFS units |  | This is a byproduct of reducing the number of movable LGS
6 | Do not refrigerate the LGS WFS
7 | Reduce the number of LGS WFS subapertures |  | This is a byproduct of reducing the number of real-time controlled subapertures.
8 | Reduce the number of LGS WFS lenslets |  | Con: Reduced flexibility for different conditions
9 | Collaborate on the LOWFS assembly to reduce cost | $2.29M in FY08 $ including contingency & excluding risk mitigation | TMT has similar needs. COO has put in a relevant proposal for a robotic AO telescope.
10 | Only provide one TWFS
11 | Reduce the capabilities of the NGS WFS |  | Reduce number of lenslets
12 | Revisit the need for ADCs in the LOWFS |  | This is tied to multiple other elements
13 | Reduce the number of degrees of freedom to be controlled | $1.45M in FY08 $ including contingency & excluding system I&T | This is tied to multiple other elements
14 | Reduce the number of degrees of freedom to be input & controlled by the RTC |  | The complexity of the system is directly scalable to the number of degrees of freedom
15
16
17
18
19
20
21

## Laser Facility
ID # | Idea | Current Estimate | Discussion | Cost Savings
1 | Refine laser cost estimate | $5.7M for two 50W lasers plus $0.3M in labor & $1.2M in contingency | We are collaborating with ESO, TMT & GMT to insure the lasers we will need will be available when needed. ESO has received five vendor bids to develop laser preliminary designs and 2 to 3 will be funded yielding designs & fixed price quotes by the end of CY09. This strongly leverages our dollars & reduces risk. | TBD. May be able to reduce cost estimate & contingency
2 | Reduce laser power requirement to 75W |  | Con: Reduced performance
3 | Assume laser on elevation moving part of telescope | $0.162M for laser enclosure & $2.1M for launch facility including contingency, but excluding lab & telescope I&T. | All the laser proposals to ESO commit to this requirement. Pro: Removes need to have a tracking beam transport system. Pro: Laser enclosure is small. Con: Need to get cooling & cabling onto El ring | $0.25M
4 | Reduce the number of laser beacons |  | Pro: Reduces complexity Con: Reduces flexibility
5 | Assume a fixed central laser asterism & only 3 moving beacons |  | Pro: Reduces complexity Con: Reduces flexibility
6 | Procure & implement the top-end laser launch facility in FY10 |  | Basis of an MRI proposal that is being considered. Pro: Early procurement reduces then-year $. Con: Some risk associated with procurement prior to final design
7
8
9
10
11
12
13
14
15
16
17
18
|  |  | Total savings ($M) = | 0.25

## Science Instruments
ID # | Idea | Current Estimate | Discussion | Cost Savings ($M)
1 | Implement a single NIR IFU instead of the deployable multi-IFU | $14M for deployable multi-IFU in FY06 $ |  | 10
2 | Do not implement OSIRIS with NGAO | $0.15M for OSIRIS mods excluding infrastructure in AO enclosure & I&T | Con: OSIRIS offers an early instrument capability | 0.25
3 | Implement OSIRIS in the f/15 beam after the 1st relay |  | Space potentially available if d-IFS not in this location. Pro: No need for reimaging optics.
4 | No coronagraph in visible imager | $60k for coronagraph hardware | Not required to meet reduced companion sensitivity requirements | 0.1
5 | Reduce visible imager detector to 2kx2k | $300k for 4kx4k LBNL | 4kx4k in current cost estimate. Science does not require this large a field. | 0.15
6 | Exploit commonalities between instruments & with NGAO
7 | Exploit controls commonalities between instruments & NGAO
8 | Don't implement a visible imager | $3.45M in ~ then-year $ | The NIR imager may be able to provide some capability at wavelengths down to ~ 800 nm.
9 | Don't provide a visible IFU |  | Already part of the baseline cost not to provide.
10
11 |  |  | Total savings ($M), excluding item 1 = | 0.5
12
13
14
15
16
17
18
19