## Sheet1
WBS |  | Start | Finish | Total | BB | RK | JB | MB | JC | RD | RF | DG | EJ | JJ | DLM | CL | AM | CN | MR | PS | VV
3.2 | AO System
3.2.1 | AO System Architecture | 2007-09-04 08:00 | 2007-11-23 17:00 | 40 | DG: 40
3.2.2 | AO Enclosure | 2007-10-01 08:00 | 2007-11-07 17:00 | 40 | JB: 40
3.2.3 | Opto-mechanical
3.2.3.1 | Field Rotation | 2007-09-04 08:00 | 2007-11-02 17:00 | 45 | BB: 5; RK: 25; CL: 15
3.2.3.2 | Optical Relay | 2007-09-04 08:00 | 2007-11-02 17:00 | 60 | BB: 5; RK: 35; RD: 10; CL: 10
3.2.3.3 | Optical Switchyard | 2007-09-04 08:00 | 2007-11-02 17:00 | 50 | BB: 5; RK: 20; CL: 25
3.2.3.4 | Optical Support Structure | 2007-11-05 08:00 | 2007-11-30 17:00 | 45 | BB: 3; RK: 12; CL: 30
3.2.3.5 | Wavefront Sensors
3.2.3.5.1 | High Order LGS Wavefront Sensors | 2007-08-22 15:52 | 2007-11-16 17:00 | 80 | JB: 20; VV: 60
3.2.3.5.2 | High Order NGS Wavefront Sensor | 2007-08-22 15:52 | 2007-11-16 17:00 | 40 | JB: 10; VV: 30
3.2.3.5.3 | Low Order NGS Wavefront Sensors | 2007-08-22 15:52 | 2007-11-16 17:00 | 80 | JB: 20; AM: 20; VV: 40
3.2.3.5.4 | Calibration Wavefront Sensor | 2007-08-22 15:52 | 2007-11-16 17:00 | 40 | CN: 40
3.2.3.6 | Wavefront Correctors
3.2.3.6.1 | Tip/Tilt Corrector | 2007-10-01 08:00 | 2007-11-30 17:00 | 20 | BB: 2; RK: 8; RF: 10
3.2.3.6.2 | Deformable Mirror | 2007-08-13 08:00 | 2007-09-21 17:00 | 50 | BB: 2; RK: 8; CN: 40
3.2.3.6.3 | Tip/tilt Vibration Mitigation | 2007-08-22 15:52 | 2007-09-28 17:00 | 45 | DG: 5; EJ: 20; CN: 20
3.2.3.7 | Acquisition Cameras
3.2.3.7.1 | NGS Acquisition Camera | 2007-10-01 08:00 | 2007-10-26 17:00 | 20 | CN: 20
3.2.3.7.2 | LGS Acquisition Camera | 2007-10-01 08:00 | 2007-10-26 17:00 | 20 | CN: 20
3.2.3.8 | Atmospheric Dispersion Correction | 2007-08-21 08:00 | 2007-12-14 17:00 | 24 | BB: 10; RK: 10; RD: 4
3.2.3.9 | Alignment, Calibration, Diagnostics, Metrology and Monitoring | 2007-05-29 08:00 | 2007-06-29 17:00 | 60 | RF: 20; DLM: 20; CN: 20
3.2.3.10 | Atmospheric Profiler | 2007-08-22 15:52 | 2007-10-02 17:00 | 50 | MB: 50
3.2.3.11 | d-IFU & LOWFS AO & Object Selection | 2007-08-22 15:52 | 2007-11-07 17:00 | 200 | JB: 80; DG: 40; AM: 80
3.2.3.12 | PSF Monitoring Camera | 2007-10-01 08:00 | 2007-10-26 17:00 | 30 | MB: 10; CN: 20
3.2.4 | Non-real-time Control
3.2.4.1 | Non-RTC Software | 2007-06-25 08:00 | 2007-08-31 17:00 | 170 | EJ: 80; JJ: 10; PS: 80
3.2.4.2 | Non-RTC Electronics | 2007-07-23 08:00 | 2007-11-22 17:00 | 160 | JC: 60; EJ: 40; MR: 60
3.2.5 | Real-time Control
3.2.5.1 | RTC Architecture Analysis and Design Study | 2007-08-01 08:00 | 2007-08-31 17:00 | 180 | RF: 40; DG: 20; EJ: 40; MR: 80
3.2.5.2 | RTC Software Module Definition | 2007-09-03 08:00 | 2007-12-03 17:00 | 80 | EJ: 60; MR: 20
3.2.5.3 | RTC Hardware Module Definition | 2007-09-03 08:00 | 2007-12-03 17:00 | 80 | EJ: 20; MR: 60
3.3 | Laser Facility
3.3.1 | Laser System Architecture | 2007-08-27 08:00 | 2007-10-19 17:00 | 80 | VV: 80
3.3.2 | Laser Enclosure | 2007-10-22 08:00 | 2007-12-19 17:00 | 80 | JB: 80
3.3.3 | Laser | 2007-10-22 08:00 | 2007-12-07 17:00 | 20 | VV: 20
3.3.4 | Laser Launch Facility
3.3.4.1 | Laser Beam Transport | 2007-08-06 08:00 | 2007-09-07 17:00 | 50 | JC: 4; CN: 30; VV: 16
3.3.4.2 | Laser Pointing & Diagnostics | 2007-08-06 08:00 | 2007-09-07 17:00 | 80 | BB: 3; JC: 10; CN: 15; VV: 52
3.3.4.3 | Laser Launch Telescope | 2007-08-06 08:00 | 2007-09-07 17:00 | 70 | JC: 10; CN: 30; VV: 30
3.3.5 | Laser Safety Systems
3.3.5.1 | Personnel and Equipment Safety Systems | 2007-10-08 08:00 | 2007-11-02 17:00 | 20 | JC: 20
3.3.5.2 | Aircraft, Satellite & Laser Traffic Control Safety Systems | 2007-10-08 08:00 | 2007-11-02 17:00 | 20 | JC: 20
3.3.6 | Laser System Control
3.3.6.1 | Laser System Software | 2007-10-01 08:00 | 2007-12-14 17:00 | 80 | EJ: 40; PS: 40
3.3.6.2 | Laser System Electronics | 2007-10-01 08:00 | 2007-12-14 17:00 | 70 | JC: 70
|  |  | Total = | 2279 | 35 | 118 | 250 | 60 | 194 | 14 | 70 | 105 | 300 | 10 | 20 | 80 | 100 | 255 | 220 | 120 | 328
|  | change? | original |  | JB: Groups:; DG: Leads
| select here -------------------------> | change | change |  | JB: AO Opto-mechanical; DG: DG
[7 empty] | AO Wavefront Sensors |  |  |  |  | VV
[7 empty] | AO Operational Tools |  |  |  |  | CN
[7 empty] | Laser |  |  |  |  | VV
[7 empty] | Laser Facility |  |  |  |  | JC
[7 empty] | Controls |  |  |  |  | EJ
Note on C51: Don Gavel: Click and select here