## Sheet1
COO Example Work Breakdown Structure (WBS)
Version 1 |  |  |  |  | Principles invoked here:
R. Dekany
1/1/2006 | [15 empty] | Inflated median engineer labor rate |  |  | 1 | $K | per work-year
WBS | WBS Number |  |  |  | WBS Element |  |  |  | Option 1 | Option 2 | Option 3 | Option 1 | Option 2 | Option 3 | Option 1 | Option 2 | Option 3 | Number | Unit | Option 1 | Option 2 | Option 3 | Type | Note | MS Project Task Name
Level | [8 empty] | Cost ($K) | Cost ($K) | Cost ($K) | Cost ($K) | Cost ($K) | Cost ($K) | Cost ($K) | Cost ($K) | Cost ($K) |  | Cost ($K) | Cost ($K) | Cost ($K) | Cost ($K)
4 | TMT.INS.INST.IRMOS |  |  |  | IRMOS |  |  |  | 0 | 0 | 0 | [13 empty] | IRMOS
5 | TMT.INS.INST.IRMOS.MAN | .MAN |  |  | IRMOS Management | Management | [5 empty] | 0 | 0 | 0 | [10 empty] | Management
6 | TMT.INS.INST.IRMOS.MAN.SEN |  | .SEN |  | IRMOS Management Senior |  | Senior | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Senior
6 | TMT.INS.INST.IRMOS.MAN.BUS |  | .BUS |  | IRMOS Management Business Office |  | Business Office | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Business Office
6 | TMT.INS.INST.IRMOS.MAN.SEC |  | .SEC |  | IRMOS Management Sectretarial |  | Sectretarial | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Sectretarial
5 | TMT.INS.INST.IRMOS.SYS | .SYS |  |  | IRMOS Systems Engineering | Systems Engineering | [5 empty] | 0 | 0 | 0 | [10 empty] | Systems Engineering
6 | TMT.INS.INST.IRMOS.SYS.LAB |  | .LAB |  | IRMOS Systems Engineering Labor |  | Labor | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Labor
5 | TMT.INS.INST.IRMOS.RLAY | .RLAY |  |  | IRMOS Offner Relay | Offner Relay | [5 empty] | 0 | 0 | 0 | [10 empty] | Offner Relay
6 | TMT.INS.INST.IRMOS.RLAY.SYS |  | .SYS |  | IRMOS Offner Relay Systems Engineering |  | Systems Engineering | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
6 | TMT.INS.INST.IRMOS.RLAY.ENCL |  | .ENCL |  | IRMOS Offner Relay Enclosure |  | Enclosure | [7 empty] | 0 | 0 | 0 | [7 empty] | Enclosure
7 | TMT.INS.INST.IRMOS.RLAY.ISL |  | .ISL |  | IRMOS Offner Relay Enclosure Insullation |  |  | Insullation | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Insullation
7 | TMT.INS.INST.IRMOS.RLAY.CPR |  | .CPR |  | IRMOS Offner Relay Enclosure Compressor |  |  | Compressor | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Compressor
7 | TMT.INS.INST.IRMOS.RLAY.SAF |  | .SAF |  | IRMOS Offner Relay Enclosure Safety System |  |  | Safety System | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Safety System
6 | TMT.INS.INST.IRMOS.RLAY.STR |  | .STR |  | IRMOS Offner Relay Structure |  | Structure | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Structure
6 | TMT.INS.INST.IRMOS.RLAY.WIN |  | .WIN |  | IRMOS Offner Relay Entrance Window |  | Entrance Window | [7 empty] | 0 | 0 | 0 | [7 empty] | Entrance Window
7 | TMT.INS.INST.IRMOS.RLAY.WIN.WIN |  |  | .WIN | IRMOS Offner Relay Entrance Window Window |  |  | Window | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Window
7 | TMT.INS.INST.IRMOS.RLAY.WIN.MNT |  |  | .MNT | IRMOS Offner Relay Entrance Window Window Mount |  |  | Window Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Window Mount
7 | TMT.INS.INST.IRMOS.RLAY.WIN.CON |  |  | .CON | IRMOS Offner Relay Entrance Window Condensation Mitigation |  |  | Condensation Mitigation | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Condensation Mitigation
6 | TMT.INS.INST.IRMOS.RLAY.M4 |  | .M4 |  | IRMOS Offner Relay M4 Fold Mirror |  | M4 Fold Mirror | [7 empty] | 0 | 0 | 0 | [7 empty] | M4 Fold Mirror
7 | TMT.INS.INST.IRMOS.RLAY.M4.MIR |  |  | .MIR | IRMOS Offner Relay M4 Fold Mirror Mirror |  |  | Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror
7 | TMT.INS.INST.IRMOS.RLAY.M4.MNT |  |  | .MNT | IRMOS Offner Relay M4 Fold Mirror Mirror Mount |  |  | Mirror Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mount
6 | TMT.INS.INST.IRMOS.RLAY.M5/7 |  | .M5/7 |  | IRMOS Offner Relay M5/7 Sphere |  | M5/7 Sphere | [7 empty] | 0 | 0 | 0 | [7 empty] | M5/7 Sphere
7 | TMT.INS.INST.IRMOS.RLAY.M5/7.MIR |  |  | .MIR | IRMOS Offner Relay M5/7 Sphere Mirror |  |  | Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror
7 | TMT.INS.INST.IRMOS.RLAY.M5/7.MNT |  |  | .MNT | IRMOS Offner Relay M5/7 Sphere Mirror Mount |  |  | Mirror Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mount
6 | TMT.INS.INST.IRMOS.RLAY.DIC |  | .DIC |  | IRMOS Offner Relay Dichroic |  | Dichroic | [7 empty] | 0 | 0 | 0 | [7 empty] | Dichroic
7 | TMT.INS.INST.IRMOS.RLAY.DIC.MIR |  |  | .MIR | IRMOS Offner Relay Dichroic Dichroic Mirror |  |  | Dichroic Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Dichroic Mirror
7 | TMT.INS.INST.IRMOS.RLAY.DIC.CEL |  |  | .CEL | IRMOS Offner Relay Dichroic Mirror Cell |  |  | Mirror Cell | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Cell
7 | TMT.INS.INST.IRMOS.RLAY.DIC.CWT |  |  | .CWT | IRMOS Offner Relay Dichroic Mirror Counterweights |  |  | Mirror Counterweights | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Counterweights
7 | TMT.INS.INST.IRMOS.RLAY.DIC.MOT |  |  | .MOT | IRMOS Offner Relay Dichroic Mirror Motor |  |  | Mirror Motor | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Motor
7 | TMT.INS.INST.IRMOS.RLAY.DIC.STR |  |  | .STR | IRMOS Offner Relay Dichroic Support Structure |  |  | Support Structure | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Support Structure
6 | TMT.INS.INST.IRMOS.RLAY.IT |  | .IT |  | IRMOS Offner Relay Integration and Testing |  | Integration and Testing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
5 | TMT.INS.INST.IRMOS.MOAO | .MOAO |  |  | IRMOS MOAO | MOAO | [5 empty] | 0 | 0 | 0 | [10 empty] | MOAO
6 | TMT.INS.INST.IRMOS.MOAO.SYS |  | .SYS |  | IRMOS MOAO Systems Engineering |  | Systems Engineering | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
6 | TMT.INS.INST.IRMOS.MOAO.M6DM |  | .M6DM |  | IRMOS MOAO M6 Deformable Mirror |  | M6 Deformable Mirror | [7 empty] | 0 | 0 | 0 | [7 empty] | M6 Deformable Mirror
7 | TMT.INS.INST.IRMOS.MOAO.M6DM.MIR |  |  | .MIR | IRMOS MOAO M6 Deformable Mirror Mirror |  |  | Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror
7 | TMT.INS.INST.IRMOS.MOAO.M6DM.MNT |  |  | .MNT | IRMOS MOAO M6 Deformable Mirror Mirror Mount |  |  | Mirror Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mount
7 | TMT.INS.INST.IRMOS.MOAO.M6DM.DRV |  |  | .DRV | IRMOS MOAO M6 Deformable Mirror Drive Electronics |  |  | Drive Electronics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Drive Electronics
6 | TMT.INS.INST.IRMOS.MOAO.M6TT |  | .M6TT |  | IRMOS MOAO M6 Tip/Tilt Stage |  | M6 Tip/Tilt Stage | [7 empty] | 0 | 0 | 0 | [7 empty] | M6 Tip/Tilt Stage
7 | TMT.INS.INST.IRMOS.MOAO.M6TT.ACT |  |  | .ACT | IRMOS MOAO M6 Tip/Tilt Stage Actuators |  |  | Actuators | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Actuators
7 | TMT.INS.INST.IRMOS.MOAO.M6TT.DRV |  |  | .DRV | IRMOS MOAO M6 Tip/Tilt Stage Drive Electronics |  |  | Drive Electronics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Drive Electronics
7 | TMT.INS.INST.IRMOS.MOAO.M6TT.STR |  |  | .STR | IRMOS MOAO M6 Tip/Tilt Stage Support Structure |  |  | Support Structure | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Support Structure
6 | TMT.INS.INST.IRMOS.RLAY.M6ME |  | .M6ME |  | IRMOS MOAO M6 Real Time Metrology |  | M6 Real Time Metrology | [7 empty] | 0 | 0 | 0 | [7 empty] | M6 Real Time Metrology
7 | TMT.INS.INST.IRMOS.RLAY.M6ME.SYS |  |  | .SYS | IRMOS MOAO M6 Real Time Metrology Systems Engineering |  |  | Systems Engineering | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
7 | TMT.INS.INST.IRMOS.RLAY.M6ME.SRC |  |  | .SRC | IRMOS MOAO M6 Real Time Metrology Source |  |  | Source | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Source
7 | TMT.INS.INST.IRMOS.RLAY.M6ME.CAM |  |  | .CAM | IRMOS MOAO M6 Real Time Metrology Camera |  |  | Camera | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Camera
7 | TMT.INS.INST.IRMOS.RLAY.M6ME.MNT |  |  | .MNT | IRMOS MOAO M6 Real Time Metrology Mount |  |  | Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mount
7 | TMT.INS.INST.IRMOS.RLAY.M6ME.IT |  |  | .IT | IRMOS MOAO M6 Real Time Metrology Integration and Testing |  |  | Integration and Testing | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
6 | TMT.INS.INST.IRMOS.MOAO.M11 |  | .M11 |  | IRMOS MOAO M11 (MEMS-DM) |  | M11 (MEMS-DM) | [7 empty] | 0 | 0 | 0 | [7 empty] | M11 (MEMS-DM)
7 | TMT.INS.INST.IRMOS.MOAO.M11.DM |  |  | .DM | IRMOS MOAO M11 (MEMS-DM) Mirror |  |  | Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror
7 | TMT.INS.INST.IRMOS.MOAO.M11.MNT |  |  | .MNT | IRMOS MOAO M11 (MEMS-DM) Mirror Mount |  |  | Mirror Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mount
7 | TMT.INS.INST.IRMOS.MOAO.M11.DRV |  |  | .DRV | IRMOS MOAO M11 (MEMS-DM) Drive Electronics |  |  | Drive Electronics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Drive Electronics
7 | TMT.INS.INST.IRMOS.MOAO.M11.IT |  |  | .IT | IRMOS MOAO M11 (MEMS-DM) Integration and Testing |  |  | Integration and Testing | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
6 | TMT.INS.INST.IRMOS.MOAO.M11T |  | .M11T |  | IRMOS MOAO M11 Tip/Tilt Stage |  | M11 Tip/Tilt Stage | [7 empty] | 0 | 0 | 0 | [7 empty] | M11 Tip/Tilt Stage
7 | TMT.INS.INST.IRMOS.MOAO.M11T.ACT |  |  | .ACT | IRMOS MOAO M11 Tip/Tilt Stage Actuators |  |  | Actuators | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Actuators
7 | TMT.INS.INST.IRMOS.MOAO.M11T.DRV |  |  | .DRV | IRMOS MOAO M11 Tip/Tilt Stage Drive Electronics |  |  | Drive Electronics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Drive Electronics
7 | TMT.INS.INST.IRMOS.MOAO.M11T.STR |  |  | .STR | IRMOS MOAO M11 Tip/Tilt Stage Support Structure |  |  | Support Structure | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Support Structure
6 | TMT.INS.INST.IRMOS.MOAO.LGSW |  | .LGSW |  | IRMOS MOAO Laser Guide Star Wavefront Sensor |  | Laser Guide Star Wavefront Sensor | [7 empty] | 0 | 0 | 0 | [7 empty] | Laser Guide Star Wavefront Sensor
7 | TMT.INS.INST.IRMOS.MOAO.LGSW.OPT |  |  | .OPT | IRMOS MOAO Laser Guide Star Wavefront Sensor Zoom Optics |  |  | Zoom Optics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Zoom Optics
7 | TMT.INS.INST.IRMOS.MOAO.LGSW.LA |  |  | .LA | IRMOS MOAO Laser Guide Star Wavefront Sensor Lenslet Array |  |  | Lenslet Array | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Lenslet Array
7 | TMT.INS.INST.IRMOS.MOAO.LGSW.CAM |  |  | .CAM | IRMOS MOAO Laser Guide Star Wavefront Sensor Camera |  |  | Camera | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Camera
6 | TMT.INS.INST.IRMOS.MOAO.NGSW |  | .NGSW |  | IRMOS MOAO Natural Guide Star Wavefront Sensor |  | Natural Guide Star Wavefront Sensor | [7 empty] | 0 | 0 | 0 | [7 empty] | Natural Guide Star Wavefront Sensor
7 | TMT.INS.INST.IRMOS.MOAO.NGSW.OPT |  |  | .OPT | IRMOS MOAO Natural Guide Star Wavefront Sensor Optics |  |  | Optics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics
7 | TMT.INS.INST.IRMOS.MOAO.NGSW.PYR |  |  | .PYR | IRMOS MOAO Natural Guide Star Wavefront Sensor Pyramid |  |  | Pyramid | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Pyramid
7 | TMT.INS.INST.IRMOS.MOAO.NGSW.DM |  |  | .DM | IRMOS MOAO Natural Guide Star Wavefront Sensor MEMS-DM |  |  | MEMS-DM | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | MEMS-DM
7 | TMT.INS.INST.IRMOS.MOAO.NGSW.DRV |  |  | .DRV | IRMOS MOAO Natural Guide Star Wavefront Sensor Drive Electronics |  |  | Drive Electronics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Drive Electronics
7 | TMT.INS.INST.IRMOS.MOAO.NGSW.CAM |  |  | .CAM | IRMOS MOAO Natural Guide Star Wavefront Sensor Camera |  |  | Camera | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Camera
6 | TMT.INS.INST.IRMOS.MOAO.SUP |  | .SUP |  | IRMOS MOAO Supervisory Controller |  | Supervisory Controller | [7 empty] | 0 | 0 | 0 | [7 empty] | Supervisory Controller
7 | TMT.INS.INST.IRMOS.MOAO.SUP.COM |  |  | .COM | IRMOS MOAO Supervisory Controller Computer |  |  | Computer | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Computer
7 | TMT.INS.INST.IRMOS.MOAO.SUP.MOTCO |  |  | .MOTCO | IRMOS MOAO Supervisory Controller Motion Controller |  |  | Motion Controller | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Motion Controller
7 | TMT.INS.INST.IRMOS.MOAO.SUP.ENVCO |  |  | .ENVCO | IRMOS MOAO Supervisory Controller Environment Controller |  |  | Environment Controller | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Environment Controller
7 | TMT.INS.INST.IRMOS.MOAO.SUP.LGSFI |  |  | .LGSFI | IRMOS MOAO Supervisory Controller LGSF Interface |  |  | LGSF Interface | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | LGSF Interface
7 | TMT.INS.INST.IRMOS.MOAO.SUP.TCSIF |  |  | .TCSIF | IRMOS MOAO Supervisory Controller TCS Interface |  |  | TCS Interface | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | TCS Interface
6 | TMT.INS.INST.IRMOS.MOAO.RTC |  | .RTC |  | IRMOS MOAO Real Time Controller |  | Real Time Controller | [7 empty] | 0 | 0 | 0 | [7 empty] | Real Time Controller
7 | TMT.INS.INST.IRMOS.MOAO.RTC.COM |  |  | .COM | IRMOS MOAO Real Time Controller Computer |  |  | Computer | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Computer
7 | TMT.INS.INST.IRMOS.MOAO.RTC.CENTR |  |  | .CENTR | IRMOS MOAO Real Time Controller Centroider |  |  | Centroider | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Centroider
7 | TMT.INS.INST.IRMOS.MOAO.RTC.TOMRE |  |  | .TOMRE | IRMOS MOAO Real Time Controller Tomographic Reconstructor |  |  | Tomographic Reconstructor | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Tomographic Reconstructor
7 | TMT.INS.INST.IRMOS.MOAO.RTC.SERVO |  |  | .SERVO | IRMOS MOAO Real Time Controller Servo |  |  | Servo | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Servo
7 | TMT.INS.INST.IRMOS.MOAO.RTC.TEL |  |  | .TEL | IRMOS MOAO Real Time Controller Telemetry System |  |  | Telemetry System | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Telemetry System
6 | TMT.INS.INST.IRMOS.MOAO.PSFM |  | .PSFM |  | IRMOS MOAO Point Spread Function Monitor |  | Point Spread Function Monitor | [7 empty] | 0 | 0 | 0 | [7 empty] | Point Spread Function Monitor
7 | TMT.INS.INST.IRMOS.MOAO.PSFM.MIR |  |  | .MIR | IRMOS MOAO Point Spread Function Monitor Mirrors |  |  | Mirrors | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirrors
7 | TMT.INS.INST.IRMOS.MOAO.PSFM.MNT |  |  | .MNT | IRMOS MOAO Point Spread Function Monitor Mirror Mounts |  |  | Mirror Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mounts
7 | TMT.INS.INST.IRMOS.MOAO.PSFM.DM |  |  | .DM | IRMOS MOAO Point Spread Function Monitor MEMS-DM |  |  | MEMS-DM | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | MEMS-DM
7 | TMT.INS.INST.IRMOS.MOAO.PSFM.DRV |  |  | .DRV | IRMOS MOAO Point Spread Function Monitor Drive Electronics |  |  | Drive Electronics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Drive Electronics
7 | TMT.INS.INST.IRMOS.MOAO.PSFM.CAM |  |  | .CAM | IRMOS MOAO Point Spread Function Monitor Camera |  |  | Camera | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Camera
7 | TMT.INS.INST.IRMOS.MOAO.PSFM.LEN |  |  | .LEN | IRMOS MOAO Point Spread Function Monitor Lenses |  |  | Lenses | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Lenses
7 | TMT.INS.INST.IRMOS.MOAO.PSFM.LMT |  |  | .LMT | IRMOS MOAO Point Spread Function Monitor Lens Mounts |  |  | Lens Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Lens Mounts
6 | TMT.INS.INST.IRMOS.MOAO.IT |  | .IT |  | IRMOS MOAO Integration and Testing |  | Integration and Testing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
5 | TMT.INS.INST.IRMOS.OSM | .OSM |  |  | IRMOS Object Selection Mechanism | Object Selection Mechanism | [5 empty] | 0 | 0 | 0 | [10 empty] | Object Selection Mechanism
6 | TMT.INS.INST.IRMOS.OSM.SE |  | .SE |  | IRMOS Object Selection Mechanism Systems Engineering |  | Systems Engineering | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
6 | TMT.INS.INST.IRMOS.OSM.STR |  | .STR |  | IRMOS Object Selection Mechanism Structure |  | Structure | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Structure
6 | TMT.INS.INST.IRMOS.OSM.TA |  | .TA |  | IRMOS Object Selection Mechanism Tile Array |  | Tile Array | [7 empty] | 0 | 0 | 0 | [7 empty] | Tile Array
7 | TMT.INS.INST.IRMOS.OSM.TA.MIR |  |  | .MIR | IRMOS Object Selection Mechanism Tile Array Macro Mirrors |  |  | Macro Mirrors | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Macro Mirrors
7 | TMT.INS.INST.IRMOS.OSM.TA.MNT |  |  | .MNT | IRMOS Object Selection Mechanism Tile Array Macro Mirror Mounts |  |  | Macro Mirror Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Macro Mirror Mounts
7 | TMT.INS.INST.IRMOS.OSM.TA.MOT |  |  | .MOT | IRMOS Object Selection Mechanism Tile Array Macro Mirror Motors |  |  | Macro Mirror Motors | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Macro Mirror Motors
7 | TMT.INS.INST.IRMOS.OSM.TA.ENC |  |  | .ENC | IRMOS Object Selection Mechanism Tile Array Macro Mirror Encoders |  |  | Macro Mirror Encoders | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Macro Mirror Encoders
7 | TMT.INS.INST.IRMOS.OSM.TA.MMIR |  |  | .MMIR | IRMOS Object Selection Mechanism Tile Array Mini Mirrors |  |  | Mini Mirrors | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mini Mirrors
7 | TMT.INS.INST.IRMOS.OSM.TA.MMNT |  |  | .MMNT | IRMOS Object Selection Mechanism Tile Array Mini Mirror Mounts |  |  | Mini Mirror Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mini Mirror Mounts
7 | TMT.INS.INST.IRMOS.OSM.TA.MMOT |  |  | .MMOT | IRMOS Object Selection Mechanism Tile Array Mini Mirror Motors |  |  | Mini Mirror Motors | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mini Mirror Motors
7 | TMT.INS.INST.IRMOS.OSM.TA.MENC |  |  | .MENC | IRMOS Object Selection Mechanism Tile Array Mini Mirror Encoders |  |  | Mini Mirror Encoders | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mini Mirror Encoders
7 | TMT.INS.INST.IRMOS.OSM.TA.FMIR |  |  | .FMIR | IRMOS Object Selection Mechanism Tile Array Faceted Micro Mirror |  |  | Faceted Micro Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Faceted Micro Mirror
6 | TMT.INS.INST.IRMOS.OSM.SM |  | .SM |  | IRMOS Object Selection Mechanism Steering Mirror |  | Steering Mirror | [7 empty] | 0 | 0 | 0 | [7 empty] | Steering Mirror
7 | TMT.INS.INST.IRMOS.OSM.SM.MIR |  |  | .MIR | IRMOS Object Selection Mechanism Steering Mirror Mirror |  |  | Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror
7 | TMT.INS.INST.IRMOS.OSM.SM.MNT |  |  | .MNT | IRMOS Object Selection Mechanism Steering Mirror Mirror Mount |  |  | Mirror Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mount
7 | TMT.INS.INST.IRMOS.OSM.SM.STG |  |  | .STG | IRMOS Object Selection Mechanism Steering Mirror Stage |  |  | Stage | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Stage
6 | TMT.INS.INST.IRMOS.OSM.PARM |  | .PARM |  | IRMOS Object Selection Mechanism Paraboloid Mirror |  | Paraboloid Mirror | [7 empty] | 0 | 0 | 0 | [7 empty] | Paraboloid Mirror
7 | TMT.INS.INST.IRMOS.OSM.PARM.MIR |  |  | .MIR | IRMOS Object Selection Mechanism Paraboloid Mirror Mirror |  |  | Mirror | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror
7 | TMT.INS.INST.IRMOS.OSM.PARM.MNT |  |  | .MNT | IRMOS Object Selection Mechanism Paraboloid Mirror Mirror Mount |  |  | Mirror Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mount
6 | TMT.INS.INST.IRMOS.OSM.IT |  | .IT |  | IRMOS Object Selection Mechanism Integration and Testing |  | Integration and Testing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
5 | TMT.INS.INST.IRMOS.SPEC | .SPEC |  |  | IRMOS Spectrograph | Spectrograph | [5 empty] | 0 | 0 | 0 | [10 empty] | Spectrograph
6 | TMT.INS.INST.IRMOS.SPEC.SE |  | .SE |  | IRMOS Spectrograph Systems Engineering |  | Systems Engineering | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
6 | TMT.INS.INST.IRMOS.SPEC.STR |  | .STR |  | IRMOS Spectrograph Structure |  | Structure | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Structure
6 | TMT.INS.INST.IRMOS.SPEC.DWR |  | .DWR |  | IRMOS Spectrograph Dewar |  | Dewar | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Dewar
6 | TMT.INS.INST.IRMOS.SPEC.OBJM |  | .OBJM |  | IRMOS Spectrograph Object Magnifier |  | Object Magnifier | [7 empty] | 0 | 0 | 0 | [7 empty] | Object Magnifier
7 | TMT.INS.INST.IRMOS.SPEC.OBJM.WHL |  |  | .WHL | IRMOS Spectrograph Object Magnifier Wheel |  |  | Wheel | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Wheel
7 | TMT.INS.INST.IRMOS.SPEC.OBJM.MIR |  |  | .MIR | IRMOS Spectrograph Object Magnifier Mirrors |  |  | Mirrors | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirrors
7 | TMT.INS.INST.IRMOS.SPEC.OBJM.MNT |  |  | .MNT | IRMOS Spectrograph Object Magnifier Mirror Mounts |  |  | Mirror Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mirror Mounts
6 | TMT.INS.INST.IRMOS.SPEC.IMSL |  | .IMSL |  | IRMOS Spectrograph Image Slicer |  | Image Slicer | [7 empty] | 0 | 0 | 0 | [7 empty] | Image Slicer
7 | TMT.INS.INST.IRMOS.SPEC.IMSL.OPT |  |  | .OPT | IRMOS Spectrograph Image Slicer Optic |  |  | Optic | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optic
7 | TMT.INS.INST.IRMOS.SPEC.IMSL.MNT |  |  | .MNT | IRMOS Spectrograph Image Slicer Optic Mount |  |  | Optic Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optic Mount
6 | TMT.INS.INST.IRMOS.SPEC.COL |  | .COL |  | IRMOS Spectrograph Collimator |  | Collimator | [7 empty] | 0 | 0 | 0 | [7 empty] | Collimator
7 | TMT.INS.INST.IRMOS.SPEC.COL.OPT |  |  | .OPT | IRMOS Spectrograph Collimator Optics |  |  | Optics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics
7 | TMT.INS.INST.IRMOS.SPEC.COL.MNT |  |  | .MNT | IRMOS Spectrograph Collimator Optics Mounts |  |  | Optics Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics Mounts
6 | TMT.INS.INST.IRMOS.SPEC.FIL |  | .FIL |  | IRMOS Spectrograph Filter Wheel |  | Filter Wheel | [7 empty] | 0 | 0 | 0 | [7 empty] | Filter Wheel
7 | TMT.INS.INST.IRMOS.SPEC.FIL.OPT |  |  | .OPT | IRMOS Spectrograph Filter Wheel Optics |  |  | Optics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics
7 | TMT.INS.INST.IRMOS.SPEC.FIL.WHL |  |  | .WHL | IRMOS Spectrograph Filter Wheel Wheel |  |  | Wheel | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Wheel
6 | TMT.INS.INST.IRMOS.SPEC.GRA |  | .GRA |  | IRMOS Spectrograph Grating |  | Grating | [7 empty] | 0 | 0 | 0 | [7 empty] | Grating
7 | TMT.INS.INST.IRMOS.SPEC.GRA.OPT |  |  | .OPT | IRMOS Spectrograph Grating Optics |  |  | Optics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics
7 | TMT.INS.INST.IRMOS.SPEC.GRA.WHL |  |  | .WHL | IRMOS Spectrograph Grating Wheel |  |  | Wheel | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Wheel
6 | TMT.INS.INST.IRMOS.SPEC.CAM |  | .CAM |  | IRMOS Spectrograph Camera |  | Camera | [7 empty] | 0 | 0 | 0 | [7 empty] | Camera
7 | TMT.INS.INST.IRMOS.SPEC.CAM.OPT |  |  | .OPT | IRMOS Spectrograph Camera Optics |  |  | Optics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics
7 | TMT.INS.INST.IRMOS.SPEC.CAM.MNT |  |  | .MNT | IRMOS Spectrograph Camera Optics Mounts |  |  | Optics Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics Mounts
6 | TMT.INS.INST.IRMOS.SPEC.DET |  | .DET |  | IRMOS Spectrograph Detector |  | Detector | [7 empty] | 0 | 0 | 0 | [7 empty] | Detector
7 | TMT.INS.INST.IRMOS.SPEC.DET.ARR |  |  | .ARR | IRMOS Spectrograph Detector Array |  |  | Array | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Array
7 | TMT.INS.INST.IRMOS.SPEC.DET.MNT |  |  | .MNT | IRMOS Spectrograph Detector Mount |  |  | Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mount
7 | TMT.INS.INST.IRMOS.SPEC.DET.CON |  |  | .CON | IRMOS Spectrograph Detector Controller |  |  | Controller | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Controller
6 | TMT.INS.INST.IRMOS.SPEC.CAL |  | .CAL |  | IRMOS Spectrograph Calibration Unit |  | Calibration Unit | [7 empty] | 0 | 0 | 0 | [7 empty] | Calibration Unit
7 | TMT.INS.INST.IRMOS.SPEC.CAL.ARC |  |  | .ARC | IRMOS Spectrograph Calibration Unit Arc Lamps |  |  | Arc Lamps | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Arc Lamps
7 | TMT.INS.INST.IRMOS.SPEC.CAL.ISP |  |  | .ISP | IRMOS Spectrograph Calibration Unit Integrating Sphere |  |  | Integrating Sphere | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Integrating Sphere
6 | TMT.INS.INST.IRMOS.SPEC.SUC |  | .SUC |  | IRMOS Spectrograph Supervisory Controller |  | Supervisory Controller | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Supervisory Controller
6 | TMT.INS.INST.IRMOS.SPEC.DH |  | .DH |  | IRMOS Spectrograph Data Handling |  | Data Handling | [7 empty] | 0 | 0 | 0 | [7 empty] | Data Handling
7 | TMT.INS.INST.IRMOS.SPEC.QLOOK |  |  | .QLOOK | IRMOS Spectrograph Quick Look |  |  | Quick Look | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Quick Look
7 | TMT.INS.INST.IRMOS.SPEC.DH.ARCHI |  |  | .ARCHI | IRMOS Spectrograph Data Handling Archive |  |  | Archive | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Archive
6 | TMT.INS.INST.IRMOS.SPEC.IT |  | .IT |  | IRMOS Spectrograph Integration and Testing |  | Integration and Testing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
5 | TMT.INS.INST.IRMOS.AMS | .AMS |  |  | IRMOS Acquisition and Metrology System | Acquisition and Metrology System | [5 empty] | 0 | 0 | 0 | [10 empty] | Acquisition and Metrology System
6 | TMT.INS.INST.IRMOS.AMS.SE |  | .SE |  | IRMOS Acquisition and Metrology System Systems Engineering |  | Systems Engineering | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
6 | TMT.INS.INST.IRMOS.AMS.BAR |  | .BAR |  | IRMOS Acquisition and Metrology System Illuminator |  | Illuminator | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Illuminator
6 | TMT.INS.INST.IRMOS.AMS.ILL |  | .ILL |  | IRMOS Acquisition and Metrology System Barrel |  | Barrel | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Barrel
6 | TMT.INS.INST.IRMOS.AMS.CAM |  | .CAM |  | IRMOS Acquisition and Metrology System Camera |  | Camera | [7 empty] | 0 | 0 | 0 | [7 empty] | Camera
7 | TMT.INS.INST.IRMOS.AMS.CAM.OPT |  |  | .OPT | IRMOS Acquisition and Metrology System Camera Optics |  |  | Optics | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics
7 | TMT.INS.INST.IRMOS.AMS.CAM.MNT |  |  | .MNT | IRMOS Acquisition and Metrology System Camera Optics Mounts |  |  | Optics Mounts | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Optics Mounts
6 | TMT.INS.INST.IRMOS.AMS.DET |  | .DET |  | IRMOS Acquisition and Metrology System Detector |  | Detector | [7 empty] | 0 | 0 | 0 | [7 empty] | Detector
7 | TMT.INS.INST.IRMOS.AMS.DET.ARR |  |  | .ARR | IRMOS Acquisition and Metrology System Detector Array |  |  | Array | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Array
7 | TMT.INS.INST.IRMOS.AMS.DET.ARR.MNT |  |  | .MNT | IRMOS Acquisition and Metrology System Detector ArrayMount |  |  | Mount | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Mount
7 | TMT.INS.INST.IRMOS.AMS.DET.ARR.MNT.CON |  |  | .CON | IRMOS Acquisition and Metrology System Detector ArrayMountController |  |  | Controller | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Controller
6 | TMT.INS.INST.IRMOS.AMS.SUC |  | .SUC |  | IRMOS Acquisition and Metrology System Supervisory Controller |  | Supervisory Controller | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Supervisory Controller
6 | TMT.INS.INST.IRMOS.AMS.IT |  | .IT |  | IRMOS Acquisition and Metrology System Integration and Testing |  | Integration and Testing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
5 | TMT.INS.INST.IRMOS.STIM | .STIM |  |  | IRMOS Stimulus | Stimulus | [5 empty] | 0 | 0 | 0 | [10 empty] | Stimulus
6 | TMT.INS.INST.IRMOS.STIM.SE |  | .SE |  | IRMOS Stimulus Systems Engineering |  | Systems Engineering | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
6 | TMT.INS.INST.IRMOS.STIM.ENCL |  | .ENCL |  | IRMOS Stimulus Enclosure |  | Enclosure | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Enclosure
6 | TMT.INS.INST.IRMOS.STIM.LGSS |  | .LGSS |  | IRMOS Stimulus LGS Simulator |  | LGS Simulator | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | LGS Simulator
6 | TMT.INS.INST.IRMOS.STIM.NGSS |  | .NGSS |  | IRMOS Stimulus NGS Simulator |  | NGS Simulator | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | NGS Simulator
6 | TMT.INS.INST.IRMOS.STIM.TURB |  | .TURB |  | IRMOS Stimulus Turbulence Generator |  | Turbulence Generator | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Turbulence Generator
6 | TMT.INS.INST.IRMOS.STIM.SLD |  | .SLD |  | IRMOS Stimulus Slide |  | Slide | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Slide
6 | TMT.INS.INST.IRMOS.STIM.IT |  | .IT |  | IRMOS Stimulus Integration and Testing |  | Integration and Testing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
5 | TMT.INS.INST.IRMOS.IROT | .IROT |  |  | IRMOS Instrument Rotator | Instrument Rotator | [5 empty] | 0 | 0 | 0 | [10 empty] | Instrument Rotator
6 | TMT.INS.INST.IRMOS.IROT.SE |  | .SE |  | IRMOS Instrument Rotator Systems Engineering |  | Systems Engineering | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Systems Engineering
6 | TMT.INS.INST.IRMOS.IROT.ROT |  | .ROT |  | IRMOS Instrument Rotator Rotation Stage |  | Rotation Stage | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Rotation Stage
6 | TMT.INS.INST.IRMOS.IROT.NASI |  | .NASI |  | IRMOS Instrument Rotator Nasmyth Platform Interface |  | Nasmyth Platform Interface | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Nasmyth Platform Interface
6 | TMT.INS.INST.IRMOS.IROT.SUC |  | .SUC |  | IRMOS Instrument Rotator Supervisory Controller |  | Supervisory Controller | [7 empty] | 0 | 0 | 0 | [7 empty] | Supervisory Controller
7 | TMT.INS.INST.IRMOS.IROT.SUC.COM |  |  | .COM | IRMOS Instrument Rotator Supervisory Controller Computer |  |  | Computer | [9 empty] | 0 | 0 | 0 | 0 | 0 | Purchase |  | Computer
7 | TMT.INS.INST.IRMOS.IROT.SUC.MOTCO |  |  | .MOTCO | IRMOS Instrument Rotator Supervisory Controller Motion Controller |  |  | Motion Controller | [9 empty] | 0 | 0 | 0 | 0 | 0 | Labor |  | Motion Controller
6 | TMT.INS.INST.IRMOS.IROT.IT |  | .IT |  | IRMOS Instrument Rotator Integration and Testing |  | Integration and Testing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Integration and Testing
5 | TMT.INS.INST.IRMOS.IT | .IT |  |  | IRMOS System Integration and Testing | System Integration and Testing | [5 empty] | 0 | 0 | 0 | [10 empty] | System Integration and Testing
6 | TMT.INS.INST.IRMOS.IT.LAB |  | .LAB |  | IRMOS System Integration and Testing Labor |  | Labor | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Labor
6 | TMT.INS.INST.IRMOS.IT.M6TO |  | .M6TO |  | IRMOS System Integration and Testing M6 Test Optics |  | M6 Test Optics | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | M6 Test Optics
6 | TMT.INS.INST.IRMOS.IT.SCR |  | .SCR |  | IRMOS System Integration and Testing OSM Calibration Screen |  | OSM Calibration Screen | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | OSM Calibration Screen
5 | TMT.INS.INST.IRMOS.COMM | .COMM |  |  | IRMOS Commissioning | Commissioning | [5 empty] | 0 | 0 | 0 | [10 empty] | Commissioning
6 | TMT.INS.INST.IRMOS.COMM.LAB |  | .LAB |  | IRMOS Commissioning Labor |  | Labor | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Labor |  | Labor
6 | TMT.INS.INST.IRMOS.COMM.FRE |  | .FRE |  | IRMOS Commissioning Freight |  | Freight | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Freight
6 | TMT.INS.INST.IRMOS.COMM.INS |  | .INS |  | IRMOS Commissioning Insurance |  | Insurance | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Purchase |  | Insurance
[18 empty] | Cross-check |  | 0 | 0 | 0 |  | Total Labor
[20 empty] | 0 | 0 | 0 |  | Total Purchase
[6 empty] | PBS | [13 empty] | 0 | 0 | 0
[6 empty] | Offner Relay | [11 empty] | Total Labor |  | 0 | 0 | 0 |  | Wk-Yrs
MOAO
Object Selection Mechanism
Spectrograph
Acquisition and Metrology System
Stimulus
Instrument Rotator
WBS
| Number | Title |  |  | Title
| TMT.INS.INST.IRMOS | IRMOS |  |  | IRMOS
| TMT.INS.INST.IRMOS.MAN | IRMOS Management |  |  | IRMOS Management
| TMT.INS.INST.IRMOS.SYS | IRMOS Systems Engineering |  |  | IRMOS Systems Engineering
| TMT.INS.INST.IRMOS.RLAY | IRMOS Offner Relay |  |  | IRMOS Offner Relay
| TMT.INS.INST.IRMOS.MOAO | IRMOS MOAO |  |  | IRMOS MOAO
| TMT.INS.INST.IRMOS.OSM | IRMOS Object Selection Mechanism |  |  | IRMOS Object Selection Mechanism
| TMT.INS.INST.IRMOS.SPEC | IRMOS Spectrograph |  |  | IRMOS Spectrograph
| TMT.INS.INST.IRMOS.AMS | IRMOS Acquisition and Metrology System |  |  | IRMOS Acquisition and Metrology System
| TMT.INS.INST.IRMOS.STIM | IRMOS Stimulus |  |  | IRMOS Stimulus
| TMT.INS.INST.IRMOS.IROT | IRMOS Instrument Rotator |  |  | IRMOS Instrument Rotator
| TMT.INS.INST.IRMOS.IT | IRMOS System Integration and Testing |  |  | IRMOS System Integration and Testing
| TMT.INS.INST.IRMOS.COMM | IRMOS Commissioning |  |  | IRMOS Commissioning
WBS
| Number | Title
| TMT.INS.INST.IRMOS | IRMOS
| TMT.INS.INST.IRMOS.MAN | IRMOS Management
| TMT.INS.INST.IRMOS.MAN.SEN | IRMOS Management Senior
| TMT.INS.INST.IRMOS.MAN.BUS | IRMOS Management Business Office
| TMT.INS.INST.IRMOS.MAN.SEC | IRMOS Management Sectretarial
| TMT.INS.INST.IRMOS.SYS | IRMOS Systems Engineering
| TMT.INS.INST.IRMOS.SYS.LAB | IRMOS Systems Engineering Labor
| TMT.INS.INST.IRMOS.RLAY | IRMOS Offner Relay
| TMT.INS.INST.IRMOS.RLAY.SYS | IRMOS Offner Relay Systems Engineering
| TMT.INS.INST.IRMOS.RLAY.ENCL | IRMOS Offner Relay Enclosure
| TMT.INS.INST.IRMOS.RLAY.STR | IRMOS Offner Relay Structure
| TMT.INS.INST.IRMOS.RLAY.WIN | IRMOS Offner Relay Entrance Window
| TMT.INS.INST.IRMOS.RLAY.M4 | IRMOS Offner Relay M4 Fold Mirror
| TMT.INS.INST.IRMOS.RLAY.M5/7 | IRMOS Offner Relay M5/7 Sphere
| TMT.INS.INST.IRMOS.RLAY.DIC | IRMOS Offner Relay Dichroic
| TMT.INS.INST.IRMOS.RLAY.IT | IRMOS Offner Relay Integration and Testing
| TMT.INS.INST.IRMOS.MOAO | IRMOS MOAO
| TMT.INS.INST.IRMOS.MOAO.SYS | IRMOS MOAO Systems Engineering
| TMT.INS.INST.IRMOS.MOAO.M6DM | IRMOS MOAO M6 Deformable Mirror
| TMT.INS.INST.IRMOS.MOAO.M6TT | IRMOS MOAO M6 Tip/Tilt Stage
| TMT.INS.INST.IRMOS.RLAY.M6ME | IRMOS MOAO M6 Real Time Metrology
| TMT.INS.INST.IRMOS.RLAY.M6ME.SYS | IRMOS MOAO M6 Real Time Metrology Systems Engineering
| TMT.INS.INST.IRMOS.MOAO.M11 | IRMOS MOAO M11 (MEMS-DM)
| TMT.INS.INST.IRMOS.MOAO.M11T | IRMOS MOAO M11 Tip/Tilt Stage
| TMT.INS.INST.IRMOS.MOAO.LGSW | IRMOS MOAO Laser Guide Star Wavefront Sensor
| TMT.INS.INST.IRMOS.MOAO.NGSW | IRMOS MOAO Natural Guide Star Wavefront Sensor
| TMT.INS.INST.IRMOS.MOAO.SUP | IRMOS MOAO Supervisory Controller
| TMT.INS.INST.IRMOS.MOAO.RTC | IRMOS MOAO Real Time Controller
| TMT.INS.INST.IRMOS.MOAO.PSFM | IRMOS MOAO Point Spread Function Monitor
| TMT.INS.INST.IRMOS.MOAO.IT | IRMOS MOAO Integration and Testing
| TMT.INS.INST.IRMOS.OSM | IRMOS Object Selection Mechanism
| TMT.INS.INST.IRMOS.OSM.SE | IRMOS Object Selection Mechanism Systems Engineering
| TMT.INS.INST.IRMOS.OSM.STR | IRMOS Object Selection Mechanism Structure
| TMT.INS.INST.IRMOS.OSM.TA | IRMOS Object Selection Mechanism Tile Array
| TMT.INS.INST.IRMOS.OSM.SM | IRMOS Object Selection Mechanism Steering Mirror
| TMT.INS.INST.IRMOS.OSM.PARM | IRMOS Object Selection Mechanism Paraboloid Mirror
| TMT.INS.INST.IRMOS.OSM.IT | IRMOS Object Selection Mechanism Integration and Testing
| TMT.INS.INST.IRMOS.SPEC | IRMOS Spectrograph
| TMT.INS.INST.IRMOS.SPEC.SE | IRMOS Spectrograph Systems Engineering
| TMT.INS.INST.IRMOS.SPEC.STR | IRMOS Spectrograph Structure
| TMT.INS.INST.IRMOS.SPEC.DWR | IRMOS Spectrograph Dewar
| TMT.INS.INST.IRMOS.SPEC.OBJM | IRMOS Spectrograph Object Magnifier
| TMT.INS.INST.IRMOS.SPEC.IMSL | IRMOS Spectrograph Image Slicer
| TMT.INS.INST.IRMOS.SPEC.COL | IRMOS Spectrograph Collimator
| TMT.INS.INST.IRMOS.SPEC.FIL | IRMOS Spectrograph Filter Wheel
| TMT.INS.INST.IRMOS.SPEC.GRA | IRMOS Spectrograph Grating
| TMT.INS.INST.IRMOS.SPEC.CAM | IRMOS Spectrograph Camera
| TMT.INS.INST.IRMOS.SPEC.DET | IRMOS Spectrograph Detector
| TMT.INS.INST.IRMOS.SPEC.CAL | IRMOS Spectrograph Calibration Unit
| TMT.INS.INST.IRMOS.SPEC.SUC | IRMOS Spectrograph Supervisory Controller
| TMT.INS.INST.IRMOS.SPEC.DH | IRMOS Spectrograph Data Handling
| TMT.INS.INST.IRMOS.SPEC.IT | IRMOS Spectrograph Integration and Testing
| TMT.INS.INST.IRMOS.AMS | IRMOS Acquisition and Metrology System
| TMT.INS.INST.IRMOS.AMS.SE | IRMOS Acquisition and Metrology System Systems Engineering
| TMT.INS.INST.IRMOS.AMS.BAR | IRMOS Acquisition and Metrology System Illuminator
| TMT.INS.INST.IRMOS.AMS.ILL | IRMOS Acquisition and Metrology System Barrel
| TMT.INS.INST.IRMOS.AMS.CAM | IRMOS Acquisition and Metrology System Camera
| TMT.INS.INST.IRMOS.AMS.DET | IRMOS Acquisition and Metrology System Detector
| TMT.INS.INST.IRMOS.AMS.SUC | IRMOS Acquisition and Metrology System Supervisory Controller
| TMT.INS.INST.IRMOS.AMS.IT | IRMOS Acquisition and Metrology System Integration and Testing
| TMT.INS.INST.IRMOS.STIM | IRMOS Stimulus
| TMT.INS.INST.IRMOS.STIM.SE | IRMOS Stimulus Systems Engineering
| TMT.INS.INST.IRMOS.STIM.ENCL | IRMOS Stimulus Enclosure
| TMT.INS.INST.IRMOS.STIM.LGSS | IRMOS Stimulus LGS Simulator
| TMT.INS.INST.IRMOS.STIM.NGSS | IRMOS Stimulus NGS Simulator
| TMT.INS.INST.IRMOS.STIM.TURB | IRMOS Stimulus Turbulence Generator
| TMT.INS.INST.IRMOS.STIM.SLD | IRMOS Stimulus Slide
| TMT.INS.INST.IRMOS.STIM.IT | IRMOS Stimulus Integration and Testing
| TMT.INS.INST.IRMOS.IROT | IRMOS Instrument Rotator
| TMT.INS.INST.IRMOS.IROT.SE | IRMOS Instrument Rotator Systems Engineering
| TMT.INS.INST.IRMOS.IROT.ROT | IRMOS Instrument Rotator Rotation Stage
| TMT.INS.INST.IRMOS.IROT.NASI | IRMOS Instrument Rotator Nasmyth Platform Interface
| TMT.INS.INST.IRMOS.IROT.SUC | IRMOS Instrument Rotator Supervisory Controller
| TMT.INS.INST.IRMOS.IROT.IT | IRMOS Instrument Rotator Integration and Testing
| TMT.INS.INST.IRMOS.IT | IRMOS System Integration and Testing
| TMT.INS.INST.IRMOS.IT.LAB | IRMOS System Integration and Testing Labor
| TMT.INS.INST.IRMOS.IT.M6TO | IRMOS System Integration and Testing M6 Test Optics
| TMT.INS.INST.IRMOS.IT.SCR | IRMOS System Integration and Testing OSM Calibration Screen
| TMT.INS.INST.IRMOS.COMM | IRMOS Commissioning
| TMT.INS.INST.IRMOS.COMM.LAB | IRMOS Commissioning Labor
| TMT.INS.INST.IRMOS.COMM.FRE | IRMOS Commissioning Freight
| TMT.INS.INST.IRMOS.COMM.INS | IRMOS Commissioning Insurance
Note on C272: Richard Dekany: The 16 spectrographs are mounted to a superstructure costed in the OSM structure section
Note on F126: Richard Dekany: The 16 spectrographs are mounted to a superstructure costed in the OSM structure section
Note on H34: Richard Dekany: Assume tip/tilt of M4 to compensate pupil nutation (from M3) is not necessary