## Template
data base field names | Who nominated or originated requirement | Section | Category | Sub Category | WBS | Short Name | Description | Rationale | Traceability | Status | Verification method | Version | Created | Modified | Comments
data type | String | Selection (string) | Selection (string) | Selection (string) | Selection (string) | string | text | text | text | selection | selection | string | date | date | text
comments |  | Assign to Sean's requirements document sections: should make it easier to draft requirements documents from database (See Adkins, "Draft Engineering Guideline For the Preparation of Requirements Documents" version 1.1, September 2006) |  |  | What part of the system is the requirement assigned to (by WBS) |  | Text of the requirement | Why requirement is needed, plus technical reference, KAONS, other requirements documents, etc. | What requirements this one is derived from: should be a reference to other data bases or design document |  | How the requirement is tested | What version | Date Created | history of modification | Any comments or problems
|  | pick one from list: | pick one from list: | pick one from list: | pick one from list: |  |  |  |  | pick one from list: | pick one from list:
| Chris Neyman | Overall | Implementation Requirements | Feature | 3.2.3.10 Atmospheric Profiler | PSF camera | The main NGAO optical relay will include an interface to a camera for recording images of natural sources that have been corrected by the AO system. This camera will provide point spread function for calibration of scientific data for systematic errors in the NGAO performance, Strehl variations, and angular anisoplanatism, etc. | Design decision based on current AO practice. | "Cascaded Relay Requirement Flowdown and Open Issues", R. Dekany NGAO Team Meeting #9 and KAON 499 "NGAO System Architecture Definition | draft | inspection | 0.4 | 2007-09-20 | 2007-11-02
[6 empty] | Accuracy | The PSF camera will be able to measure point spread functions to an overall accuracy of 0l02 magnitudes
[6 empty] | Wavelength | The PSF camera will observe over 1.0 -2.5 microns, approximately the astronomical J,H,K bands
[6 empty] | Spatial Sampling | The spatial sampling will be 13 milli arc seconds per detector array pixle, this is Nyquist sampling at the center of the astronomical J band (1.25 microns)
Sensativity
[6 empty] | Field of view | The PSF camera will produce an image of the PSF star over a field of view of at least 3 arc seconds by 3 arcseconds
[6 empty] | Field of regard | The PSF camera imager will be deployable about the field of view pass by the first stage optical relay
[6 empty] | Thermal Background (cooling) | The PF camera will be cooled to allow operation in the astronomical K band
[6 empty] | Transmission | The transmission of the PSF camera optics will be
[6 empty] | Array Electrical Properties | The dark curren, read noise, quantum effieciny are TBD
[6 empty] | Static wavefront error | The static wavefront error of the PSF camera will be
[6 empty] | MOAO correction | The PSF camera will have its own MEMS mirror for MOAO correction of the PSF star image
[6 empty] | Array controller | The PSF camer will have an array controller
[6 empty] | Software | The PSF camera willl be controlled by a dedicated software server
| Chris Neyman | Overall | Implementation Requirements | Feature | 3.2.3.10 Atmospheric Profiler | Interface to data archive | PSF monitoring camera interface to observatory data archive: The PSF camera will be controlled by the AO non real-time control software. PSF images will be relayed to the observatory data archive for use in AO PSF estimation and calibration of scientific data | Design decision based on current AO practice. | "Cascaded Relay Requirement Flowdown and Open Issues", R. Dekany NGAO Team Meeting #9 and KAON 499 "NGAO System Architecture Definition | draft | inspection | 0.4 | 2007-09-21 | 2007-11-03

## AdkinsTaxonomy
See Adkins, "Draft Engineering Guideline For the Preparation of Requirements Documents" version 1.1, September 2006
Adkins requirements taxonomy
Document Sections (roughly by engineering discipline) | Categories | Sub Categories
Performance Requirements
Overall |  | Parametric Performance Requirements
Optical |  | Operational Performance Requirements
Mechanical | Implementation Requirements
Electronic/Electrical |  | Feature Implementation Requirements
Safety |  | Common Practices Implementation Requirements
Software |  | Standards Implementation Requirements
Interface |  | Regulatory Implementation Requirements
Reliability | Design requirements
Spares |  | Technological Design Requirements
Service and Maintenance |  | Regulatory Design Requirements
Documentation |  | Standards Related Design Requirements
Integration Related Design Requirements

## RequirementsOutline
| Outline of requirements document | See Adkins, "Draft Engineering Guideline For the Preparation of Requirements Documents" version 1.1, September 2006
1 | Introduction
2 | Scope and Applicability
3 | Related Documents
4 | Revision History
5 | Background
6 | Overall System Requirements
Performance Requirements
Implementation Requirements
Design Requirements
7 | Optical Requirements
Performance Requirements
Implementation Requirements
Design Requirements
8 | Mechanical Requirements
Performance Requirements
Implementation Requirements
Design Requirements
9 | Electronic/Electrical Requirements
Performance Requirements
Implementation Requirements
Design Requirements
10 | Safety Requirements
Performance Requirements
Implementation Requirements
Design Requirements
11 | Software Requirements
12 | Interface Requirements
Performance Requirements
Implementation Requirements
Design Requirements
13 | Reliability Requirements
14 | Spares Requirements
15 | Service and Maintenance Requirements
16 | Documentation Requirements
Glossary

## DataBaseFields (hidden)
[6 empty] | WBS | WBS (Sys. Design Plan)
data base field names | ID # | Who nominated or originated requirement | Section | Category | Sub Category |  | L.1 | L.2 | L.3 | L.4 | Description | Rationale | Traceability | Status | Verification method | Version | Created | Modified
data type |  | String | Selection (string) | Selection (string) | Selection (string) | Selection (string) | int | int | int | int | text | text | text | selection | selection | string | date | date
comments | Just a unique number in the database |  | Assign to Sean's requirements document sections: should make it easier to draft requirements documents from database (see taxonomy, outline) |  |  | What part of the system is the requirement assigned to (by WBS) | What part of the system is the requirement assigned to (by WBS) |  |  |  | Text of the requirement | Why requirement is needed, plus technical reference, KAONS, other requirements documents, etc. | What requirements this one is derived from: should be a reference to other data bases or design document |  | How the requirement is tested | What version | Date Created | history of modification
Selections |  |  | pick one: | pick one: | pick one: | pick one: | [7 empty] | pick one: | pick one:
|  |  | Overall | Performance Requirements | if performance: | [8 empty] | draft | inspection
|  |  | Optical |  | Parametric | [8 empty] | final | analysis
|  |  | Mechanical |  | Operational | [8 empty] | approved | demonstration
|  |  | Electronic/Electrical | Implementation Requirements | if implementation: | [8 empty] | pending approval | test
|  |  | Safety |  | Feature | [8 empty] | disapprove
|  |  | Software |  | Common Practices
|  |  | Interface |  | Standards
|  |  | Reliability |  | Regulatory
|  |  | Spares | Design requirements | if design:
|  |  | Service and Maintenance |  | Technological
|  |  | Documentation |  | Regulatory
Standards
Integration

## pickfields (hidden)
[6 empty] | WBS | WBS (Sys. Design Plan)
data base field names | ID # | Who nominated or originated requirement | Section | Category | Sub Category |  | L.1 | L.2 | L.3 | L.4 | Status | Verification method
data type |  | String | Selection (string) | Selection (string) | Selection (string) | Selection | int | int | int | int | selection | selection
comments | Just a unique number in the database |  | Assign to Sean's requirements document sections: should make it easier to draft requirements documents from database (see taxonomy, outline) |  |  |  | What part of the system is the requirement assigned to (by WBS) |  |  |  |  | How the requirement is tested
Selections |  |  | pick one: | pick one: | pick one: | pick one |  |  |  |  | pick one: | pick one:
|  |  | Overall | Performance Requirements | if performance: | 3.2 AO System |  |  |  |  | draft | inspection
|  |  | Optical | Implementation Requirements | Parametric | 3.2.1 AO System Architecture |  |  |  |  | final | analysis
|  |  | Mechanical | Design requirements | Operational | 3.2.2 AO Enclosure |  |  |  |  | approved | demonstration
|  |  | Electronic/Electrical |  | if implementation: | 3.2.3 Opto-mechanical |  |  |  |  | pending approval | test
|  |  | Safety |  | Feature | 3.2.3.1 Field Rotation |  |  |  |  | disapprove
|  |  | Software |  | Common Practices | 3.2.3.2 Optical Relay
|  |  | Interface |  | Standards | 3.2.3.3 Optical Switchyard
|  |  | Reliability |  | Regulatory | 3.2.3.4 Optical Support Structure
|  |  | Spares |  | if design: | 3.2.3.5 Wavefront Sensors
|  |  | Service and Maintenance |  | Technological | 3.2.3.5.1 High Order LGS Wavefront Sensors
|  |  | Documentation |  | Regulatory | 3.2.3.5.2 High Order NGS Wavefront Sensor
[5 empty] | Standards | 3.2.3.5.3 Low Order NGS Wavefront Sensors
[5 empty] | Integration | 3.2.3.5.4 Calibration Wavefront Sensor
3.2.3.6 Wavefront Correctors
3.2.3.6.1 Tip/Tilt Corrector
3.2.3.6.2 Deformable Mirror
3.2.3.6.3 Tip/tilt Vibration Mitigation
3.2.3.7 Acquisition Cameras
3.2.3.7.1 NGS Acquisition Camera
3.2.3.7.2 LGS Acquisition Camera
3.2.3.8 Atmospheric Dispersion Correction
3.2.3.9 Alignment, Calibration, Diagnostics, Metrology and Monitoring
3.2.3.10 Atmospheric Profiler
3.2.3.11 d-IFU & LOWFS AO & Object Selection
3.2.3.12 PSF Monitoring Camera
3.2.4 Non-real-time Control
3.2.4.1 Non-RTC Software
3.2.4.2 Non-RTC Electronics
3.2.5 Real-time Control
3.2.5.1 RTC Architecture Analysis and Design Study
3.2.5.2 RTC Software Module Definition
3.2.5.3 RTC Hardware Module Definition
3.3 Laser Facility
3.3.1 Laser System Architecture
3.3.2 Laser Enclosure
3.3.3 Laser
3.3.4 Laser Launch Facility
3.3.4.1 Laser Beam Transport
3.3.4.2 Laser Pointing & Diagnostics
3.3.4.3 Laser Launch Telescope
3.3.5 Laser Safety Systems
3.3.5.1 Personnel and Equipment Safety Systems
3.3.5.2 Aircraft, Satellite & Laser Traffic Control Safety Systems
3.3.6 Laser System Control
3.3.6.1 Laser System Software
3.3.6.2 Laser System Electronics