## Instructions
NGAO Estimating Template (revised January 25, 2008)
INSTRUCTIONS
1. Use one sheet for each WBS/Subphase combination.
2. Each labor line item must be estimated in discrete hours. For activities where Full Time Equivalent rates are more appropriate, convert to total work-hours based on the expected duration of each phase (one work-month = 1800 / 12 = 150 productive work-hours)
3. If you need more lines to add line items, use the "+" box to add more lines. If you need more room for BOE or Dictionary entries, do NOT add additional cells or rows, just increase the height of the row.
4. If you have any additional questions or comments, please contact Richard Dekany (rgd at astro.caltech.edu).

## 6.1 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Observing Setup
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.1 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Observing Setup
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.1 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Observing Setup
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.1 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Observing Setup
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.2 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Interfaces
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.2 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Interfaces
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.2 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Interfaces
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.2 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Interfaces
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.3 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Astronomer Planning
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.3 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Astronomer Planning
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.3 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Astronomer Planning
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.3 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Astronomer Planning
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.5 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Performance Monitoring
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.5 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Performance Monitoring
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.5 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Performance Monitoring
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.5 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Performance Monitoring
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.6 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.6 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Automation and Optimization
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.6 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.6 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Automation and Optimization
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.6 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.6 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Automation and Optimization
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.6 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.6 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Automation and Optimization
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.7 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.7 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Documentation
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.7 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.7 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Documentation
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.7 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.7 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Documentation
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 6.7 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 6.7 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | User Documentation
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.3 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | LGS AO System On-sky I&T
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.3 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | LGS AO System On-sky I&T
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.3 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | LGS AO System On-sky I&T
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.3 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.3 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | LGS AO System On-sky I&T
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.5 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Science Verification
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.5 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Science Verification
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.5 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Science Verification
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 8.5 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 8.5 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Science Verification
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.1 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Personnel Training
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.1 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Personnel Training
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.1 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Personnel Training
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.1 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.1 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Personnel Training
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.2 PD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Acceptance
|  |  | Phase*: | PD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.2 DD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Acceptance
|  |  | Phase*: | DD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.2 FSD
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Acceptance
|  |  | Phase*: | FSD | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## 9.2 DC
NGAO Cost Estimating Worksheet
|  |  | WBS*: | 9.2 |  |  |  | Estimate Date: |  | Links:
|  |  | WBS Title*: | Operations Acceptance
|  |  | Phase*: | DC | [5 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | David le Mignant | [5 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+

## Template
NGAO Cost Estimating Worksheet
|  |  | WBS*: |  |  |  |  | Estimate Date: |  | Links:
WBS Title*:
|  |  | Phase*: | [6 empty] | Cost Estimating Plan
|  |  | Responsible Estimator*: | [6 empty] | Input Cheat Sheet
Estimators*:
* - Required Fields
Element Scope / WBS Dictionary Entry*:
Deliverables*:
Labor
BOE*:
|  | Resource | Estimate Type | Hours
1
2
Non-Labor
BOE*:
|  | Expense Item |  | Description |  | Category | Estimate Type | Unit Cost | Number of units
1
2
Travel
BOE*:
|  | Trip Type | Duration | Number of Trips
1
2
Risk Factors
|  |  | Factor | % | Basis*:
Technical*:
Cost*:
Schedule*:
|  | TOTAL: | 0%
Override:
Misc Comments:
Scoping Options:
Note on B9: Element Scope: Provide a description of what this WBS item/phase IS and IS NOT. To paste text into this box, double-click in the cell and paste.
Note on B13: Deliverables: Summarize all key deliverables of this WBS item/phase. To paste text into this box, double-click in the cell and paste.
Note on B57: Comments: Add any comments, assumptions, or concerns. To paste text into this box, double-click in the cell and paste.
Note on B61: Scoping Options: Ideas for reducing cost through scoping alternatives or other methods. To paste text into this box, double-click in the cell and paste.
Note on C18: Labor Basis: Provide a thorough description and all details relevant to the Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C21: Resource: Enter the code that indicates the labor resource for which you are providing an estimate. Input Code - Resource PostDoc - Post Doc Tech - Technician JunSci - Junior Scientist / Engineer AssoSci - Associate Scientist / Engineer IT - Information Tech. Specialist SrSci - Senior Scientist / Engineer LdSci - Lead Scientist / Engineer AsstAdmin - Administrative I AssoAdmin - Administative II SubMgr - Subsystem Manager ProjMgr - Project Manager
Note on C27: Non-Labor Basis: Provide a thorough description and all details relevant to the Non-Labor estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C30: Expense Item: Enter an appropriate name that best identifies the particular subcontract, material, or item estimated. Due to database field size restrictions, please limit this entry to eight (8) characters or less.
Note on C36: Travel Basis: Provide a thorough description and all details relevant to the Travel estimate. Electronic references, links, and hyperlinks are preferred to provide for dynamic updating should the underlying assumptions change. To paste text into this box, double-click in the cell and paste.
Note on C39: Trip: Enter the code that indicates the Trip type for which you are providing an estimate. CALIF - Intra California HAWAII - Between Hawaii and California INTER - International OTHER - Other locations not included above
Note on C46: Risk Technical Enter the appropriate number from the following options: Factor: 1 - Existing design and off-the-shelf hardware 2 - Minor modifications to an existing design 3 - Extensive modifications to an existing design 4 - New design within established product line 6 - New design different from established product line. Existing technology. 8 - New design. Requires some R&D development but does not advance the state-of-the-art. 10 - New design. New development of new technology which advances the state-of-the-art. 15 - New design way beyond the current state-of-the-art. Multiplier: 2% - Design or manufacturing concerns only 4% - Design and manufacturing concerns
Note on C48: Risk Cost Enter the appropriate number from the following options: Factor: 1 - Off-the-shelf or catalog item 2 - Vendor quote from established drawings 3 - Vendor quote with some design sketches 4 - In-house estimate for item within current production line 6 - In-house estimate for item with minimal company experience but related to existing capabilities 8 - In-house estimate for item with minimal company experience and minimal in-house capability 10 - Top down estimate from analogous programs 15 - Engineering judgment Multiplier: 1% - Material cost or labor rate concern 2% - Material and labor rate concern
Note on C50: Risk Schedule Enter the appropriate number from the following options: 2 - No schedule impact on any other item 4 - Delays completion of non-critical path subsystem item 8 - Delays completion of critical path subsystem item
Note on C54: Risk Override If the Contingency value determined using the above process does not seem appropriate, an override value may be utilized. Enter the value that you feel is more appropriate and provide a rationale for the use of this particular value instead of the product of the risk matrix.
Note on D3: WBS Enter the WBS number for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D4: WBS Enter the WBS Title for the item estimated. This list is maintained as part of the NGAO WBS, which is posted on the NGAO TWiki
Note on D5: Phase: Indicate the particular phase for which this estimate supports for the WBS element. PD - Preliminary Design DD - Detailed Design FSD - Full Scale Development DC - Delivery and Commissioning
Note on D6: Estimator: The name of the person responsible for managing the completion of the estimate.
Note on D7: Estimator: The name of all people who contributed to the creation of the estimate.
Note on D21: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CER - Cost Estimating Relationship EE - Engineering Estimate
Note on D39: Duration: Enter the code that indicates the Duration type for which you are providing an estimate. EXT - More than 3 weeks LONG - 1 - 3 weeks MID - 3 - 7 days SHORT - Less than 3 days
Note on E21: Hours: The number of hours required during the indicated time frame. If this activity is is considered LOE, do not include a discrete estimate of hours and instead estimate the resource requirements using FTE.
Note on E30: Description: Enter a brief description or title that can be used to identify the item estimated in a moderately clear fashion for program reporting purposes.
Note on E39: Number of Trips: Enter the number of trips of this particular type and duration that will be necessary to directly support this activity. Do not estimate the number of trips if this activity is based on a cyclical pattern tied to schedule.
Note on F45: Basis: To paste text into this box, double-click in the cell and paste.
Note on H30: Category: Enter the code that indicates the Non-Labor Category for which you are providing an estimate. EQP - Equipment MAT - Material SUB - Subcontract SHIP - Shipping ODC - Other Direct CoQP
Note on I30: Estimate Type: Enter the appropriate code that indicates the methodology used to determine the estimate: DH - Direct Historical Data CP - Catalog Price VQ - Vendor Quote CER - Cost Estimating Relationship EE - Engineering Estimate
Note on J3: Date: Indicate the date this revision of the estimate was developed or last updated.
Note on J30: Unit Cost: Provide the unit cost for the Expense Item and Number of Units estimated. For multiple items that may realize long-term cost savings due to learning curve or other phenomena, please contact NGAO Management for the most efficient way to express the cost estimate.
Note on K30: Number of Units: Enter the number of units of this Expense Item that will be utilized or purchased. Include all production units, spares, and consummable items for which the program will incur cost. Use this only if the estimate is not considered to be cyclical and tied to a relationship with the schedule.
+
+
+