## LGS-AO Acquisition
| NGAO Flowdown Budget: |  |  |  |  | #VALUE!
Version 0.2 - 5/19/09
| Units |  |  | Seconds
| Available Allocation |  |  | 180 |  |  |  | Requirement: 120s from end of slew to first science exposure
| Remainder |  |  | 10
Step | Flowdown Tree |  |  | Value |  |  |  | Rationale
Current Estimate 170
1 | Terminate AO correction |  |  | 0 |  |  | Terminate AO correction 0 | Open loops and shutter laser
2 | Slew to pointing star |  |  | 60 |  |  |  | TBC; need median value vs. science case
| Check pointing |  |  | 18
3 |  | Integration |  |  | 5 |  |  | Must reach R=12.0 with SNR>20 for easy automated analysis
4 |  | Readout |  |  | 1
5 |  | Analysis |  |  | 2
6 |  | Operator verify |  |  | 5
7 |  | Correct pointing |  |  | 5
8 | Slew to science target |  |  | 10
| Project laser |  |  | 12 |  |  |  | laser should be tuned off 589nm line
9 |  | Spotter confirmation |  |  | 10 |  | Spotter confirmation 10
10 |  | Open laser shutter |  |  | 2 |  | Open laser shutter 2
| Acquire LGS |  |  | 22 |  |  | Acquire LGS 22
11 |  | Record LGS WFS background |  |  | 10
12 |  | Tune laser to 589nm |  |  | 5 |  |  | Not certain how realistic this estimate is.
13 |  | Close LGS TT loops |  |  | 2 |  | Close LGS TT loops 2
14 |  | Offset PnS LGS pickoffs |  |  | 5 |  | Offset PnS LGS pickoffs 5 | If necessary, offset pickoffs <3" to center TT stages
| Acquire NGS |  |  | 34 |  |  | Acquire NGS 34
15 |  | Close DM loops |  |  | 2
16 |  | Record full-frame TTS/TTFA image |  |  | 2 |  |  | ~1s integration, full-frame
17 |  | Offset TT/TTFA sensor arms |  |  | 10 |  |  | Offset arms to center stars in FOV (automated, <2")
18 |  | Select region of interest |  |  | 2 |  |  | ~1s integration, full-frame
19 |  | Offset telescope to sky |  |  | 3
20 |  | Record TT/TTFA background |  |  | 10
21 |  | Offset back to target |  |  | 3
22 |  | Close NGS TTS loops |  |  | 2
| Close TT and NGS focus loops |  |  | 12
23 |  | Close Science TT & focus loops |  |  | 2
24 |  | Wait for focus to converge |  |  | 10 |  |  | Depends on
25 | Close TWFS loop |  |  | 2
| Current Estimate |  |  | 170
Step | Parallel Activities |  | Budget | Value |  | Remainder
26 | Install ACAM fold mirror |  | 60 | 10 |  | 50 |  | Parallel to step 2
27 | Configure PnS laser asterism |  | 88 | 60 |  | 28 |  | Parallel to steps 2-8
28 | Configure LGS WFS |  | 100 | 90 |  | 10 |  | Parallel to steps 2-10
29 | Configure NGS sensors |  | 122 | 90 |  | 32 |  | Parallel to steps 2-14

## NGS-AO Acquisition
| NGAO Flowdown Budget: |  |  |  |  | #VALUE!
Version 0.2 - 5/19/09
| Units |  |  | Seconds
| Available Allocation |  |  | 180 |  |  |  | Requirement: ?
| Remainder |  |  | 74
Step | Flowdown Tree |  |  | Value |  |  |  | Rationale
Current Estimate 106
1 | Terminate AO correction |  |  | 0 |  |  | Terminate AO correction 0 | Open loops and shutter laser
2 | Slew to pointing star |  |  | 60 |  |  |  | TBC; need median value vs. science case
| Check pointing |  |  | 18
3 |  | Integration |  |  | 5 |  |  | Must reach R=12.0 with SNR>20 for easy automated analysis
4 |  | Readout |  |  | 1
5 |  | Analysis |  |  | 2
6 |  | Operator verify |  |  | 5
7 |  | Correct pointing |  |  | 5
8 | Slew to science target |  |  | 10
| Acquire NGS |  |  | 18 |  |  | Acquire NGS 18
9 |  | Offset telescope to sky |  |  | 3
10 |  | Record HO-WFS background |  |  | 10
11 |  | Offset back to target |  |  | 3
12 |  | Close TT & DM loops |  |  | 2
| Current Estimate |  |  | 106
Step | Parallel Activities |  | Budget | Value |  | Remainder
13 | Install ACAM fold mirror |  | 60 | 10 |  | 50 |  | Parallel to step 2
14 | Remove ACAM fold mirror |  | 10 | 8 |  | 2 |  | Parallel to step 8
15 | Configure HO-WFS |  | 88 | 10 |  | 78 |  | Parallel to steps 2-14