## NGAO Risk ID
Ref. # | Rank | Description | Severity | First Probability WAG | Mitigation Plans
1 |  | Achieving science requirements.
a |  | Long exposure time performance. | Moderate | Likely | On instrument metrology
b |  | (add other parameters?)
2 |  | Science requirements inadequately understood & changing. | Major | Likely | Talk to the astronomers a lot
3 |  | Delivered PSF too variable (spatially and temporally) to satsify astrometry and photometry requirements | Moderate | Possible
4 |  | Adequately meeting interferometer needs | Unk | Likely | Review proposed performance with KI team
|  | Rayleigh background on LGS WFS cannot calibrated out. | Major | Possible | Issue for GS MCAO, will be tested by them. Use long period pulsed laser and eletronic shutter on HOWFS CCD to gate out Rayleigh
5 |  | Wavefront error budget assumptions & accuracy
a |  | Bandwidth error assumptions. Assumption that closed loop bandwidth is 1/15 of sample rate. The rate of ~1/20 has been demonstrated, but would significantly impact error budget. | Moderate | Unlikely | Invesitgate and simulate control loop impact.
b |  | Sodium return expectations not met | Major | Possible | Refine and adjust assumptions based on data from current systems
c |  | 1e- CCDs for WFS. | Major | Possible | Another design turn for CCID-56, more laser power
d |  | Impact of telescope vibration. | Moderate | Possible | Reduce telescope vibrations
e |  | Tomography. No sky demonstration.
i |  | Codes contain assumptions that are untested in actual operating conditions | Major | Possible | Refine and adjust assumptions based on testing
ii |  | Alignment and registration - beacons and WFS | Major | Likely | Design opto-mechanics for closed loop beacon positioning and stability. Implement test procedures during I&T to ensure proper alignment and registration.
g |  | Tip/tilt tomography. No sky demonstration of benefits of multiple TT stars | Moderate | Unlikely
|  | Rotating LGS constellation limits performance for long exposures | Moderate | Likely | De-rotate, configurable add beacons?
|  | MCAO mirrors are not at proper conjigates or correct "statistical position" for the actual Cn^2 profile | Moderate | Possible | Get MASS/DIMM data for Mauna Kea before detailed design phase
6 |  | Achieving contrast performance budget. | Unk | Possible | (Need to verify science requirements)
7 |  | Achieving defined photometry budget | Unk | Possible | (Need to verify science requirements)
8 |  | Achieving defined astrometry budget | Unk | Possible | (Need to verify science requirements)
9 |  | Achieving desired SNRs | Unk | Possible | Managing throughput in optical design, making provisions for long exposure stability
10 |  | Achieving polarimetry requirement | Unk | Possible | Control effects that rotate or scramble polarization
11 |  | Risk of not being able to find adequate tip/tilt stars for certain science cases. | Minor | Likely | System provides gradual degradation, TT stars AO corrected
12 |  | Fiber transport. Mitigation is conventional beam transport. | Moderate | Likely | Testing programs underway for fibers.
13 |  | Availability of 65 actuator DM with 3.5 mm pitch with adequate stroke. | Major | Possible | Use 48 x 48, 5 mm, add a second DM
14 |  | DM on a tip/tilt stage. | Major | Likely
|  | DM incompatible with operation on TT stage | Major | Unlikely | Use a separate TT mirror
|  | Problems with DM interface cabling on TT stage | Major | Likely | Address in DM design
|  | Insufficient TT rejection | Moderate | Possible | Add a second TT mirror
15 |  | Switchyard approach:
a |  | Dichroics. Size and performance. | Major | Likely | (at report we will not have this level of risk). Test coating samples to confirm performance before completing design
b |  | Performance and reliability of dichroic changers. | Moderate | Unlikely
16 |  | K-mirror. Size, performance. | Moderate | Possible | Other architectures for derotation, better coatings
17 |  | Achieving real-time control performance requirements | Major | Possible | Benchmark tests, simiulations anchored to RTC hardware performance, prototype testing
18 |  | Fitting system on telescope. | Major | Unlikely | Design process will ensure compatible system
19 |  | Thermal/mechanical performance of AO system environmental enclosure. | Moderate | Unlikely | Careful design, thermal performance modeling including FEA.
20 |  | Design & cost of interfacing with existing instruments exceeds value of doing so | Unk | Possible | Replace those instruments
21 |  | Availability of required lasers. | Major | Likely | Continue to pursue laser development
22 |  | MOAO not demonstrated. | Moderate | Likely | MCAO gives reasonable sky coverage, VILLAGES testing planned. Other testing programs, perhaps on existing Keck AO system.
23 |  | Fast LOWFS IR (SNAP) based camera.
|  | Detector performance | Moderate | Possible | Some performance data on hand. Testing continues.
|  | Detector availability | Major | Unlikely | Two sources of supply
24 |  | Calibration unit with LGS simulators.
a |  | Finding space for it | Major | Possible | Will be designed in from the beginning as an essential capability
b |  | Achieving required level of performance | Moderate | Possible | On-sky calibration can substitute at greater expense.