## LE
NGAO Laser Enclosure WBS 5.1 | Total |  |  | Delta |  |  | MRI | [10 empty] | Delta | [5 empty] | MRI activites
| DD | FSD | DC | DD | FSD | DC | DD | FSD | DC |  | Effort | Input Code | Salary Grade | DD | FSD | DC |  | DD | FSD | DC |  |  |  | DD | FSD | DC
Post Doc PostDoc A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Principal Investigator | ProjMgr | E | 8 | 8 | 8 |  | 4 | 4 | 4 |  |  |  | 4 | 4 | 4
Technician Tech A | 92 | 130.17 | 188.72 | 16 | 24.67 | 38 | 76 | 105.5 | 150.72 |  | Senior Managers | ProjMgr | E | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Junior Scientist / Engineer JunSci B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Instrumentation Manager | SubMgr | E | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Associate Scientist / Engineer AssoSci C | 317 | 240.83 | 172.28 | 93 | 144.33 | 100 | 224 | 96.5 | 72.28 |  | Subsystem Manager | SubMgr | E | 114 | 83 | 80 |  | 8 | 8 | 32 |  |  |  | 106 | 75 | 48
Information Tech. Specialist IT C | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | System Engineer | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Senior Scientist / Engineer SrSci D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AO Scientist | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Lead Scientist / Engineer5 LdSci E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AO System Engineer | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Business Functions: | [10 empty] | Optics Engineer | AssoSci | C | 56 | 32.66 | 28 |  | 28 | 12.33 | 16 |  |  |  | 28 | 20.33 | 12
Administrative I AsstAdmin A | 18 | 6 | 14 | 1 | 1 | 5 | 17 | 5 | 9 |  | AO Software Engineer | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Administrative II AssoAdmin B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Software Engineer | AssoSci | C | 27 | 88 | 32 |  | 19 | 84 | 28 |  |  |  | 8 | 4 | 4
Management Functions: | [10 empty] | Support Astronomer | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Subsystem Manager SubMgr E | 114 | 83 | 80 | 8 | 8 | 32 | 106 | 75 | 48 |  | Mechanical Engineer | AssoSci | C | 88 | 48 | 44.28 |  | 4 | 4 | 8 |  |  |  | 84 | 44 | 36.28
Project Manager ProjMgr E | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 |  | Facilities Engineer | AssoSci | C | 58 | 8 | 8 |  | 8 | 0 | 8 |  |  |  | 50 | 8 | 0
Subtotal | 549 | 476 | 463 | 122 | 182 | 179 | 427 | 294 | 284 |  | System Administrator | IT | C | 0 | 8 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 8 | 0
Procurements $$ | 0 | 31500 | 2000 | 0 | 6000 | 1000 | 0 | 25500 | 1000 |  | Electronics Engineer | AssoSci | C | 88 | 64.17 | 60 |  | 34 | 44 | 40 |  |  |  | 54 | 20.17 | 20
[11 empty] | Laser Engineer | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Personnel | DD | FSD | DC | DD | FSD | DC | DD | FSD | DC |  | Laser Safety Officer | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
AssoSci | 317 | 248.83 | 172.28 | 93 | 144.33 | 100 | 224 | 104.5 | 72.28 |  | Summit Supervisor | AssoSci | C | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
SrSci | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | AO Electronics Technician | Tech | A | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
JunSci | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Electronics Technician | Tech | A | 0 | 40.83 | 40 |  | 0 | 0 | 20 |  |  |  | 0 | 40.83 | 20
Tech | 92 | 130.17 | 188.72 | 16 | 24.67 | 38 | 76 | 105.5 | 150.72 |  | Mechanical Technician | Tech | A | 0 | 33.34 | 100.72 |  | 0 | 16.67 | 10 |  |  |  | 0 | 16.67 | 90.72
AsstAdmin | 18 | 6 | 14 | 1 | 1 | 5 | 17 | 5 | 9 |  | Mechanical Designer | Tech | A | 92 | 8 | 0 |  | 16 | 0 | 0 |  |  |  | 76 | 8 | 0
SubMgr | 114 | 83 | 80 | 8 | 8 | 32 | 106 | 75 | 48 |  | Laser Technician | Tech | A | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
ProjMgr | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 |  | Facilities Technician | Tech | A | 0 | 48 | 48 |  | 0 | 8 | 8 |  |  |  | 0 | 40 | 40
Subtotal | 549 | 476 | 463 | 122 | 182 | 179 | 427 | 294 | 284 |  | Administrative Assistant | AssAdmin | A | 18 | 6 | 14 |  | 1 | 1 | 5 |  |  |  | 17 | 5 | 9
Procurements $ | 0 | 31500 | 2000 | 0 | 6000 | 1000 | 0 | 25500 | 1000 |  | Subtotal |  |  | 549 | 476 | 463 |  | 122 | 182 | 179 |  |  |  | 427 | 294 | 284
Total Labor () | 1488 |  |  | 483 |  |  | 1005 |  |  |  | Total |  |  |  |  | 1488 |  |  |  | 483 | [5 empty] | 1005
Total Procurements $ | 33500 |  |  | 7000 |  |  | 26500
Cost
[11 empty] | Procurements | Input Code | Estimate | DD | FSD | DC |  | DD | FSD | DC | DD | FSD | DC | DD | FSD | DC | DD | FSD | DC
[10 empty] | 1 | MRI Mounting Frame | SUB | EE | 0 | 4000 | 0 | 4000 | 0 | 0 | 0 |  |  |  | 0 | 4000 | 0 |  | 1
[10 empty] | 2 | MRI Laser Enclosure Panelling | MAT | EE | 0 | 1000 | 0 | 1000 | 0 | 0 | 0 |  |  |  | 0 | 1000 | 0 |  | 1
[10 empty] | 3 | MRI Glycol Infrastructure | MAT | EE | 0 | 3000 | 0 | 3000 | 0 | 0 | 0 |  |  |  | 0 | 3000 | 0 |  | 1
[10 empty] | 4 | MRI Electrical Infrastructure | MAT | EE | 0 | 2500 | 0 | 2500 | 0 | 0 | 0 |  |  |  | 0 | 2500 | 0 |  | 1
[10 empty] | 5 | MRI Optical Mount and Window | EQP | EE | 0 | 10000 | 0 | 10000 | 0 | 0 | 0 |  |  |  | 0 | 10000 | 0 |  | 1
[10 empty] | 6 | MRI Electronics Assemblies | EQP | EE | 0 | 5000 | 0 | 5000 | 0 | 0 | 0 |  |  |  | 0 | 5000 | 0 |  | 1
[10 empty] | 7 | MRI Installation Hardware | MAT | EE | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 |  |  |  | 0 | 0 | 1000 |  |  | 1
[10 empty] | 8 | Temperature/Humidity Monitor | EQP | CPE | 0 | 1500 | 0 | 1500 | 0 | 1500 | 0 |  | 1 |  | 0 | 0 | 0
[10 empty] | 9 | Particulate Monitor | EQP | CPE | 0 | 3000 | 0 | 3000 | 0 | 3000 | 0 |  | 1 |  | 0 | 0 | 0
[10 empty] | 10 | HEPA Filtration | EQP | EE | 0 | 500 | 0 | 500 | 0 | 500 | 0 |  | 1 |  | 0 | 0 | 0
[10 empty] | 11 | SYD Optical Mounts | EQP | EE | 0 | 1000 | 0 | 1000 | 0 | 1000 | 0 |  | 1 |  | 0 | 0 | 0
[10 empty] | 12 | Installation Hardware | MAT | EE | 0 | 0 | 1000 | 1000 | 0 | 0 | 1000 |  |  | 1 | 0 | 0 | 0
[10 empty] | 13 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 14 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 15 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 16 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 17 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 18 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 19 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 20 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 21 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 22 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 23 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 24 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[10 empty] | 25 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
[11 empty] | Subtotal |  |  | 0 | 31500 | 2000 |  | 0 | 6000 | 1000 |  |  |  | 0 | 25500 | 1000
[11 empty] | Total |  |  |  |  | 33500 |  |  |  | 7000 | [5 empty] | 26500