Sept 13, 2009

- Keck Next Generation Adaptive Optics

- System Monthly Report for J. Chin

- August, 2009 Completed Activities

- The following are activities completed for this period.

- General:  Focus of the effort was to complete the optical mechanical designs for the LLF in support for the upcoming Oct 30 design review.  Significant effort went into the RFQ for the launch telescope.

1.3.2 Management & Planning

1.3.3 System Engineering

1.3.3.5 External Interfaces (50%)

1.3.3.5.1.5 Telescope to LGSF Software ICD

No new activities.  Draft ICD completed for telescope to LGSF Software in May.  Context of the data is provided.  Needs review by System Engineering.

1.3.3.5.1.5 Acquisition Guider System to LGSF Software ICD

No new activities.  Draft ICD completed for AGS to LGSF Software in May.  Context of the data is provided.  Needs review by System Engineering.

1.3.3.6 Internal Interfaces

1.3.3.6.2 AO to LGSF ICD

No new activities.  Draft ICD completed for AO to LGSF in May.  Context of the data is provided.  Needs review by System Engineering.

- 1.3.5 Laser Guide Star Facility

- 1.3.5.1  Laser Enclosure (5% complete)

- Current K2 laser enclosure mechanical drawings are being placed into the “vault” area for NGAO.  The “vault” is an area where drawings are sufficiently mature for collaborative work.  Drawing numbers are being generated for NGAO.

- 1.3.5.3  Laser Launch Facility(35% complete)

- Management:

- Jim Bell is turning over his work in the LLF to Drew Medeiros.  Jim will continue as a resource role only.  However, Jim will complete the BGS system since he has played a major role in the design.

- With the Keck II Center Launch System starting, BTO and launch telescope activities will be charged to the new project.

Beam Generation System: In the previous design, the motion control device selected was too large for the BGS optical bench.  A new set of motion devices have been selected and electronics have examined that they are acceptable.  New layouts and drawings are being generated for this design.

Beam Transport Optics:  Drawings have been generated showing layout of optical path.  Documentation has started on the BTO; but still has a way to go.  Flexure testing has been scheduled for Sept 22.  The results will help in determining the requirements on the design.

Launch Telescope:  Significant work went into this area for requirements, vendor selection, and contracts in preparation for RFQ; expecting solicitation to go out on the week of Sept 14.

- 1.3.5.4 Safety System Design

- 1.3.5.4.1 Personnel and Equipment Safety System (50%)

No new activities on laser designs.  Needs review by System Engineering.

.

- 1.3.5.4.2 LTCS (50%)

No new activities.  Preliminary Draft Design on Twiki.  Needs review by System Engineering.

1.3.5.4.3 Space Command Laser Clearing House (85%)

Submission of LCH registration form for NGAO lasers.  LCH finally came back with further questions that need to be answered.

1.3.5.5  Laser System Lab I&T Plan (0%)

1.3.9 Telescope Integration and Test

1.3.9.1 Old AO/Laser Removal

No new activities.  Updated Laser Removal Plan for completeness (90% complete).  Draft plan on Twiki for review.

- 1.3.10 Operations Transition

- 1.3.10.1  Operations Plans (15% complete)

- No new activities on laser designs.  Draft Operations Support Plan and Maintenance Plans are on Twiki for review.

- 1.3.10.2Operations Handover (15% complete)

No new activities on laser designs .  Draft Operations Handover Success Criteria on Twiki for review.

Draft LGSF Training Plan on Twiki for review.