March 8, 2010

- Keck Next Generation Adaptive Optics

- System Monthly Report for J. Chin

- February, 2010 Completed Activities

- The following are activities completed for this period.

- General:  The Launch Telescope Selection Committee has focused the candidates to two contractors from four.  Three members of NGAO team visited one vendor to assist with the selection.  The vendor was deemed positive and contract negotiations are on-going.   With the laser vendor chosen, the supporting subsystems for the laser moved forward such as the safety system and laser enclosure.

1.3.2 Management & Planning

1.3.3 System Engineering

1.3.3.5 External Interfaces (50%)

1.3.3.5.1.5 Telescope to LGSF Software ICD

(no new activity for the month) Draft ICD completed for telescope to LGSF Software in May.  Context of the data is provided.  Needs review by System Engineering.

1.3.3.5.1.5 Acquisition Guider System to LGSF Software ICD

(no new activity for the month) Draft ICD completed for AGS to LGSF Software in May.  Context of the data is provided.  Needs review by System Engineering.

1.3.3.6 Internal Interfaces

1.3.3.6.2 AO to LGSF ICD

(no new activity for the month) Draft ICD completed for AO to LGSF in May.  Context of the data is provided.  Needs review by System Engineering.

- 1.3.5 Laser Guide Star Facility

- 1.3.5.1  Laser Enclosure (85% complete)

- With the selection of the laser vendor, the laser enclosure preliminary design was able to make progress.  The decision is made to reuse the existing laser enclosure on the Keck II elevation ring.  The PD document shows the ability of the current LE to support the requirements of the new lasers with modifications.  The modifications have been documented and only management issues remain to complete the PD.

- 1.3.5.2  Laser (70% complete)

- With the selection of the vendor, a PD document has been written to support the installation of three lasers.  The laser design must still go through its detailed design before all interfaces are finalized.  The PD document demonstrates how the new lasers are integrated onto the telescope.  The PD document includes the designs and interfaces necessary to support the laser.  Management issues remain to be completed for the PD.

- 1.3.5.3  Laser Launch Facility(75% complete)

- Management:

Beam Generation System: (no new activity for the month)  The selection of the BGS motors for the PNS is still unanswered although the baseline design has a stage that is capable of meeting the specifications.  The current drawings have this stage represented.  The drawings have also been changed to reflect the changing gravity vector so there is minimal mass on the stage affected by gravity.

Beam Transport Optics: (no new activity for the month)  A new set of drawings have been completed to the PDR level to show the BTO from the switchyard to the BGS.  Final touches are being made to complete this set.

Switchyard:  (no new activity for the month) New drawings have been generated to show the lasers in the Switchyard assembly.  This provides a relative scale of new lasers with respect to the Switchyard and LSE.  Considerations were made to support maintenance and servicing of the lasers.

Launch Telescope:  A site visit was conducted on a vendor.  Contract negotiations are ongoing.

- 1.3.5.4 Safety System Design

- 1.3.5.4.1 Personnel and Equipment Safety System (75%)

With the selection of the laser vendor, the safety system design has been updated.  Only the management issues remain for the PD.

.

- 1.3.5.4.2 LTCS (50%)

(no new activity for the month)  Preliminary Draft Design on Twiki.  Needs review by System Engineering.

1.3.5.4.3 Space Command Laser Clearing House (85%)

(no new activity for the month)  Submission of LCH registration form for NGAO lasers.  No new activities.

1.3.5.5  Laser System Lab I&T Plan (0%)

1.3.9 Telescope Integration and Test

1.3.9.1 Old AO/Laser Removal

(no new activity for the month)  Updated Laser Removal Plan for completeness (90% complete).  Draft plan on Twiki for review.

- 1.3.10 Operations Transition

- 1.3.10.1  Operations Plans (15% complete)

- (no new activity for the month) Draft Operations Support Plan and Maintenance Plans are on Twiki for review.

- 1.3.10.2Operations Handover (15% complete)

(no new activity for the month).  Draft Operations Handover Success Criteria on Twiki for review.

Draft LGSF Training Plan on Twiki for review.