Keck Adaptive Optics Note 720

NGAO Preliminary Design Phase

Risk Evaluation

Peter Wizinowich, Rich Dekany, Don Gavel

May 4, 2010

Introduction

This note is intended to summarize the significant programmatic and technical risks associated with the NGAO program at the end of the preliminary design phase.  This KAON is an update to the system design phase programmatic risk evaluation discussed in KAON 566 and the technical risk evaluation discussed in KAON 510.

1. Methodology

The JPL risk evaluation matrix approach used for the Keck Interferometer was selected to track the significant programmatic and technical risks.  This matrix ranks each risk by the consequences and likelihood of the risk occurring.  A scale of 1 to 5 is used with higher numbers representing higher risk.

Likelihood of Occurrence:

| Level | Definition |
| --- | --- |
| 5 | Very High > 70%, almost certain |
| 4 | High >50%, more likely than not |
| 3 | Moderate >30%, significant likelihood |
| 2 | Low > 1%, unlikely |
| 1 | Very Low <1%, very unlikely |

Consequence of Occurrence – Programmatic Risks

(replaced JPL’s usage of “launch” with “schedule”)

| Level | Implementation Risk Definition |
| --- | --- |
| 5 | Overrun budget & contingency. Cannot deliver. |
| 4 | Consume all contingency, budget or schedule |
| 3 | Significant reduction in contingency or schedule slack |
| 2 | Small reduction in budget or schedule slack |
| 1 | Minimal reduction in budget or schedule slack |

Consequence of Occurrence – Technical Risks

(replaced JPL’s usage of “mission return” with “science return”):

| Level | Performance Risk Definition |
| --- | --- |
| 5 | Project Failure |
| 4 | Significant reduction in science return |
| 3 | Moderate reduction in science return |
| 2 | Small reduction in science return |
| 1 | Minimal or no impact to science return |

The JPL-format risk matrices using these definitions are shown in the next section.  In this risk matrix red represents high risks that require implementation of new processes or a change in the baseline plan, yellow represents medium risks that need to be aggressively managed including considering alternative approaches, and green represents relatively low risks that should at least be monitored.

2. Programmatic Risks Identification and Ranking

2.1 Programmatic Risk Matrix

The programmatic risk matrix before and after the PDR are shown in the following Figure.  At left is the risk matrix presented at the SDR and the current risk matrix is shown at right.

Overall the three risks associated with funding have increased in likelihood (all are in the red), two risks have decreased in both likelihood and consequence (moving them into the green), two other risks have decreased in likelihood and two risks remain unchanged.

2.2 Significant Programmatic Risks

The following table lists the significant programmatic risks that were identified during the system design in the same order as in KAON 566. No new risks have been identified.  Each risk has a unique number, a trend column which has been used for tracking which way the risks are moving, a consequence ranking, a likelihood ranking, a description, the status of the risk and plans for mitigation.

3. Technical Risks Identification and Ranking

3.1 Technical Risk Matrix

The technical risk matrix before and after the PDR are shown in the following Figure.  At left is the risk matrix presented at the SDR and the current risk matrix is shown at right.

Overall there are no risks in the red and the risks in the yellow have decreased from 12 to 8 with two of the remaining yellow risks dropping in likelihood; however two new technical risks have been added with the inclusion of the science instrument in the risk assessment.  The simplifications introduced by the build-to-cost redesign and the completion of the preliminary design have both resulted in lowering the technical risks.

3.2 Significant Technical Risks

The following table lists the significant programmatic risks that were identified during the system design in the same order as in KAON 510. No new risks have been identified.  Each risk has a unique number, a trend column which has been used for tracking which way the risks are moving, a consequence ranking, a likelihood ranking, a description, the status of the risk and plans for mitigation.

4. Risk Mitigation Plan

The risk mitigation plan addresses risks that were shown as “red” or “yellow” in the risk matrices.  For “green” items is to simply track these risks and look for opportunities to reduce these risks.

4.1 Programmatic Risk Mitigation Plan

There are three “red” programmatic risks all associated with funding uncertainty:

- Significant NGAO funding needed.

- Challenge of a rapid project ramp-up.

- Schedule impact of funding uncertainty.

The “yellow” risks include:

- Required lasers unavailable &/or costs too high.

- Lack of full-time personnel.

- Development schedule for DAVINCI is delayed with respect to NGAO.

- External contract schedule slips.

- Schedule slip due to personnel availability.

4.2 Technical Risk Mitigation Plan

There are no “red” technical risks.  The “yellow” risks include:

- Inadequate PSF calibration to support precision astrometry, photometry and companion sensitivity science.

- Required lasers unavailable.

- Wavefront error budget not achieved due to inadequate assumptions and calculations.

- Inadequate tomographic reconstruction accuracy to support the wavefront error budget and hence specific science cases.

- Astrometry performance requirement not achieved.

- Complexity and instability of interactions in the overall software control system.

- Adequate wavefront sensor CCDs not available.

- Photometry performance requirement not achieved.

- H4RG chip not available for DAVINCI.

- DAVINCI hybrid image slicer reformatting optics scattering exceeds acceptable limit.