Keck Adaptive Optics Note 822

Keck Next Generation Adaptive Optics

Preliminary Design Phase Project Report #29

P. Wizinowich, Sean Adkins and the NGAO Team

October 27, 2010

# Narrative

This report is the twenty-ninth monthly project report for the Preliminary Design (PD) phase in the development of the W. M. Keck Observatory’s (WMKO’s) Next Generation Adaptive Optics (NGAO) facility.  This report covers the PDR follow-up work performed in September 2010.

## Summary

The focus in September was on the post-PDR NGAO activities and the next steps for NGAO.

## Management Status

The PD phase plan presented at the SDR included work under the following management WBS elements. The progress in each of these areas is discussed below.

### WBS 1.3.2.1 Planning

The NGAO related post-PDR development activities, identified in the June report, include the following items (in approximate order of priority).  Their high level status as been included:

- MRI-funded laser launch telescope. System PDR successfully completed on October 12.

- ATI-funded near-IR tip-tilt sensor. SDR planned for Dec. 7.

- MRI-proposed laser. Proposal unsuccessful; considering resubmitting.

- PSF reconstruction demonstration. Efforts ongoing.

- Parametric oscillator implementation. Effort discontinued.

- Reduced focal anisoplanatism error. Cost/benefit analysis continuing.

Several additional NGAO risk reduction activities were also identified as appropriate to carry out:

- Differential motion between DAVINCI and the NGAO tip-tilt sensors

- Real-time control design

- Control system design

- Performance modeling

- Wavefront sensor camera path forward

- Mechanical model clean-up

The mechanical model clean-up is nearly complete.

### WBS 1.3.2.4 Proposals

It was agreed to submit a PSF reconstruction proposal to ATI on November 1.

## Technical Status

The technical status was reported at the NGAO PDR held in June.

Technical progress in September included the following:

- PSF-reconstruction

  - Worked on understanding the discrepancies in the tip-tilt error estimated by the OPERA PSF recovery algorithm and the tip-tilt errors in Gemini AO observations and computer simulations.

  - Preliminary PSF recovery estimates, made using Flicker’s Keck code, appear to be in error by 10-15% in estimated Strehl when compared to NIRC2 images from the August engineering.

  - Started work on ATI proposal.

- Parametric Oscillator (PO) implementation

  - Based on preliminary Keck AO data analysis it appears that the PO technique will have a smaller than anticipated effect. The team has stopped work on this project.

- Reduced  Focal Anisoplanatism (FA)

  - Ellerbroek converted his closed loop minimum variance reconstructor code from RATFOR to MATLAB. Preliminary results for Keck show a modest but significant improvement for the minimum variance reconstructors over the current regularized least squares reconstructors.

  - Benchmarks were run on the current Keck IDL reconstructor tool. This tool is responsible for generating new reconstructors as the irregularly shaped Keck telescope pupil rotates across the wavefront sensor subapertures. The Keck reconstructor runs on the K2 AO server, which is an ~ 5 year old dual processor Sparc Sun-Fire-V240. A full reconstructor happens in ~2.7 seconds of which ~1.4 seconds is spent in the IDL INVERT routine.

- Software Framework Selection

  - An official decision was made in September to proceed with EPICS.

## Keck Adaptive Optics Notes

All of the NGAO KAONs can be found at:

http://www.oir.caltech.edu/twiki_oir/bin/view/Keck/NGAO/NewKAONs.

The following KAONs were produced in September:

KAON 807, NGAO/TCSU Software Framework Selection

KAON 810, Preliminary Design Report #28

## Schedule and Budget Status

### Milestones

As reported in the June report all of the preliminary design phase milestones and preliminary design phase mini-reviews were completed.

### Schedule

There is little point in tracking the PD phase schedule since our tasks and priorities have changed for the post-PDR work.  A high level snapshot of the tracked version of the new schedule through July 2010 was provided in the July 2010 report; with 82% of the total PD phase work complete.

For the purposes of the NGAO PD phase, and due to the future funding uncertainty, no additional work has occurred on the DAVINCI science instrument design. The tracked version of the DAVINCI MS Project plan is therefore unchanged since the June 2010 report (52% of the overall design work and 73% of the PD work is complete).

### Budget

The total NGAO PD phase budget (from the SEMP) was $3030k excluding contingency; the contingency was $449k.  The revised total NGAO PD phase budget, based on the funded TSIP proposal, is $3276k including contingency (an overall reduction of $203k).  The contingency in the new budget is $157k and we also assigned $149k for work in July and August to wrap up action items from the preliminary design review meeting.  The new budget to complete the work through the design review, excluding contingency, is therefore $3276k - $157k - $149k = $2970k.

A total of $2981k has been spent through September or 91% of the budget including contingency, compared to 82% of work completed excluding the science instrument.

## Anticipated Accomplishments in the Next Period

All of the previously anticipated accomplishments through June have been completed and we have chosen not to list them here (see the June report for this list).

The anticipated accomplishments for July along with their status in italics:

- NGAO presentation to the WMKO Science Steering Committee and CARA Board.  Complete.

The anticipated accomplishments for August along with their status in italics:

- Submit & review pre-proposals with SSC/Directors.  Complete.

The anticipated accomplishments for September along with their status in italics:

- Make a decision on the software framework infrastructure for NGAO.  Complete.

- Make a decision on whether to proceed with the parametric oscillator.  Complete.

No major accomplishments are planned to be completed in October.

# Financial Summary

The budget, expenditures to date and estimate to completion for the NGAO project is shown in Table 1.

Table 1:  NGAO PD Phase Expenditure Summary for Year 1 to 3 through September 2010