## Software Plan
TRICK project tasks and milestones for controls and software
Task | Milestone Date | Plan/comment | Status w/ Date
Motion Control | 2011-01-14 | Meeting w/ AC 12/28 to gather details of hardware devices. | Complete 1/3/2011
DAR | 2011-01-28 | Setup meeting w/PS and finalize code structure + implementation
Focus compensation | 2011-01-28 | Same as above
Non-sidereal tracking | 2011-01-28 | Same as above
Device control | 2011-02-11 | Coordinate w/ CN,JL to gather requirements from operations side and Caltech for implementation
Operations software | 2/18/2011 | Coordinate w/CN to identify requirements for development of EPICS channel access
RTC | 2011-02-25 | WCP interface requirements, EPICS keywords…
TRS | 2011-02-25 | interface requirements and changes to TRS Client
ECR | 2011-02-25 | Entry, updates
Test plan | future | Document by working w/ CN+Caltech+MG
Documentation | 2011-03-10 | DM, ICD, SM

## WBS
TRICK project tasks and milestones for controls and software
Task | Plan/comment | Completion Date | Milestone Date
Motion Control | meet with EE to gather detailed requirements | 2010-12-28 | 2011-01-14
| send keywords list to EE and finalize | 2011-02-18
| Create par files for dichroic and focus stage devices | 2011-01-03
| Update startup file to invoke the par files | 2011-01-03
| Add a sequencer for each device to manage state machine controls | 2011-01-03
| Update keyword cake file to populate device specific keywords | 2011-01-03
| Update capfast schematics to add the blocks for 1 dof for each device | 2011-01-03
| Edit k1obTop engineering display to include the controls for the devices from the GUI | 2011-01-03
Device Control | Kick-off meeting with John Cromer (JC) @ Caltech to establish a plan | 2011-01-31
| Create a requirements document and send to JC | 2011-02-02
| Feedback from JC | 2011-02-10
| Populate keywords required for device control | 2011-02-11
| Review keyword list with JC and finalize the list |  | 2011-02-11
Centroid offset calculation | Setup meeting with Paul Stomski to understand requirements | 2010-12-15
| document requirements | 2011-01-06
| document implementation details | 2011-01-28
Add a coordinate conversion block for TRICK to map TRICK's Xim,Yim to AO bench (use ACAM as reference)
Offset summation block to capture offset correction from DAR, RESUMEX,Y from DCS resume positions for user requested offsets
convert output from summation block to pixel units, compute centroid offset correction to be sent to RTC and ROI location to be sent to TRICK Host computer
Timing sync up between sending ROI location to TRICK and centroid offset to RTC
| update keyword list to accommodate DAR, non-sidereal, acquisition offset, user requested offset, image shifts (pickoffs, plate scales in OSIRIS, distortion mapping) | 2011-01-28 | 2011-01-28
Focus compensation | update SC capfast to include focus compensation control for TRICK. The exact implementation details is not available until the TRICK detector fully characterized and the calibrated. This includes a focus error (Z term) calculation from X and Y and some TBD control parameters to control the focus. An example is already available for focus control for current instruments
| document keywords required to support focus control | 2011-01-28 | 2011-01-28
Operations software | Coordinate w/CN to identify requirements for development of EPICS channel access to support ops software | 2011-02-14 | 2/18/2011
RTC | document list of keywords required for interfacing camera to RTC via fiber link for image data
document list of keywords for interfacing controls to RTC via WCP
| document implementation details for WCP changes | 2011-02-09
| send keyword list to MicroGate | 2011-02-23 | 2011-02-25
| Review keyword list with MicroGate and finalize the list |  | 2011-02-25
update kxwifMGAOSBaseParameter.ini for parameter changes
kxStartupScript for loading project specific records, execute any additional sequences, code, fileLoadSeq calls if any parametric files are to be loaded at startup
Update wfc2ifepics to add new commands
Add genSub support for new commands as necessary
update capfast schematics for newly created genSubs
wif/init, command, MGAOSVariables.h, public.h and wif.h changes for adding new commands
TRS | document list of data to be stored in telemetry | 2011-02-15
| document implementation details for changes to TRS client | 2011-02-09
| send keywords list to MicroGate | 2011-02-23
| Review keyword list with MicroGate and finalize the list |  | 2011-02-25
update WCP_telem data struct for new data
Update EPICS genSub
Update excel spreadsheet with memory map
update trsServer files that are affected by the additional data logging including kx_db_ddl.sql database files
update wifAvgTelemetry if any averaging specific to this instrument needs to be done outside of MGAOS
might need to add supporting functions for idl query specific to this instrument
update capfast schematics for tl channels and tl channels2 and even add another block to support the genSub
ECR | Entry, updates | 2011-01-07 | 2011-02-25
Test plan | Document by working w/ CN+Caltech+MG |  | future
Documentation | Approved keyword list (controlled document) |  | 2011-03-10