## Sheet1
| NGAO Opto-mechanical subsystem - action item tracking list |  |  | original | 2010-02-18
|  |  |  | rev | 2010-04-30
Item number | Short name | Description | Status | Source | Plan | Completion | Comments/Questions
or Expected Completion
1 | ADC | Design the science path ADC and incorporate into the Zemax and SolidWorks models. Design for 1-2 microns and evaluate performance to 600 nm | done | Design doc, ch. 6 "Work remaining for PDR" | Documentation to be done | 2010-04-30
2 | Thermal analysis
2a | Thermal drift analysis | Determine the tolerance requirements for thermal drift. | not started | Reviewer final report | Reni to do | 2010-05-30
2b | Thermal alignment analysis | Determine the issues involved in aligning at ambient for operation at cooled-down temperature | not started | Reviewer final report | Reni to do | 2010-05-30
3 | Tolerancing for pupil location and distortion
3a | Tolerancing OAP radius of curvature | Determine the tolerance requiement for OAP radius of curvature | done | Reviewer final report | Reni to do | 2010-04-01
3b | Tolerancing placement of DM | Determine the tolerance requirement for both LODM and HODM placement | done | Reviewer final report | Reni to do. | 2010-04-30 | Use 10 micron decenter tolerance rather than 100 micron.
3c | K mirror alignment | Determine the tolerance requirement for K mirror alignment | done | Reviewer final report |  | 2010-04-15 | Note: Rich points out that Zemax may not handle tolerances of tilted and decentered optics correctly. You were going to check using the methods of KAON 107.
3d | Manufacturing error tolerancing on pupil location and distortion | Determine the allowable manufacturing tolerances given a pupil distortion criterion | done | Reviewer final report | Reni to do | 2010-04-30
4 | Pupil registration | Produce a map of pupil registration between LODM, HODM, and WFS pupils | awaiting optical design from WFS team | Reviewer final report | Reni to do. | 2010-05-30
5 | Anisoplanatism of tilted pupil | Determine the anisoplanatic error caused by the tilted and curved pupil plane at the DMs | done |  | Don to calculate | 2010-04-30 | negligible altitude shift
6 | Cleanliness environment | Define the required cleanliness environment | done | Reviewer final report |  |  | This is now reflected in the transmission/emissivity calculator, assumiing class 1000 cleanroom conditions
7 | Specification of mounts | Develop the mechanical mounting strategy given the tolerancing results | done | Reviewer final report | Chris to do | 2010-04-30
8 | Entrance window | Specify the entrance window | done | Reviewer final report
9 | AO relay alignment process | Write a section on relay alignment in the design document | done | Design doc, ch. 6 "Work remaining for PDR" | Thomas Stalcup | 2010-04-01 | see Peter's memo KAON 719
10 | Substrates and coatings | Specify the substrates and coatings for optics and windows | done (they're stated in the transmission/emissivity spreadsheet, but need to be entered into Zemax) | Design doc, ch. 6 "Work remaining for PDR" | Reni to complete | 2010-04-30
11 | Polarization analysis | Analyze the effect on polarization pertenant to the interferometer feed | done | Design doc, ch. 6 "Work remaining for PDR" | Chris Neyman | 2010-05-01 | Peter's memo "NGAO and the Keck Interferometer" dated May 1
12 | Update design document | Include results of action items in the appropriate sections of the design document and post to the web | in progress | Project manager | All to contribute | 2010-05-07