## Sheet1
| NGAO Opto-mechanical subsystem - action item tracking list |  |  |  | 2010-02-18
Item number | Short name | Description | Status | Source | Plan | Predicted completion | Comments/Questions
1 | ADC | Design the science path ADC and incorporate into the Zemax and SolidWorks models. Design for 1-2 microns and evaluate performance to 600 nm | not started | Design doc, ch. 6 "Work remaining for PDR" | Reni to design | 2010-04-01
2 | Thermal analysis
2a | Thermal drift analysis | Determine the tolerance requirements for thermal drift. |  | Reviewer final report | Reni to do | 2010-04-01
2b | Thermal alignment analysis | Determine the issues involved in aligning at ambient for operation at cooled-down temperature |  | Reviewer final report | Reni to do | 2010-04-01
3 | Tolerancing for pupil location and distortion
3a | Tolerancing OAP radius of curvature | Determine the tolerance requiement for OAP radius of curvature | Done for wavefront error criterion. Needs to be done for pupil shift | Reviewer final report | Reni to do | 2010-04-01 | Reni, it seems from sections 5.2 and 5.3 of the design document that this tolerance analyses had been done prior to the review. Were the reviewers' commentes targed to pupil alignment only?
3b | Tolerancing placement of DM | Determine the tolerance requirement for both LODM and HODM placement | not started | Reviewer final report | Reni to do. | 2010-04-01 | Use 10 micron decenter tolerance rather than 100 micron.
3c | K mirror alignment | Determine the tolerance requirement for K mirror alignment | Done for wavefront error criterion. Needs to be done for pupil shift. | Reviewer final report |  | 2010-04-01 | Note: Rich points out that Zemax may not handle tolerances of tilted and decentered optics correctly. You were going to check using the methods of KAON 107.
3d | Manufacturing error tolerancing on pupil location and distortion | Determine the allowable manufacturing tolerances given a pupil distortion criterion | not started | Reviewer final report | Reni to do | 2010-04-01
4 | Pupil registration | Produce a map of pupil registration between LODM, HODM, and WFS pupils | awaiting optical design from WFS team | Reviewer final report | Reni to do. | 2010-04-01
5 | Anisoplanatism of tilted pupil | Determine the anisoplanatic error caused by the tilted and curved pupil plane at the DMs |  |  | Don to calculate | 2010-04-01
6 | Cleanliness environment | Define the required cleanliness environment | done | Reviewer final report |  |  | This is now reflected in the transmission/emissivity calculator, assumiing class 1000 cleanroom conditions
7 | Specification of mounts | Develop the mechanical mounting strategy given the tolerancing results | not started, pending the final layout work in conjuction with interfacing systems now ongoing. | Reviewer final report | Chris to do | 2010-04-01
8 | Entrance window | Specify the entrance window | done | Reviewer final report
9 | AO relay alignment process | Write a section on relay alignment in the design document | not started | Design doc, ch. 6 "Work remaining for PDR" | Thomas Stalcup | 2010-04-01
10 | Substrates and coatings | Specify the substrates and coatings for optics and windows | partially done (they're stated in the transmission/emissivity spreadsheet, but need to be entered into Zemax) | Design doc, ch. 6 "Work remaining for PDR" | Reni to complete | 2010-04-01
11 | Polarization analysis | Analyze the effect on polarization pertenant to the interferometer feed | not started | Design doc, ch. 6 "Work remaining for PDR" | Chris Neyman | 2010-04-01
12 | Update design document | Include results of action items in the appropriate sections of the design document and post to the web | in progress | Project manager | All to contribute | 2010-04-01