## Sheet1
AI# | ALTAIR or KECK actions | Deliverables (data, code, documents) | who | LJO days | JCH days | Total LJO days | end date | LJO Cost per item | Total LJO cost | Tolstoy grant | CfAO Keck | Gemini
A01 | Get back on OPERA (house keeping, run it on ALTAIR archive data) |  | LJO | 10 | 0 | 10 | 2010-01-29 | 6560 | 6560 |  | 6560
A02 | establish range of WFS photo-electron count rate per lenslet that is of interest for testing OPERA in bright to faint NGS conditions | DOC: lenslet count rate for tests | LJO | 2 | 0 | 12 | 2010-02-11 | 1312 | 7872 |  | 1312
A03 | Get on-sky AO data (archive or not), first batch. | DATA: 1st batch of ALTAIR sky data | JCH | 0 | 5 | 12 | 2010-02-11 | 0 | 7872 |  | 0
A04 | Testing OPERA on 1st batch of sky data. | DOC: report on first test of OPERA | LJO | 20 | 0 | 32 | 2010-04-23 | 13120 | 20992 |  | 13120
A05 | System debugging – ALTAIR & OPERA. | CODE: new OPERA software | LJO & JCH | 40 | 40 | 72 | 2010-06-23 | 26240 | 47232 | 1766 | 22708 | 1766
A06 | Get 2nd batch of ALTAIR sky data | DATA: 2nd batch of ALTAIR sky data | JCH | 0 | 5 | 72 | 2010-06-23 | 0 | 47232 | 0 |  | 0
A07 | Testing OPERA on 2nd batch of sky data | DOC: report on final test of OPERA | LJO | 20 | 0 | 92 | 2010-09-13 | 13120 | 60352 | 6560 |  | 6560
A08 | Prepare OPERA to make it compatible with GEMINI observatory software standards | CODE: OPERA code translated to Gemini standards | LJO (+?) | 15 | 0 | 107 | 2010-10-12 | 9840 | 70192 | 4920 |  | 4920
A09 | Implement OPERA inside ALTAIR data pipeline | CODE: OPERA implemented into ALTAIR data pipeline | LJO (+?) | 10 | 0 | 117 | 2010-11-02 | 6560 | 76752 | 3280 |  | 3280
A10 | Integrate Ralf Flicker legacy on KECK-AO | DOC: summary of Ralf's contribution that is of interest for our project | LJO | 10 | 0 | 127 | 2010-11-22 | 6560 | 83312 | 3280 |  | 3280
A11 | OPERA modifications for Keck AO (writing interfaces) | CODE: OPERA for KECK-AO | LJO | 15 | 0 | 142 | 2011-01-04 | 9840 | 93152 | 4920 |  | 4920
A12 | Testing final product on ALTAIR, ensure that OPERA delivers what was expected | DOC: report demonstrating compatibility of deliverable with specifications | LJO (+?) | 5 | 0 | 147 | 2011-01-13 | 3280 | 96432 | 1640 |  | 1640
A13 | Set-up a code maintenance procedure for OPERA on ALTAIR | DOC: maintenance procedure defined and implemented | LJO (+?) | 10 | 0 | 157 | 2011-02-02 | 6560 | 102992 | 3280 |  | 3280
A14 | Get on-sky Keck AO data, first batch | DATA: KECK-AO data archives | PWI (+?) | 10 | 0 | 167 | 2011-02-23 | 6560 | 109552 | 3280 |  | 3280
A15 | Testing & debugging OPERA for Keck | CODE: OPERA made ready for KECK-AO | LJO (PWI, +?) | 15 | 0 | 182 | 2011-03-24 | 9840 | 119392 | 4920 |  | 4920
A16 | write OPERA user manual for ALTAIR | DOC: OPERA code user manual | LJO | 10 | 0 | 192 | 2011-04-27 | 6560 | 125952 | 3280 |  | 3280
[10 empty] | 41126 | 43700 | 41126
| LJO hourly rate US$ | 82
| number of hour per day | 8
| LJO daily rate US$ | 656
| total time days | 192
| total cost | 125952
| E Tolstoy grant | 44000
| KECK/CfAO | 43700
| Gemini | 41126
| total availabe | 128826
| margin US$ | -2874
| margin days | -4.3811
vacations in 2010-2011
| Mar-29 to Apr-11 | Eastern
| 13,14,24 May | ascension-pentecote
| Jun-27 to Jul-2 | SPIE 2010 San Diego
| Jul-12 to Aug-22 | summer
| Dec-20 to Jan-2 | winter
| 2 weeks in March 2011 | Eastern
activity level: days / week
| Jan-4 to Mar-26: 1.5 | time shared with IMAKA
| Apr-12 to Aug-27: 5 | full on OPERA
| Aug-30 to end: 3.5 | time left to start other projects