## ProjectCharter
Project Charter
(CN notes: This can all be modified, but it documents our present working assumptions) |  | 1026
Title: | Parametric Oscillator Implementation
Project Lead: | Kevin Tsubota
Project Requirements and Constraints: | 1) We would like to implement the Keck Interferometer parametric oscillator approach to tip-tilt vibration reduction on at least one of the Keck AO systems.
2) We will place a contract with Microgate to implement the required RTC modifications.
3) Demonstrate approach with one of the existing Keck AO systems.
4) Determine remaining implementation cost if demonstration successful
Team: | Kevin Tsubota, Sudha LaVen, Olivier Martin & Chris Neyman
Budget: | Keck: 1026 hours total labor (Par. Osc. Project Plan Kevin Tsubota)
Microgate Subcontract: $18,000.00 USD (ROM estimate)
Schedule: | Start 7/15/2010 Finish 4/4/2011 (Par. Osc. Project Plan Kevin Tsubota)
Sources: | NGAO Post-PDR Priorities and Tasks: P. Wizinowich, June 23, 2010
Parametric Oscillator MS Project Plan: Kevin Tsubota
Keck Request to Microgate for Parametric Oscillator: Erik Johansson
Microgate reply to Keck ROM price request
KAON 680, "Telescope vibration mitigation for NGAO", Chris Neyman August 17, 0009
Original estimates: | NGAO PDR Cost Books: NGAO Team
NGAO Detailed Design MS Project Plan: Jason Chin

## WBS_Dictionary
WBS # | Work Breakdown Structure (WBS) Items
| WBS Sub WBS | Notes (short definition)
1 | Parametric Oscillator Implementation
1.1 | Demonstration Planning | Initial planning of demonstration effort
1.1.1 | Define scope
1.1.2 | Define tasks
1.1.3 | Schedule efforts and costs
1.1.4 | Engineering Change Requests (ECR) | Complete the Keck required forms to change operational AO system software
1.2 | Preparation
1.2.1 | Parametric Oscillator algorithm background investigation | Investigate Keck Interferometer algorithm and real time software realization
1.2.2 | NGWFC architecture background investigation
1.2.3 | Wavefront Processor (WFP) and Interface (WIF) documentation and code review
1.2.4 | Wavefront Controller Command Processor (WCP) documentation and code review
1.2.5 | Setup and document software development environment at Waimea HQ
1.2.6 | Setup and document NGWFC lab hardware at Waimea HQ
1.3 | Management
1.3.1 | Requirements Document | Simplified specification of what needed for parametric oscillator demonstration on Keck II
1.3.2 | Generate SOW | Statement of work to direct Microgate
1.3.3 | Write-up Contract with Microgate
1.3.4 | Ensure remote access for Microgate | Current plan is to have Microgate work on spare NGWFC system in Waimea remotely from Italy
1.3.5 | Oversee and direct Microgate | project long continuous task
1.3.6 | Schedule Tracking
1.4 | Microgate RTC Mods | Work for Microgate under subcontract
1.4.1 | NGWFC Design Document (WFP, WIF) | Note Wavefront Processor (WFP) and Wavefront Interface (WIF) are subsystems of current NGWFC system at Keck
1.4.2 | Document NGWFC Test Plan (WFP,WIF)
1.4.3 | Implementation of WFP algorithm and Wavefront Controller Interface (WIF) modification by Microgate on HQ system (this may require reflashing?)
1.4.4 | Microgate Testing on Waimea NGWFC system
1.4.5 | WMKO run tests based on MG test plan
1.4.6 | Milestone: WMKO acceptance of Microgate mods
1.5 | Systems Engineering / Design
1.5.1 | Design Parametric Oscillator Algorithm | Determine "as built" STRAP, DTT and WFP control loop parameters for Keck AO system, Modify KAON 680 simulations, Write Par. Osc. Design Document section on performance. Provide algorithm outline and direction to software team
1.5.2 | Software Design Document
1.5.3 | Software Test Plan
1.6 | Implementation and Lab Testing | Implement parametric oscillator and related software modification on spare NGWFC system in Waimea
1.6.1 | Wavefront Control Command Processor (WCP)
1.6.2 | AO User Tools
1.6.3 | AO SC
1.6.4 | Lab Integration
1.7 | Summit Integration | Integration of Microgate and Keck Software modifications on summit AO systems with some daytime testing. All changes must be removed and system returned to operational status
1.7.1 | NGWFC | Microgate real-time code
1.7.2 | AO | Keck AO related support code
1.7.3 | System Integration | Test combined Keck and Microgate modifications
1.8 | Parametric Oscillator Demonstration | Nighttime testing of Par. Osc.
1.8.1 | Observing Plan | Plan nighttime observations with Parametric Oscillator
1.8.2 | Observation | Nighttime testing of Par. Osc. Modification
1.8.3 | Demonstration Report | Analysis of Test Data Write demonstration test report
1.9 | Remaining Implementation Plan for Parametric Oscillator | If demonstration successful define tasks and effort remaining for full operational implementation Requests
1.9.1 | Define tasks and effort remaining for implementation
1.9.2 | Schedule efforts and cost