## Changes
# | Proposed Requirements Change | Date | Proposer | Status (3/26/11)
1 | SR 4 needs an integration time | pre-12/7 | AB RIQ 2 | Added
2 | Typo in SR2 (NGS --> LGS) | pre-12/7 | AB RIC 2 | Corrected
3 | Would like to see more performance measurements coming out of NIR TTS if possible. In addition to Strehl, magnitude of tip-tilt stars and seeing disk (how broad is the uncorrected part of the PSF. FWHM might not be enough, if the strehl is very good. Maybe a two component gaussian fit) would be useful parameters to estimate how well one is doing & if one needs to adjust exposure times in real time. It could also be done off line, of course, every now and then if the images are saved. See also item 17 below. | pre-12/7 | TT RIQ 4 | Added to SR-30
4 | Component requirements flow down & interfaces | 2010-12-14 | SDR report | Requirements flowdown to systems in this spreadsheet. See also "WFE Budget" tab, and throughput & emissivity budget spreadsheet. Interfaces to RTC & camera addressed in KAONs 824 & 836. Keyword interfaces between all systems in KAON 857.
5 | Develop requirement 4: It would be useful to add words to define the measurement precision and accuracy needed for the Tip-Tilt guide star position under various operational conditions | 2010-12-14 | SDR report | Not able to do this for PDR. Needs more modeling. See "WFE Budget" tab.
6 | The motivations to use simultaneously the Near-Infrared Tip-Tilt Sensor and the existing STRAP system are not convincing. There are still some concerns about additional complexity. We recommend considering descoping this capability. | 2010-12-14 | SDR report | SR 12 changed to goal
7 | Consider descoping requirement 9 (only one Tip-Tilt Guide Star) | 2010-12-14 | SDR report | No change. Already a goal.
8 | Develop the operation concept document to better define the calibration, acquisition and dithering requirements including the software requirements | 2010-12-14 | SDR report | See OOCD document produced for PDR
9 | A requirement should be added that the Near-Infrared Tip-Tilt Sensor unit, cryogenics, CCR, coolant, mechanisms, electronics, etc, is serviceable while in position, or that the unit can be removed for service and re-installed without realignment | 2010-12-14 | SDR report | Inserted Camera 29 & OM 24
10 | The wavefront error budget requirements should flow down into subsystems requirements | 2010-12-14 | SDR report | See start on "WFE Budget" tab. See also throughput & emissivity budget spreadsheet.
11 | We support the team’s effort to make the design consistent with the future addition of a Tip-Tilt mirror. Such an option will reduce the risks associated with operating with under-sampled images | 2010-12-14 | SDR report | Inserted OM 8 & Controls 10 as goals
12 | It was noted during the review that the image quality, sensitivity, field of view, and other qualities of the camera would have significant capability for use as a science instrument. Since it’s possible to readout ROI’s on a H2RG at a high bandwidth for use in sensing tip/tilt correction while integrating on the rest of the chip (for example WIRCam on CFHT) this option should be considered for a possible upgrade project. See http://www.cfht.hawaii.edu/Instruments/Imaging/WIRCam/. | 2010-12-14 | SDR report | PW decision not to make this a goal or requirement
13 | Add a goal for rotator control from 3 stars | 2011-01-12 | CN | Inserted Controls 12 as a goal
14 | What do we want to continue to work in the absence of the TRS? Minimize dependence on TRS - see original MG requirement to operate in absence of TRS From Tsubota: It is possible to run the NGWFC without the TRS by modifying the startup script not to load the TRS logging application. | 2011-01-12 | CN | Inserted as SR-61
15 | Need definitions of dither, nod & offset (see SR-23) | 2011-01-12 | CN | Definitions added to SR-23, 24 & 25.
16 | Need definitions of initialize and startup (& how do you test?) From Tsubota: Initialize happens after startup. Startup includes powering up the the hardware and booting. Boot up loads the application and parameter files. Both soft & hard resets (re-boots) load the software. A hard reset also power cycles the hardware. Initialization includes items like homing devices. | 2011-01-12 | CN | Some clarification added to SR-19
17 | Make sure that real-time photometry is only a goal. Agreed to by Treu & Morris. | 2011-01-13 | PW | Related to item 3 above & will be addressed with it.
18 | Provide the ability to operate the NIR TTS with the high order NGS WFS in "dual NGS" mode to support development & testing. | 2011-01-17 | CN | Inserted as SR-32
19 | Requirement or goal for a fixed pupil mode with the GS off-axis? How close does it need to go to zenith? | 2011-01-24 | CN | Inserted SR-29 as a goal.
20 | Does the NIR camera need a dark slide or shutter? | 2011-01-24 | CN | RS feels at least needed for testing. Inserted Camera 8 as a goal.
21 | Close the LGS loops (UT & DM) before closing the DT loop when in NIR TTS mode | 2011-02-03 | CN | No change. This is an approach to achieving requirements & not a requirement
22 | Add a goal to Controls to use the RTC focus information to update the sodium altitude | 2011-02-24 | PW | Inserted Controls 11 as a goal
23 | Provide a ROI for measuring sky background. | 2011-03-08 | PW/CN | Added to SR-9 (a goal).
24 | Selected Ks filter for SDR to minimize thermal background | 2011-03-26 | RS/PW | Modified camera functional req 1 from K' to Ks
25 | Add "for one ROI" to camera req #5 | 2011-03-26 | RS | Done
26 | Change camera req 17 to reference KAON 836 for the available volume | 2011-03-26 | PW | Done
27 | Change camera req 18 from 10 kg to 50 kg and remove the TBC | 2011-03-26 | RS/PW | Done
28 | Remove TBD volume in SR-38 in favor of just leaving the requirement not to interfere with existing components. | 2011-03-26 | PW | Done
29 | Change NIR TTS mass limit from 30 kg to 70 kg due to the increase in camera mass from 10 kg to 50 kg in SR-39 | 2011-03-26 | PW | Done

## System - Overall
Flowdown to Major Subsystems
# | Overall Requirements | Compliance | # | Camera | O-M | RTC | Controls | Obs SW
1 | Provide a NIR TTS system for the Keck I LGS AO system and OSIRIS. | Yes | 1 | Yes | Yes | Yes | Yes | Yes
2 | The NIR TTS system shall be capable of operating as an integrated part of the Keck I LGS AO control system. | Yes | 2 | Yes | Yes | Yes | Yes | Yes
3 | When the NIR TTS system is not in use it shall allow the current science modes of the AO system and science instruments to be used with no reduction in performance. | Yes | 3 | Yes | Yes | Yes | Yes | Yes
4 | Provide improved tip-tilt correction and improved sky coverage for LGS AO science operations. Specifically, the NIR TTS system shall achieve the performance improvements predicted in Table 1 under the conditions indicated. The performance is allowed to degrade with respect to Table 1 as the conditions worsen. See "WFE Budget" tab. | Yes | 4 | Yes | Yes | Yes | Yes | Yes
5 | Goal: Provide TBD improved focus correction and reduce the overhead for focus measurements by TBD during LGS AO science operations. | No (future option) | 5 | Yes | Yes | Yes | No | No
6 | The NIR TTS system shall be operable, with performance consistent with system requirement #4, over a range of seeing conditions up to the 80th percentile seeing. The goal is 90th percentile seeing. | Yes | 6 | Yes | Yes | Yes | Yes | Yes
7 | The NIR TTS system shall be operable, with performance consistent with system requirement #4, over the telescope zenith angle range from 0.5° to 65°. | Yes | 7 | Yes | Yes | Yes | Yes | Yes
8 | The NIR TTS system shall come equipped with a means of identifying the location of tip-tilt stars on the camera. For example, the NIR TTS could have its own acquisition mode or the existing acquisition camera should be capable of adequately positioning stars on the NIR TTS. | Yes | 8 | Yes | n/a | n/a | Yes | Yes
9 | Goal: The NIR TTS system shall be capable of using up to three tip-tilt stars as input to the real-time controller tip-tilt determination, plus a single readout area for sky background measurements. | Yes | 9 | Yes | n/a | Yes | Yes | Yes
10 | The NIR TTS system shall be capable of using non-point sources £ 0.1" in diameter, with performance consistent with system requirement #4. | Yes | 10 | Yes | n/a | Yes | n/a | Yes
11 | Goal: The NIR TTS system shall be capable of using non-point sources £ 1" in diameter, with performance consistent with system requirement #4. | 0.8" max | 11 | Yes | n/a | 0.8" max | n/a | Yes
12 | Goal: The NIR TTS system shall be capable of operating in parallel with the existing visible TTS (STRAP) for improved tip-tilt correction. Both sets of data shall be capable of being used together by the real-time controller to calculate the tip-tilt to be applied to the tip-tilt mirror. | No (future option) | 12 | n/a | n/a | Yes | Yes | No
13 | The NIR TTS system shall be capable of using stars as faint as K = 16 mag over its entire field of view. | Yes | 13 | Yes | Yes | Yes | n/a | Yes
14 | The NIR TTS system shall be capable of using stars as faint as H = 16 mag over its entire field of view. | Yes | 14 | Yes | Yes | Yes | n/a | Yes
15 | When the NIR TTS system is used the science field of view of interest shall be unvignetted. Depending on the science case the science field of view of interest may include just the OSIRIS IFU or both the IFU and imager. Options shall be provided to allow both the IFU and imager fields of view to be passed when the NIR TTS is operated in H or K-band. | Yes | 15 | Yes | Yes | n/a | n/a | n/a
16 | The NIR TTS shall be positioned to be parfocal with the science instrument focal plane. This will require that the NIR TTS be able to refocus for different observing modes. | Yes | 16 | Yes | Yes | Yes | Yes | Yes
17 | The time required for any routine daytime calibrations of the NIR TTS system shall not exceed 20 minutes. | DD | 17 | Yes | Yes | Yes | Yes | DD
18 | The time required for any routine nighttime start of night calibrations of the NIR TTS system shall not exceed 10 minutes. | DD | 18 | Yes | Yes | Yes | Yes | DD
19 | The time required to initialize (assumes power up and loading of software has been performed as part of startup) the NIR TTS system shall not exceed 10 minutes. This initialization refers to the associated computer systems, software and motion control devices. The NIR TTS camera is assumed to be at operating temperature. | DD | 19 | DD | Yes | Yes | Yes | DD
20 | The NIR TTS system shall not increase the typical LGS AO acquisition time by more than 15 seconds. | DD | 20 | Yes | Yes | Yes | Yes | Yes
21 | Other than acquisition time, the NIR TTS system shall not reduce the observing efficiency of the current LGS AO system. Observing efficiency includes the time to perform such tasks as nodding, dithering and offsetting. | Yes | 21 | Yes | Yes | Yes | Yes | Yes
22 | The NIR TTS system shall support differential atmospheric refraction corrections between the TTS and the science instrument for a £ 20 minute science exposure for zenith angles £ 60°, with performance consistent with system requirement #4. | Yes | 22 | Yes | n/a | Yes | Yes | Yes
23 | The NIR TTS system shall support normal science observing modes such as dithering, nodding and offsetting. Definitions: 1) Micro-dithering is performed to finely position a science object on the science detector. 2) Dithering is performed to move a science object around the science detector. 3) Offsetting is performed to mosaic an image, to obtain a measurement of the sky background, or to perform a blind offset from a reference star to the science target when the science target is not visible on the detector. Nodding is considered to be the same as offsetting. The amplitudes and accuracy of these moves are defined in SR-24 and SR-25. | Yes | 23 | Yes | n/a | Yes | Yes | Yes
24 | The NIR TTS system shall be able to position an object on the science instrument to an accuracy of £ 120 mas (3-sigma) for moves £ 60 arcsec (i.e., an offset or nod) and £ 70 mas for moves £ 5 arcsec (i.e., a dither), assuming the tip-tilt star stays within the NIR TTS field of view. | Yes | 24 | Yes | Yes | Yes | Yes | Yes
25 | The NIR TTS system shall be able to reposition an object on the science instrument to a relative accuracy of £ 5 mas for moves £ 20 mas (i.e., a micro dither), assuming the NIR TTS system tip-tilt loop was already closed. | Yes | 25 | Yes | Yes | Yes | Yes | Yes
26 | The stability of the NIR TTS with respect to the AO bench shall be £ 5 mas over a 1 hour exposure, assuming a temperature change of £ 1° C. | DD | 26 | DD | DD | Yes | Yes | n/a
27 | The NIR TTS system shall be able to reposition an object on the science instrument to £ 10 mas after an intermediate move of £ 10 arcsec, in support of dithering. | Yes | 27 | Yes | Yes | Yes | Yes | n/a
28 | The NIR TTS system is not expected to support non-sidereal tracking; this mode will continue to be supported by STRAP. As a goal, the NIR TTS system shall be able to maintain the position of a non-sidereal object on the science instrument to £ 5 mas for a non-sidereal object with a deviation rate of 50 arcseconds per hour or less, assuming the tip-tilt star stays within the NIR TTS field of view. | No (future option) | 28 | Yes | n/a | Yes | Yes | No
29 | As a goal the NIR TTS shall support fixed pupil mode. In this mode the NIR TTS shall be able to maintain the position of science object on the science instrument to £ 5 mas for an off-axis tip-tilt star that remains on the NIR TTS throughout the observation. This mode need only be supported during meridian transiting ³ 5° (TBC) from the zenith. | No (future option) | 29 | Yes | Yes | Yes | Yes | No
30 | As a goal the NIR TTS should provide some measure of performance. Desired quantities include a Strehl measurement and a measure of the seeing disk profile (a two component Gaussian fit has been suggested) plus a relative photometry measurement for each tip-tilt star. | Yes | 30 | n/a | n/a | Yes | n/a | Yes
31 | The NIR TTS system shall meet all of its performance requirements in the operating environment conditions given in Table 2. | Yes | 31 | Yes | Yes | Yes | Yes | n/a
32 | Provide the ability to operate the NIR TTS with the high order NGS WFS in "dual NGS" mode to support development & testing. | Yes | 32 | Yes | Yes | Yes | Yes | Yes

## System - Other
Flowdown to Major Subsystems
# | Optical Requirements | Compliance | # | Camera | O-M | RTC | Controls | Obs SW
33 | The unvignetted field of view of the NIR TTS shall be at least a 100" diameter circle with a goal of a 120" diameter circle. | Yes | 33 | Yes | Yes | n/a | n/a | n/a
34 | The operational wavelengths of the NIR TTS shall be the short wavelength end of K-band (e.g. Ks or K') and H-band. Only one of these bands will be used at any given time. | Yes | 34 | Yes | Yes | n/a | Yes | Yes
35 | When the NIR TTS system is used the transmission in the science wavelength shall not be reduced by more than 5%. The goal is 3%. | DD | 35 | Yes | Yes | n/a | n/a | n/a
36 | When the NIR TTS system is used the emissivity in the science wavelength shall not be increased by more than 5% averaged over the science band. The goal is 3%. | DD | 36 | Yes | Yes | n/a | n/a | n/a
Mechanical Requirements
37 | The NIR TTS system shall not introduce vibrations into the LGS AO system that would impact science performance. This requirement is already covered by requirement 4 but is included here to draw specific attention to the importance of minimizing vibrations. | DD | 37 | Yes | Yes | Yes | Yes | n/a
38 | The NIR TTS system shall not mechanically interfere with the components already on the AO bench, unless these components can be and are appropriately modified to support the integration of the NIR TTS system. | Yes | 38 | Yes | Yes | n/a | Yes | n/a
39 | The NIR TTS system mounted on the AO bench shall not exceed a total mass of 70 kg (TBC). | DD | 39 | Yes | Yes | n/a | Yes | n/a
40 | The associated NIR TTS system equipment not on the AO bench shall not exceed a TBD envelope. | DD | 40 | Yes | Yes | Yes | Yes | n/a
Electronic/Electrical Requirements
41 | The NIR TTS system shall use less than or equal to TBD of electrical power. | DD | 41 | DD | Yes | Yes | Yes | n/a
42 | The NIR TTS system on the AO bench shall not exceed a one-hour average heat dissipation of 5 Watts into the AO bench environment. | DD | 42 | DD | DD | n/a | Yes | n/a
43 | The associated NIR TTS system equipment not on the AO bench shall not exceed a one-hour average heat dissipation of 10 Watts into the AO clean room. | DD | 43 | DD | Yes | n/a | Yes | n/a
44 | If practical the NIR TTS system electronics shall be located in a rack in the AO electronics room and cables must be of appropriate length to reach these locations. If cable lengths are required to be shorter, then the cables shall be at least long enough to allow placing this equipment outside of the enclosure directly around the AO bench. | DD | 44 | DD | Yes | n/a | Yes | n/a
Safety Requirements
45 | The NIR TTS system shall be able to withstand the acceleration profile (to be provided) without damage or severe misalignment. Restraints should be provided to prevent hardware from damaging itself or other hardware during an earthquake. | DD | 45 | Yes | Yes | Yes | Yes | n/a
Software Requirements
46 | The NIR TTS system shall provide the needed operational tools to support its daytime calibration. | Yes | 46 | Yes | Yes | Yes | Yes | Yes
47 | The NIR TTS system shall provide the needed tools to support science observation planning. | Yes | 47 | n/a | n/a | n/a | n/a | Yes
48 | The NIR TTS system shall provide the needed operational tools to support nighttime science operations. | Yes | 48 | Yes | Yes | Yes | Yes | Yes
Interface / Logging Requirements
49 | The NIR TTS system must support an interface to the Observatory standard KTL keywords. For example, command and status communications between the NIR TTS camera system and the optics bench, supervisory controller and operations software shall be via keywords. | Yes | 49 | Yes | n/a | n/a | Yes | Yes
50 | All telemetry from the NIR TTS shall be provided to the existing telemetry server. | Yes | 50 | Yes | n/a | Yes | Yes | Yes
51 | The NIR TTS system shall be capable of saving images in FITS format. | Yes | 51 | Yes | n/a | n/a | n/a | n/a
Spares Requirements
52 | The spare NGWFC electronics hardware setup currently available in WMKO HQ shall be updated to match the final hardware configuration that will be designed for the NIR TTS project. | Yes | 52 | n/a | n/a | Yes | n/a | n/a
Reliability Requirements
53 | The NIR TTS system shall meet all of its performance requirements without repair after shipment to Keck headquarters and to the telescope. | Yes | 53 | Yes | Yes | Yes | Yes | n/a
54 | The NIR TTS system shall have a lifetime of ³ 10 years. | Yes | 54 | Yes | Yes | Yes | Yes | Yes
55 | The NIR TTS system shall be capable of operating on ³ 200 nights per year. | DD | 55 | Yes | Yes | Yes | Yes | Yes
56 | The NIR TTS system shall lose no more than 5% of its total observing time to faults. | DD | 56 | Yes | Yes | Yes | Yes | DD
57 | The NIR TTS system shall have a median time between faults that result in ³ 10 minutes of lost observing time, of ³ 10 nights of operation. | DD | 57 | Yes | Yes | Yes | Yes | DD
58 | The time to restart the NIR TTS system shall not exceed 10 minutes. | DD | 58 | Yes | Yes | Yes | Yes | DD
59 | The NIR TTS system shall meet all of its performance requirements without repair or realignment after being subjected to any number of cycles of any of the non-operating environmental conditions shown in Table 3. | DD | 59 | Yes | Yes | Yes | Yes | Yes
60 | The NIR TTS system shall be able to withstand a total and sudden loss of electrical power or a transient power event, without suffering damage. | DD | 60 | Yes | Yes | Yes | Yes | Yes
61 | The NIR TTS system shall be able to operate without telemetry logging in the event that the Telemetry Recorder System (TRS) is non-operational. | DD | 61 | Yes | n/a | Yes | Yes | DD
Service and Maintenance Requirements
62 | AO system unavailability or downtime to install and integrate the NIR TTS system shall not exceed 2 weeks. | DD | 62 | Yes | Yes | Yes | Yes | Yes
63 | Routine maintenance on the NIR TTS shall not require more than 1 technician for 4 hours every 4 months. | DD | 63 | Yes | Yes | Yes | Yes | DD
Documentation Requirements
64 | The NIR TTS system shall be provided with the documentation required to understand and document its as-built design, and to maintain and operate it. | Yes | 64 | Yes | Yes | Yes | Yes | Yes
65 | The NIR TTS system shall be provided with the documentation required to support science operations planning. This should include at least 3 months of performance characterization data after the system has begun being used for shared-risk science. | Yes | 65 | n/a | n/a | n/a | n/a | Yes
66 | Goal: The NIR TTS system shall be provided with a performance estimation tool for both pre-observing planning and observing. This would be even more useful with a PSF simulator attached to it. | Yes | 66 | n/a | n/a | Yes | n/a | Yes
67 | The NIR TTS system shall successfully complete a handover review, with TBD success criteria, before being transferred to the responsibility of the AO operations group. | Yes | 67 | Yes | Yes | Yes | Yes | Yes
Configuration Management Requirements
68 | All code changes and documentation updates shall be managed according to existing WMKO configuration management practices. | Yes | 68 | Yes | n/a | Yes | Yes | Yes
69 | All software releases on the operational system shall be revertible to an on-sky demonstrated software release within 15 (TBC) minutes. | DD | 69 | n/a | n/a | Yes | Yes | Yes
70 | The NIR TTS system shall receive approval from the AO configuration control board prior to implementation into the Keck I LGS AO system. | Yes | 70 | Yes | Yes | Yes | Yes | Yes

## Functional - Camera
# | Overall Requirements | Flowdown | Compliance
1 | The camera system shall include a cryogenic dewar containing reimaging optics, a filter changer mechanism with H and K' filters and motion control, and an H2RG detector; the camera control electronics and host computer, and the associated cryo and vacuum systems. | SR-1 | Yes
2 | The camera system shall interface to the opto-mechanical system as defined in KAON 836. | SR-1,2,38 | Yes
3 | The camera system shall interface to the controls and observing software systems as defined in KAON 836. | SR-1,2 | Yes
4 | The camera system shall interface to the Microgate RTC system as defined in KAON 824. | SR-1,2,9 | Yes
5 | The camera system shall deliver a read + dark noise of < 5 electrons total for one region of interest up to 4x4 sampling at 1 kHz. | SR-4 | Yes
6 | The camera shall have a full frame readout mode that writes images in FITS format. As a goal the images should also be available in binary format via API. | SR-8 | Yes
7 | The camera shall provide H and Ks filters and a remote means of switching between these two filters. | SR-13,14 | Yes
8 | Goal: The camera shall provide a blocked position to allow dark measurements. | SR-46 | Yes
9 | The time to read out a full frame image shall be £ 5 sec. | SR-8,20 | Yes
10 | The time required to initialize the camera system shall not exceed 5 minutes. | SR-19 | DD
Optical Requirements
11 | The camera shall have a plate scale of 50 mas/pixel. | SR-4 | Yes
12 | The camera system shall have a wavefront quality £ TBD nm rms. | SR-4 | DD
13 | The camera system shall have a throughput of ³ TBD % including the detector QE at Ks. | SR-13 | DD
14 | The camera system shall have a throughput of ³ TBD % including the detector QE at H. | SR-14 | DD
15 | Optical distortions within the camera system shall be £ 10 mas for any two points separated by £ 60". | SR-24,25 | DD
Mechanical Requirements
16 | The stability of the camera system with respect to its mounting surface shall be £ 3 mas over a 1 hour exposure, assuming a temperature change of £ 1° C. | SR-26 | DD
17 | The camera system shall mount to the AO bench within an envelope defined in the camera ICD (KAON 836). The camera system shall not mechanically interfere with the components already on the AO bench, unless these components can be and are appropriately modified to support the integration of the NIR TTS system. | SR-38 | Yes
18 | The camera system mounted on the AO bench shall not exceed a total mass of 50 kg. | SR-39 | DD
19 | The associated camera system equipment not on the AO bench shall not exceed a TBD envelope. | SR-40 | DD
Electronic/Electrical Requirements
20 | Each opto-mechanical stage shall be provided with an appropriate servo motor and encoder to ensure that the positioning requirements can be met. The filter exchanger positioning requirement is £ 1 mm. | SR-1,2,4 | Yes
21 | The camera system shall use less than or equal to TBD of electrical power, in excess of the current system. | SR-41 | DD
22 | The camera system on the AO bench shall not exceed a heat dissipation of 3 Watts into the AO bench environment. | SR-42 | DD
23 | The associated camera system equipment not on the AO bench shall not exceed a heat dissipation of 7 Watts into the AO clean room. | SR-43 | DD
24 | The associated camera system equipment not on the AO bench shall be capable of being placed at least TBD m from the NIR TTS system location on the AO bench. | SR-44 | DD
Reliability Requirements
25 | The camera system shall lose no more than 3% of its total observing time to faults. | SR-56 | DD
26 | The camera system shall have a median time between faults of ³ 20 nights of operation. | SR-57 | DD
27 | The time to restart the camera system in the event of a fault shall not exceed 5 minutes. | SR-58 | DD
Service and Maintenance Requirements
28 | Routine maintenance on the camera system shall not require more than 1 technician for 2 hours every 4 months. | SR-63 | DD
29 | The camera shall be operable in a stand-alone mode to support both development and diagnostics once installed | SR-63 | Yes
30 | The camera hardware shall be serviceable while in position or shall be removable for service such that no realignment is required after reinstallation. | SR-63 | Yes
Documentation Requirements
31 | Procedures must be provided for any required calibrations. | SR-17,18 | DD

## Functional - OM
# | Overall Requirements | Flowdown | Compliance
1 | The opto-mechanical system shall include a the opto-mechanics to fold the beam to the NIR TTS camera, the opto-mechanics for the NIR TTS that are outside of the camera dewar and any associated motors and encoders, as well as any required modifications to the AO bench to support this hardware. | SR-1 | Yes
2 | The opto-mechanical system shall provide an interface plate to mount the camera as defined in KAON 836. | SR-1,2 | Yes
3 | Each opto-mechanical stage shall interface to the controls via a TBD connector. | SR-1,2 | Yes
4 | The opto-mechanical system shall provide a means of sending H or K'-band light to the camera system while transmitting the other science bands to OSIRIS. Two options are required: an H-band reflective dichroic and a K-band reflective dichroic. A goal is to leave a position for a future annular mirror that will transmit the IFU science field. | SR-15 | Yes
5 | The opto-mechanical system shall provide a focus stage. | SR-16 | Yes
6 | The time to re-position a stage via the control system shall not exceed 10 seconds. | SR-17,18,20,21 | Yes
7 | The time required to initialize the opto-mechanical system via the control system shall not exceed 5 minutes. | SR-19 | Yes
8 | Goal: The fold mirror shall be replaceable with a tip-tilt mirror used to maintain a star image at the center of a ROI (to correct small offsets, <~25 mas, & DAR without producing a significant impact on the pupil position). | SR-5,22,25,27 | Goal
Optical Requirements
9 | The opto-mechanical system shall have a wavefront quality £ TBD nm rms to the camera system. | SR-4 | DD
10 | The opto-mechanical system shall have a wavefront quality £ TBD nm rms to OSIRIS. | SR-4 | DD
11 | The opto-mechanical system shall have a throughput of ³ TBD % at K' to the camera system. | SR-13 | DD
12 | The opto-mechanical system shall have a throughput of ³ TBD % at H to the camera system. | SR-14 | DD
13 | Optical distortions within the opto-mechanical system shall be £ 10 mas for any two points separated by £ 60". | SR-24,25 | DD
Mechanical Requirements
14 | The reflected beam off each fold optic must be co-linear and repeatable to the following tolerances: the image shift shall be £ 0.1" and the pupil shift shall be £ 5% of the full pupil. The goal is ¼ of these numbers. | SR-21 | DD
15 | The stability of the output optical beam shall be £ 3 mas over a 1 hour exposure. | SR-26 | DD
16 | The opto-mechanical system shall mount to the AO bench within a TBD envelope. The opto-mechanical system shall not mechanically interfere with the components already on the AO bench, unless these components can be and are appropriately modified to support the integration of the NIR TTS system. Any required modifications are the responsibility of the opto-mechanical system. | SR-38 | Yes
17 | The opto-mechanical system mounted on the AO bench shall not exceed a total mass of 10 kg (TBC). | SR-39 | No
Electronic/Electrical Requirements
17 | Each opto-mechanical stage shall be provided with an appropriate servo motor and encoder to ensure that the positioning requirements can be met. The dichroic exchanger positioning requirement is £ 1 mm. The focus stage positioning requirement is £ 0.05 mm. | SR-1,2,4 | Yes
18 | The opto-mechanical system shall use less than or equal to TBD of electrical power, in excess of the current system. | SR-41 | DD
19 | The opto-mechanical system on the AO bench shall not exceed a heat dissipation of 2 Watts into the AO bench environment. | SR-42 | Yes
Reliability Requirements
20 | The opto-mechanical system shall lose no more than 1% of its total observing time to faults. | SR-56 | Yes
21 | The opto-mechanical system shall have a median time between faults of ³ 100 nights of operation. | SR-57 | DD
22 | The time to restart the opto-mechanical system in the event of a fault shall not exceed 5 minutes. | SR-58 | Yes
Service and Maintenance Requirements
23 | Routine maintenance on the opto-mechanical system shall not require more than 1 technician for 2 hours every 12 months. | SR-63 | Yes
24 | The camera hardware shall be serviceable while in position or shall be removable for service such that no realignment is required after reinstallation. | SR-63 | Yes

## Functional - Controls
# | Overall Requirements | Flowdown | Compliance
1 | The controls system shall include the motion control required for the opto-mechanical system, the device control required for the camera system and real-time control system, and any other software residing at the optics bench (OBS) or supervisory control (SC) level. This subsystem shall include any required modifications to the AO electronics to support this functionality. | SR-1 | Yes
2 | The opto-mechanical system stages shall interface to the controls via a TBD connector. | SR-1,2 | Yes
3 | The controls shall interface to the camera system as defined in KAON 836. | SR-1,2 | Yes
4 | The controls system shall position the opto-mechanical focus stage to be conjugate to the science instrument focal plane. | SR-16 | Yes
5 | The time to re-position a camera system or opto-mechanical system stage via the control system shall not exceed 10 seconds. | SR-17,18,20,21 | Yes
6 | The time required to initialize the opto-mechanical or camera systems via the control system shall not exceed 5 minutes. | SR-19 | Yes
7 | The controls shall support differential atmospheric refraction corrections between the TTS and the science instrument. | SR-22 | Yes
8 | The controls shall support normal science observing modes such as dithering, nodding and offsetting. | SR-23 | Yes
9 | Potential goal only: the controls system shall support non-sidereal tracking. | SR-28 | Goal
10 | Goal: The controls system shall be able to support a tip-tilt mirror used to maintain a star image at the center of a ROI. | SR-4,22,25,27 | Goal
11 | Goal: The controls system shall be able to use focus information from the RTC to update the sodium altitude information, instead of or in addition to LBWFS focus information. | SR-5 | Goal
12 | Goal: The controls system shall be able to use the tip-tilt information from 3 stars to compute and correct the rotation error in the AO rotator. | SR-9 | Goal
Software Requirements
13 | The controls system shall provide the needed operational tools to support its daytime calibration. | SR-46 | Yes
14 | The controls system shall provide the needed operational tools to support nighttime science operations. | SR-47 | Yes
Reliability Requirements
15 | The controls system shall lose no more than 2% of its total observing time to faults. | SR-56 | Yes
16 | The NIR TTS shall have a median time between faults of ³ 30 nights of operation. | SR-57 | DD
17 | The time to restart the controls system in the event of a fault shall not exceed 5 minutes. | SR-58 | Yes
Service and Maintenance Requirements
18 | Routine maintenance on the controls system shall not require more than 1 technician for 4 hours every 8 months. | SR-63 | Yes

## Functional - Obs SW
# | Overall Requirements | Flowdown | Compliance | Comments
1 | The observing software system shall provide the high-level software to plan science observations, prepare the system for observations and to carry out the observations. | SR-1 | Yes
2 | The observing software system shall interface to the camera, real-time control and controls systems via ethernet using keywords. | SR-1,2,49 | Yes
3 | The observing software system shall identify the location of tip-tilt stars on the camera. | SR-8 | Yes
4 | Goal: The NIR TTS system shall coordinate operating in parallel with the existing visible TTS (STRAP) for improved tip-tilt correction. | SR-12 | Yes
5 | The time required to initialize the observing software system shall not exceed 3 minutes. | SR-19 | DD | Its certainly not designed to take longer but no data or protype software to verify this statement
6 | The observing software system shall support normal science observing modes such as dithering, nodding and offsetting. | SR-23 | Yes
7 | As a goal the observing software should provide some measure of performance (for example, a Strehl measurement). | SR-30 | Yes
Software Requirements
8 | The observing software system shall provide the needed operational tools to support its daytime calibration. | SR-46 | Yes
9 | The observing software system shall provide the needed tools to support science observation planning. | SR-47 | Yes
10 | The observing software system shall provide the needed operational tools to support nighttime science operations. | SR-48 | Yes
Interface / Logging Requirements
11 | The observing software system shall be capable of retrieving telemetry from the telemetry server. | SR-30,50 | Yes
12 | The NIR TTS system shall be capable of saving images in FITS format. | SR-8,51 | Yes
Reliability Requirements
13 | The observing software system shall lose no more than 2% of its total observing time to faults. | SR-56 | DD | Full failure study could be done during DD, but we don't have the resources
14 | The observing software system shall have a median time between faults of ³ 30 nights of operation. | SR-57 | DD | Full failure study could be done during DD, but we don't have the resources
15 | The time to restart the observing software system in the event of a fault shall not exceed 5 minutes. | SR-58 | DD | Full failure study could be done during DD, but we don't have the resources
Service and Maintenance Requirements
16 | Routine maintenance on the observing software system shall not require more than 1 software engineer for 4 hours every 12 months. | SR-63 | DD | Maintenance is minimal for Lchock other than testing new releases which must take longer than 4h/yr assuming releases every 6 months.
Documentation Requirements
17 | Goal: The observing software system shall provided a performance estimation tool. This would be even more useful with a PSF simulator attached to it. | SR-66 | Yes

## Functional - RTC
The Real-Time Control (RTC) functional requirements are defined in KAON 824.

## WFE Budget
Error Term (nm) | High-Redshift Galaxies (r0 = 14.7 cm @ 30° zenith angle; wind 9.5 m/s)
| K2 2009 | K1 2010 | K1 2013 (w/ new TTS)
Atmospheric Fitting | 126 | 126 | 126 |  |  | Atmospheric Fitting | 126 | Not TT dependent
Telescope Fitting | 66 | 66 | 66 |  |  | Telescope Fitting | 66 | Not TT dependent
Science Camera | 30 | 30 | 30 |  |  | Science Camera | 30 | Not TT dependent
DM Bandwidth | 108 | 55 | 55 |  |  | DM Bandwidth | 55 | Not TT dependent
DM Measurement | 146 | 71 | 71 |  |  | DM Measurement | 71 | Not TT dependent
Tip-tilt Bandwidth | 145 | 145 | 89 |  |  | Tip-tilt Bandwidth | 89 | Camera Integration Time
Tip-tilt Measurement | 191 | 192 | 95 |  |  |  |  | Camera Readout & Transfer Time
Tip-tilt Anisoplanatism | 190 | 190 | 111 | Total WFE | 328.8343 |  |  | RTC Processing & Command Time
LGS Focus Error | 34 | 34 | 34 |  |  | Tip-tilt Measurement | 95 | SNR (see SNR spreadsheet)
Focal Anisoplanatism | 187 | 187 | 187 |  |  |  |  | Algorithm Performance
LGS High Order Error | 50 | 50 | 50 |  |  | Tip-tilt Anisoplanatism | 111 | TT number
Calibration Errors | 29 | 29 | 29 |  |  |  |  | TT locations
Miscellaneous | 90 | 36 | 101 |  |  |  |  | Integration Time
Total Wavefront Error | 441.9095 | 404.9062 | 328.8343 |  |  | LGS Focus Error | 34 | Not TT dependent
Science Wavelength | 2200 |  |  |  |  | Focal Anisoplanatism | 187 | Not TT dependent
Strehl Ratio | 20.33% | 26.26% | 41.4% |  |  | LGS High Order Error | 50 | Not TT dependent
Ensquared Energy (50 mas) | 18% | 23% | 32% |  |  | Calibration Errors | 29 | NIR Camera Calibrations
[6 empty] | Miscellaneous | 101 | Opto-mech Stability
Table 1: Keck LGS AO wavefront error budgets (in nm rms) as performance is improved: 2009 Keck II LGS AO system, predicted Keck I LGS AO system with the new laser in 2011, and the Keck I LGS AO system with a NIR TTS. The high redshift galaxies science case is assumed including 30% sky coverage, 60° galactic latitude, 30° zenith angle, median seeing conditions and an 1800 sec science integration. | [7 empty] | Camera Stability
Differential Atmospheric Refraction
High Order WFE (45 nm)
[6 empty] | Contingency | 0 | Remainder