## Sheet1
| NGAO Real-Time Controller subsystem - action item tracking list |  |  |  | 2010-02-22
Item number | Short name | Description | Status | Source | Plan | Predicted completion | Comments / Questions
1 | Revise requirements | Update many of the requirements to fill in the TBDs. Remove redundant or irrelevant (e.g. pertaining to pre BTC) requirements. Add requirements suggested by reviewers, particularly Peter. | done | mostly Peter W in "Wizinowich_Requirements.doc" | Send new list to SysEng team | done
2 | Re-evaluate bandwidth / latency requirement | Re-evaluate the bandwidth error term versus latency and revise requirement to allow a more conservative buffer. | KAON 710 posted. | Peter W. in "Wizinowich_Requirements.doc" |  | done
3 | FPGA vs GPU for tomography | Document the issues involved with the choice of using FPGAs instead of GPUs for the tomography engine | Memo written, need to post | Reviewer Tuan Truong comments 1 and 2 |  | done
4 | Clean up algorithm diagrams in the design document | Produce computer-drawn versions of the figures that are now photographs of hand drawings | in progress | general |  | 2010-03-15
5 | Parameter generation algorithms | Produce a description of the algorithms needed to produce the input parameters for the RTC given seeing conditions | in progress | Boyer comment on FR1438 | Gavel to add a chapter to the Alg Doc to describe the calculations needed to compute RTC paramters. Document that the calculation task is to be done by the supervisory control computer and must be part of the supervisory control to RTC interface definition. | 2010-04-15
6 | Document numerical accuracy | Provide calculations that support the choice of fixed word length | done, needs to be posted | Boyer |  | 2010-02-28
7 | Point and shoot HOWFS algorithm | Add section to design document specific to the P&S HOWFS as distinguished from tomography HOWFS | in progress | Peter W.