Keck Next Generation Adaptive Optics

Notes on costing

Revision 1

Don Gavel, 9/5/2007

# Phases

- Design means up to drawings and vendor specs.

- Implementation means component purchasing and manpower to implement.

- Fabrication means cost of in-house or vendor fabrication. In-house means at either the Keck, Lick, or Palomar shops.

- Hardware means purchase cost of either custom or off-the-shelf components from an outside vendor.

# Labor costs computation

We are no longer taking the approach of taking procurement costs and multiplying by 2 as was done at the architecture retreat. Instead, labor estimates are made considering 1) costs of implementing individual pieces of hardware, where appropriate, plus 2) costs of in-house design and fabrication effort needed to assemble each of the subsystems.

# Subsystems are:

- AO enclosure including temperature, dust, and humidity control, just for optics (i.e. not for electronincs), and mounting to the Nasmyth platform

  - Enclosure costs for large system is more than for small systems (e.g. MEMS). We used $400K for Indian Wells enclosure at -40 degrees C. Based on David Law’s curves we may need from -5 to -20 decrees C depending on throughput, but never lower than -20. We’ll assume no savings for small systems because of uncertainties in enclosing the instruments and cost/benefit trades of windows.

- Support structure – optics bench and cover. $40K assumed + 2mm of design + 2 mm of implementation. We assume <$10K for K1 upgrade option.

- Electronics enclosure – Includes cooling. Need to assume rebuild because of extra electronics needed for tomography.

- First and second optical relays of the cascaded relay architecture.

  - In the case of the K1 upgrade

    - recoat OAPs and other optics to increase throughput $5K.

    - K mirror replacement for 3 arcminute FOV. $300K + 8mm per Peter

    - OAP and mounts replacement if needed for 3 arcmin FOV. Including other mount customizing to avoid clipping, flip mechanism for Wyko pickoff. $65K

    - 589 dichroic if needed for FOV, $20K. Cost of just dichroic, see “optical switchyard” below for mounts and stages.

    - IR dichroics. 2 at $20K=$40K for big dichroics, $5K each for small dichroics x 2=$10K. Cost of just dichroic, see “optical switchyard” below for mounts and stages.

- ADC

- High order wavefront sensors –

  - LGS WFS radial CCD, small tip/tilt mirror, no DM

  - NGS WFS LL 256x256, scale CCD39 40x40 at $40K

  - assume $250K camera + $20K custom lenslet + $10K optics + $5K mounts = $285K per channel

  - Motion stages for WFS – 2 Z-axis degrees of freedom per channel $40K per channel. Possibly 3 more automated “set and forget” stages for alignment.

- Low order wavefront sensors

  - IR detector and dewar, and a small tip/tilt mirror

  - if not correcting TT star with dedicated beacon, may need to use Hartmann sensor instead of pyramid for the TTFA channel. Not a significant cost difference

  - Cost assumption: Picnic chip 256x256 $65K + $20K Leach? board + fibers, connectors + dewar $20K + $20K temp control = $140K per channel + 3mm 1st channel + 1mm each additional channel – tip/tilt only per channel

  - Cost assumption for TTFA: add $20K for custom lenslet. Needs a TT mirror for align beam on apex and/or modulate

- PSF imager

  - R camera $65K + $20K Leach board + $10K Optics + $20K dewar=$100K + 3mm testing and implementation

- Optical relays for dNIRI

  - AO relay $15K per channel (Brian’s refractive design)

  - Kick-bots and other pickoff mechanisms

  - K1 upgrade will need extra design work and possibly optics to fit it into the elevation journal. 2 mm? K1 upgrade will likely need a flat turning mirror(s?) and a relay lens to fit in without upsetting the K mirror. $30K+$15K

- Truth WFS – not well defined yet. Is this the TTFA sensor (in which case it’s one of the LOWFS)? Assume 8x8 subaps visible using CCD39 $40K + stock lenslets and mounts $10K + 2mm designing and testing. + labor

- TT Acquisition camera

  - wide field IR camera, no AO

  - includes dewar and readout electronics

  - Mounting on K1 upgrade is a little bit more complicated. Needs to be in Elevation bearing. All will need flip-in diagonal mirror.

  - Large array Hawaii 2RG $400K + $20K dewar + optics? + 3 mm testing and development

- LGS Acquisition camera – not well defined yet. Possibly a wide field CCD with astrometry good enough for handoff to LGS WFS $20K.

- Optical switchyard – mirrors and switching mechanisms. Assumes flat mirrors, stages and mounts $10K

- Telescope simulator – multiple fiber sources, mechanism for insertion, aberration simulator, optics to form pupil

- Electronics – includes hardware purchasing, assembly, and people time for software development and subsystem testing.

  - Real-time

    - WFS electronics and interfaces

    - DM electronics and interfaces

    - TTM electronics and interfaces

    - RTC – Just the computer – See costing model below. Probably <$500K and not a differentiator for architecture.

Identify differences based on architecture. I.e. if pointing to TTStars with 3 separate LGS closed loop systems and doing tomography on 6 LGS is different then one big 9 LGS tomography system. Is there an extra cost to do pseudo-open-loop control (closed loop control) vs straight open loop control. (These are probably subtle effects on cost)

Erik says $1.5M

    - Telescope interfaces. – Offloads to tracking, focus, and figure.

    - Electronics racks and support (e.g. cooling, electrical breakout, cables)

    - including centroiding, non-linear compensation, tomography, and DM control with open-loop non-linearity compensation:

  - Non-real-time

    - Motion controllers – means electronics and computer to control the AC power, moving stages, encoding and limits, encoders, software drivers, and software user-interface to all this.

    - Calibration support (e.g. taking data to help with diagnosing alignment and calibrating WFS and DMs)

    - camera control for PSF camera, acquisition camera

    - Monitoring – video camera, humidity monitor, temp monitors

    - Racks

    - Servers – to hold the diagnostic data

- Laser system

  - Laser – lasers cost $100K/watt

  - Laser enclosure

  - Laser beam transport

    - Fiber cost $200K for 5 fibers 25 meters

  - Pointing and diagnostics $600K total, not a discriminator

    - Fixed asterisms

    - Movable asterisms

    - Uplink tip/tilt $10K per beacon

    - Field rotation $10K

  - Launch telescope

    - 50cm costs $750K + 3mm design + 12mm implement

  - Laser safety and laser traffic control $75K + 4.5mm design + 9mm implement

- Alignment and diagnostics tools

  - Interferometers for measuring DM(s)

- Operations tools 2.3 FTE design and 6.7 FTE implementation

  - Observing setup

  - Astronomer planning tools

  - User Interface to AO system

  - DCS and science instrument interface - e.g creating FITS headers and communicating to science camera

  - Documentation

- Telescope I&T – differentiate cost of building and testing whole system in Lab one time vs incremental upgrades to current AO system

# Other assumptions about components

- Deformable Mirrors – includes D/A and amplifier electronics

  - In science path

    - 20x20 piezo at 7 mm pitch – either free (we have one) or $500K for new one from Xinetics

    - 32x32 piezo at 5 mm pitch from Cilas $1.0M

    - 64x64 MEMS at 0.4 mm pitch from BMC $400K

  - Only in HOWFS – 9 channels

    - Assume we are not using a DM in the HOWFS.

  - Only in LOWFS – 3 channels. Assume 32x32 MEMS at 0.4 mm pitch from BMC $100K

  - in PSF imager – 1 channel same as science 64x64 MEMS

  - in DNIRI – 6 channels of 32x32 and a PSF channel at 32x32 $400K per channel including labor

- Tip/tilt mirrors

  - In common science path

    - “Big unit” (6” mirror) $400K

    - K1 upgrade: tip/tilt stage mount for DM - $30K

  - in DNIRI

    - PI: $20K per channel

    - “Small units” PI 12mm $20K

  - in PSF imager

    - assume PI 12mm: $20K

# Not costed:

- Interferometer support

- Instruments

# Management

- Management – 18% of material and labor costs of project.

- Contingency – 30% of materials, labor, and management costs