Project Milestones:

| Year | Month | NGAO Project Milestone |
| --- | --- | --- |
| 2008 | April | System Design Review |
| 2009 | October | Preliminary Design Review |
| 2011 | June | Detailed Design Review |
| 2012 | March | Full Scale Development Intermediate Review |
| 2012 | December | Pre-Lab I&T Readiness Review |
| 2013 | June | Pre-Ship Readiness Review |
| 2013 | September | NGS First Light |
| 2013 | December | LGS First Light |
| 2014 | January | 14B Shared-Risk Science Availability Review |
| 2014 | July | Operational Readiness Review |

Preliminary Design Phase Milestones

| # | MILESTONE | DATE | DESCRIPTION | STATUS |
| --- | --- | --- | --- | --- |
| 1 | Approval to proceed with Preliminary Design Phase | 4/30/08 | Approval of this plan by the Directors. |  |
| 2 | PD phase contracts in place | 5/15/08 | Contracts issued to Caltech & UCSC for the preliminary design phase. |  |
| 3 |  |  |  |  |
| 4 | Operations Concept Document v1 Complete |  |  |  |
| 5 |  |  |  |  |
| 6 | External Interface Design Document v1 Complete |  |  |  |
| 7 | Internal Interface Design Document v1 Complete |  |  |  |
| 8 | Science Case & System Requirements Document v3.0 Complete |  |  |  |
| 9 |  |  |  |  |
| 10 | Preliminary Design Manual Complete |  |  |  |
| 11 | Cost Review Complete |  | Project cost estimates complete, documented & internally reviewed |  |
| 12 |  |  |  |  |
| 13 | Preliminary Design Review Package Distributed | 9/25/09 | PDR documents sent to reviewers |  |
| 14 | Preliminary Design Review | 10/21/09 | PDR meeting |  |
| 15 | PDR Report & Project Planning Presentation at SSC meeting | 11/18/09 | Final PD phase report including results of PDR & project plans |  |