Keck Adaptive Optics Note 414

Keck Next Generation Adaptive Optics:

System Design Phase

System Engineering Management Plan

Version 0.4     Date: August 30, 2006

W. M Keck Observatory

California Association for Research in Astronomy

65-1120 Mamalahoa Highway

Kamuela, Hawaii  96743

808-885-7887

Author List

| Name | Function |
| --- | --- |
| Peter Wizinowich | Executive Committee (EC) Chair |
| Richard Dekany | EC Member |
| Don Gavel | EC Member |
| Claire Max | EC Member & Project Scientist |

Approval Control

| Control | Name | Function |
| --- | --- | --- |
| Revised by: |  |  |
| Approved by: |  |  |
| Authorized by: |  |  |

Document Change Record

| Issue | Date | Change Description |
| --- | --- | --- |
| Initial offering | 8/30/06 |  |

Preface

This document is intended to describe the System Engineering Management Plan (SEMP) for the System Design (SD) phase of the Keck Next Generation Adaptive Optics (NGAO) project.

The purpose of the SEMP is to document the organization and development plan for the SD phase of the NGAO project, and the process by which the project will be executed.

Table of Contents

Section	Page

1	Introduction	5

2	System Design Phase Organization	5

3	System Design Phase Plan	6

3.1	Project Scope and Objectives	6

3.2	Planning Assumptions	6

3.3	Work Breakdown Structure	7

3.4	Schedule	7

3.5	Milestones	8

3.6	Risk assessment and Mitigation Plans	8

3.6.1	Technical Risks	8

3.6.2	Schedule Risks	8

3.6.3	Budget Risks	8

3.7	Configuration Management	8

3.8	Requirements Management	8

4	Process	9

4.1	Work Flow and Decision Points	9

4.2	Contracts	9

4.3	Scope of Authority	9

4.4	Performance Management	9

4.5	Reviews	9

4.6	Reporting	9

5	Coordination	9

6	References	10

6.1	Keck Adaptive Optics Notes (KAON)	10

6.2	Other Documents	10

7	Appendix: Letter from Observatory Directors establishing the NGAO SD phase Executive Committee	10

8	Appendix: System Design Phase Work Breakdown Structure Dictionary	11

9	Appendix: System Design Phase Team Meeting Schedule	14

# Introduction

A proposal for W.M. Keck Observatory’s (WMKO) Next Generation Adaptive Optics (NGAO) system was presented at the 6/21/06 meeting of the Observatory’s Science Steering Committee (SSC).1-3  This plan was well received by the SSC and Observatory management.  A 7/14/06 email from the Directors of WMKO, UC Observatory and Caltech Optical Observatory established the NGAO Executive Committee (EC) to manage the system design (SD) phase of the NGAO project (see Appendix A).  The membership of this committee included Rich Dekany, Don Gavel, Claire Max as chair of the NGAO science team and Peter Wizinowich as chair of the EC.

The Directors’ requested that the EC develop an explicit plan for this development work early in the SD phase.  This SD System Engineering Management Plan (SEMP) has been produced in response to this request.

# System Design Phase Organization

The NGAO SD phase will be managed by the NGAO EC.

The figure below illustrates the organizational structure of the project team.

Figure 1 – Organizational Structure

# System Design Phase Plan

## Project Scope and Objectives

The system design phase is the initial design phase for projects managed by WMKO.  This phase proceeds the preliminary design phase.  The system design includes a conceptual design plus a significant emphasis on how the overall project will be managed using a system engineering approach.

WMKO provides the following standard guidance for the system design (SD) phase of a development project (Adkins, 2005):

“The principle objective of a system design is to establish a design approach that meets the scientific and user requirements established for the system.  System design will establish a discipline integrated engineering plan for the proposed design, understand the technical risks, explore trade-offs, and determine estimates for performance and cost to completion.

The key deliverables from the system design phase are a Systems Requirements Document, a Systems Engineering Management Plan, a System Design Manual and a System Design Report.”

The SD phase of this project will deliver the four documents listed above.

The Systems Requirements Document will include:

- A description of the science requirements

- A description of the additional Observatory requirements

- A description of the technical requirements organized by engineering discipline with a clear flow down from the above requirements

The System Design Manual will include the following components:

- Definitions of the functional requirements.

- Descriptions of the design approach for major subsystems.

- A summary of technology drivers and the associated research needs.

- Performance budgets and error budgets.

- A technical risk analysis.

The Systems Engineering Management Plan (SEMP) document will include the following components:

- A description of the project objectives and major milestones.

- A description of the project organization.

- A description of the project management process.

- A description of the project decision process and major decision points.

- A risk assessment and a risk management plan.

- Configuration management plans for hardware, software and documentation.

The System Design Report provides a high level summary of the work done during the SD phase and makes a proposal for the preliminary design phase of the project including a plan for the remainder of the project.  This will be developed following a planning sequence based on the system level requirements, and proceeding from a WBS to task identification and description, schedule and budget development and finally a Microsoft Project plan.

## Planning Assumptions

The following assumptions were used in producing the system design phase plan:

- The NGAO proposal included a budget of $980k for the SD phase.  Only $600k of this amount is currently available in the WMKO FY07 budget.  However, WMKO is currently in active negotiation with NASA to provide additional funding in FY07 to FY09 through the exchange of 10 telescope nights/year and the WMKO Director has advised us that a significant amount of this additional funding would be available to the NGAO project after CARA Board approval.  Conclusions:

  - We do not need to prepare any funding proposals during the SD phase of this project (we will likely need to do so early in the preliminary design phase).

  - We can accelerate the SD phase once we reach FY08 (since the remaining $380k will be available early in the FY and adequate preliminary design phase funds will be available to take the project through FY08).

- During the proposal phase we made one pass through the following design process loop to demonstrate the feasibility of achieving the science requirements.  This resulted in an initial architecture or “point design.”  This process will be repeated during the system design phase.

Science  Requirements

Technical Implications

Initial  Concept

Performance Assessment

Repeat as required while making improvements & balancing trade offs

## Work Breakdown Structure

The following is the top level Work Breakdown Structure for the system design phase.  Each level one WBS element has a key deliverables that is highlighted with italics:

- System Design Phase Management

  - Planning & Contracting

  - Meetings

  - Tracking & Reporting

  - Funding Proposal(s)

  - System Design Review

- System Requirements

  - Science Requirements

  - Observatory Requirements

  - System Requirements Document

- System Design Approach

  - System Engineering

  - AO System

  - Laser Facility

  - Operations Tools

  - Science Instruments

  - System Design Manual

- System Engineering Management Plan

  - Project Plan

  - Risk Assessment & Management Plan

  - Preliminary Design Phase Plan

  - Integration & Test Plans

  - Configuration Management Plan

  - Project Management Plan

  - System Engineering Management Plan

A more detailed breakdown of the WBS including a WBS dictionary can be found in Section 8.

## Schedule

Below is the level three version of the SD schedule. We will continue to update this schedule as our understanding of the project requirements, technical plans and available resources increases through the SD phase of the project.

## Milestones

Major milestones for the NGAO SD phase are shown below in Table 1.  More details on these milestones can be found in Section 9.

Table 1: Milestones

| MILESTONE | DATE | DESCRIPTION |
| --- | --- | --- |
| System Design Review |  |  |

## Risk assessment and Mitigation Plans

Risks have been categorized into three types: Technical, Schedule and Budget. These are briefly discussed in the following paragraphs.  More detailed investigation and mitigation plans will be developed as a part of the preliminary and detailed design efforts.

Part of our risk mitigation planning will include looking at the likelihood that each individual risk will impact the project and a separate estimate of how severe the impact could be on the project. These two data points will be used to prioritize the risks so that we are able to put our mitigation efforts toward areas where we will get the most likely benefit.

### Technical Risks

### Schedule Risks

### Budget Risks

## Configuration Management

We will develop a detailed configuration management plan to establish and maintain the integrity of the NGAO software and hardware systems. This plan will be consistent with the current standards and practices for CARA and the Keck AO system.  We anticipate that this plan will include sections describing the following:

- Configuration identification

- Configuration control

- Configuration status accounting

- Configuration audits

- Software source code repositories

## Requirements Management

We will produce a plan for how we intend to accomplish this.

# Process

## Work Flow and Decision Points

We have some important decisions that need to be made as part of the system design phase.  Figure 1 – System Design Phase Decision and Activity Tree shows this process graphically.

Figure 1 – System Design Phase Decision and Activity Tree

Design Trade-offs

- Identification of Architecture Options

- Performance predictions for viable options

- Cost/Schedule/Risk assessments for viable options

## Contracts

WMKO will be issuing contracts to CIT and UC to fund personnel at these institutions to participate in the system design phase.

## Scope of Authority

Deviations from the NGAO project objectives must be approved in writing by the NGAO EC.

Decisions regarding schedule and budget are the responsibility of the NGAO EC. The chair of the NGAO EC must approve in writing all deviations from statements of work affecting the NGAO project objectives.

Purchasing, cost accounting and other financial and administrative matters will be done by WMKO.

## Performance Management

The EC will be responsible for maintaining a task plan, budget and schedule for the SD phase of the NGAO  project.

## Reviews

A System Design Review (SDR) will be held as the culmination of this design phase.  This review will be conducted in accordance with WMKO standards.

## Reporting

Project Reporting will occur at each SSC meeting.  A written report will be provided prior to these meetings.  We will use the guidelines in the document Management Guideline for the Preparation of Monthly Reports, version 1.2, Sean Adkins, July 7, 2003, in preparing our reporting format.

# Coordination

The schedule calls for various meetings and videoconferences to be held during the course of the project.

The NGAO EC will have weekly telecons throughout the SD phase of this project.

E-mail will be used as a primary means of intra-project communications.

A document archive has been set up at ...

# References

## Keck Adaptive Optics Notes (KAON)

All of the documents listed below are available on the KeckShare site at http://keckshare.keck.hawaii.edu/dsweb/View/Collection-218.

- KAON 399. NGAO Proposal Executive Summary

- KAON 400. NGAO Proposal

- KAON 409. NGAO Presentation to the SSC – 6/21/06

## Other Documents

- Management Guideline For the Preparation of Monthly Reports, version 1.2, Sean Adkins, 7/7/2003

- CARA Engineering Guideline for the Preparation of Requirements Documents, 9/4/2003

- New Instrument Design and Development, The System Design Phase, by Sean Adkins, 12/11/2003

# Appendix: Letter from Observatory Directors establishing the NGAO SD phase Executive Committee

Peter, Richard, Don and Claire,

We propose the following as the appropriate management structure for the next 18-month  phase of NGAO. This is the largest program we have undertaken since the original construction of the telescopes. As a community we are fortunate to have world-class expertise in AO development at Keck, UC and Caltech. The NGAO project presents the perfect opportunity to build a strongly collaborative effort between Keck (Hawaii) and the mainland groups. This management structure explicitly takes advantage of the geographically-distributed expertise in our community and emphasizes the collaborative nature of the effort.

The proposed structure is to have the top level of management be comprised of an Executive Committee (EC) chaired by Peter Wizinowich with Rich Dekany, Don Gavel and Claire Max (as Chair of the NGAO Science Team) as the other members. As Chair, Peter will have overall responsibility for delivery of the System Design Phase deliverables. Budget authority will be held by the EC. We also endorse the idea of a funded Science Team led by Claire.

Very early in the next phase, we’d like the EC to develop an explict plan for how the development work will be distributed between the three centers (Keck, Santa Cruz and Caltech).

This is an extremely important project for the future of the Keck Observatory. The systems as conceived of in this early phase would maintain the Keck leadership in groundbased astronomy into the next decade. The strongly collaborative model for undertaking a major development effort is also an important experiment that we need to make work.

Thank you very much for taking on such a large and important project.

Taft, Hilton Shri, Mike

# Appendix: System Design Phase Work Breakdown Structure Dictionary

- System Design Phase Management

- Management of the SD Phase of the NGAO project, including budget and schedule, and regular reporting to the SSC and Observatory Directors.  The Executive Committee (EC) has overall responsibility for the delivery of the key products of the SD Phase.

  - Planning & Contracting

    - Planning

- Preparation of the SD phase System Engineering Management Plan (this document).  Replanning as appropriate during the SD phase, including support for the Observatory FY planning.

    - Contracting

- WMKO intends to issue contracts to Caltech and UCSC, and possibly elsewhere, to provide funding for these groups to support the SD phase.  This WBS element covers the effort to prepare contract documentation, including statements of work, and to implement these contracts.

  - Meetings

- Effort in support of regular project meetings.

    - Executive Committee Telecons

- The EC will have regular telecons to manage the SD phase.  This WBS covers the effort to participate in these telecons.

    - Science Advisory Committee Telecons

- The Project Scientist will hold regular telecons with the other members of the SAC.  This WBS covers the effort to participate in these telecons.

    - Team Meetings

- Team meetings will be held every ~ 6 weeks during the SD phase.  These meetings will alternate between in-person meetings and teleconferences.  The in-person meetings will generally be held at either Caltech, UCI or WMKO in an alternating fashion.

  - Tracking & Reporting

- We will be reporting on the SD phase status and plans at each SSC meeting.  This WBS covers the effort to prepare for these meetings, including tracking our progress, and to present at these meetings.

- We will also be providing more global overviews of the SD progress at the Keck Science Meetings.  This WBS covers the effort to prepare for these meetings.

  - Funding Proposal(s)

- Generation of proposals for funding.  The current assumption is that no work will be needed in this area during the SD phase.

  - System Design Review

    - System Design Report

- Provides a high level summary of the work done during the SD phase and makes a proposal for the preliminary design phase of the project including a plan for the remainder of the project.

    - System Design Review Activities

- This WBS covers the following activities: identifying reviewers, distributing the four SD phase documents to the reviewers, responding to the reviewer questions, preparing and presenting at the SDR and responding to the SDR reviewer report.

- System Requirements

- Development and documentation of science and system requirements.

  - Science Requirements

    - Solar System

    - Galactic

      - Galactic Center

- Better understand and document the astrometry performance requirement.  Iterate with the astrometry performance budget effort.

      - Debris Disks and Binary Brown Dwarfs

- Better understand and document the companion sensitivity requirement; iterate with the companion sensitivity performance budget.  For debris disks, flesh out observing scenarios and develop requirements e.g. polarimetry.  For example, if we do want to do dual-channel polarimetry, there should be a place in the AO system for a deployable polarization modulator

    - Extragalactic

      - Resolved Stellar Populations

- Better understand and document the contiguous science field requirement.  Better understand and document the photometry performance requirement; and iterate with the photometric performance budget.  Consider how Gemini’s MCAO focus in this area should impact the science priority of this topic for NGAO.

      - High Redshift Galaxies

- Better understand and document the encircled energy and background requirements; and iterate with the encircled energy and background performance budgets.  Understand and document the d-IFU optimum lenslet scale.

    - Science Requirements Summary

  - Observatory Requirements

  - System Requirements Document

- Summary of products produced in WBS 2 including descriptions of the science requirements, additional Observatory requirements and the technical requirements organized by engineering discipline with a clear flow down from the science and Observatory requirements.

- System Design Approach

  - System Engineering

    - Performance Budgets

- Development of systems level engineering budgets for a variety of astronomical performance metrics, organized around key observing scenarios.  The level of detail available to each budget will depend on the state of the art, the resources dedicated to budget generation during the SD phase, and astronomical user experience.  All performance budgets should parameterize the performance behavior versus the corresponding sky coverage fraction.  (when appropriate, coverage levels of 5, 30, and 90% should be assumed).

      - Model Assumptions

- The goal of this WBS is to document the assumptions (and rationale) for the key parameters to be adopted for the development of all performance budgets, including such items as the median Cn2(h), sodium column density and Keck telescope optical performance.  In some cases work will be required to acquire and evaluate data to determine the appropriate assumptions to be used.

        - TMT Site Monitoring Data Mining

        - Telescope Dynamic Performance Data

- Improve/document our understanding of the actual primary mirror wavefront errors.

        - Telescope Static Wavefront Errors

- Improve/document our understanding of the actual primary mirror wavefront errors.

        - Sodium Return versus Laser Format

- Improve/document our understanding of the actual sodium return versus various laser formats.  Should base this on experience with the Keck, Gemini, Palomar and Subaru lasers.

      - Model/Tool Validation

- Execution of a series of quantitative checks on the validity of key NGAO models and development tools, as compared to results obtained from various laboratory and sky tests with existing AO systems.

        - Agreement between Tomography Codes

- Understand the differences between tomography codes in use at WMKO and UCSC, modify the codes as appropriate and document the result that should be used.

        - Agreement between Sky Coverage Codes

        - Anchor to Keck II LGS AO PSFs

- Demonstrate the ability to produce PSFs that are adequately similar to PSFs obtained with the Keck II LGS AO PSFs.  Understand and make changes to the models to achieve this result.  Document the result and use the result in updating the appropriate performance budgets.

        - Anchor to On-sky MGSU Experiments

- Use the results of the Palomar (and possibly MMT) MGSU experiments to validate and/or correct the tomography model and its assumptions.

        - Anchor to LAO Lab Experiments

- Determine what high leverage experiments should and can be performed at LAO to validate our models and tools, perform these experiments, and use the results to update the appropriate models, tools and performance budgets.

      - Throughput

- Development of optical transmission budgets for each of the science path(s), HOWFS, LOWFS(s), and slow WFS.

      - Background

- Development of thermal background budget for the IR science and wavefront sensor instruments.

      - Wavefront Error

- Development of residual wavefront error budgets for a set of key observational scenarios.  The first step is to document the budget and tool used in the proposal.

      - Encircled Energy

- Development of encircled energy budgets for a set of key observational scenarios.

      - Photometric Accuracy

- Development of a deviation budget for differential photometric precision for a set of key observational scenarios.  To be manageable, this budget should assume statistical independence among the key physical sources of degradation of photometric precision.  Physical effects to be considered may include wind-induced PSF anisoplanatism, photon noise, read noise, flat-fielding variations, field-dependent optical aberrations, imperfect estimation of the anisoplanatism contribution to PSF shape, atmospheric scintillation, filter bandpass uncertainty, transparency waves in the atmosphere, imperfect atmospheric color correction, PSF sampling issues, and nonlinear detector response.  Investigation of the impact of certain terms in the budget may require detailed AO performance simulations.  Calculation of other terms may be beyond the scope of the SD phase, resulting in a top-level allocation to the performance budget until otherwise updated.

      - Astrometric Accuracy

- Development of a deviation budget for differential astrometric precision for a set of key observational scenarios.  To be manageable, this budget should assume statistical independence among the key physical sources of degradation of astrometric precision.  Physical effects to be considered may include atmospheric tilt anisoplanatism, wind-induced PSF anisoplanatism, field-dependent optical aberrations, photon noise, read noise, flat-fielding variations, PSF sampling issues, telescope plate scale fluctuations, and nonlinear detector response.  Investigation of the impact of certain terms in the budget may require detailed AO performance simulations.  Calculation of other terms may be beyond the scope of the SD phase, resulting in a top-level allocation to the performance budget until otherwise updated.

      - Polarimetric Accuracy

      - Companion Sensitivity

- Development of a companion sensitivity performance budget.  Potential tasks include: Identify a strawman coronagraph (basic questions like whether it's part of the AO system or part of the science instrument; higher order questions like architecture choice so we can do more realistic simulations and understand how it affects the AO system).  Develop a contrast error budget that includes not just AO performance but realistic values for static/internal effects, so that we can see what instrument design choices (e.g. optics quality) are important now.

      - Point Source Sensitivity

- The purpose of this WBS is to produce a summary table of predicted point source sensitivities based on the relevant performance budgets.

      - PSF Stability

- The purpose of this WBS is to produce a document, including sample PSFs, summarizing the predicted PSF stability based on the relevant performance budgets.

      - Observing Efficiency

- The purpose of this performance budget is to determine what will be required to meet the Observing Efficiency requirement.  This budget is only intended to cover the NGAO facility and science instruments (and not the telescope or facility).  A list of all the items contributing to the loss of LGS AO-corrected integration time will be produced along with reasonable allocations of the observing efficiency budget amongst these items.

      - Observing Uptime

- The purpose of this performance budget is to determine what will be required to meeting the observing uptime requirement.  This budget is only intended to cover the NGAO facility and science instruments (and not the telescope or facility).  A list of all the items contributing to downtime will be compiled along with a distribution of the uptime budget amongst these items.

      - Performance Budgets Summary

    - System Architecture

    - Trade Studies

      - System Architecture Trade Studies

        - NGAO versus Keck AO Upgrades

- Consider the feasibility of upgrading one of the existing Keck AO systems incrementally to meet NGAO science requirements.  Consider opto-mechanical constraints & upgradability of embedded & supervisory control systems.  Consider impact on science operations during NGAO commissioning.  Complete when option assessment documented.

        - Adaptive Secondary Mirror Option

- Consider relative performance, cost, risk & schedule of an NGAO implementation based on an ASM.  Quantify the benefit of an ASM to both NGAO and non-NGAO instruments.  Complete when NGAO baseline architecture selected.

        - K & L-band Science

- Consider the relative performance, cost, risk, and schedule of different strategies for K and L-band science optimization.  Compare a Nasmyth relay, an ASM & a separate lower-order Nasmyth AO cryo-system.  Complete when performance estimates & strategy for K- & L-band observing documented.

        - Keck Interferometer Support

- Consider the relative performance, cost, risk & schedule of feeding KI with NGAO or a repackaged version of the current AO system. Decoupling of NGAO from interferometer support may simplify & improve performance of NGAO. The feasibility of maintaining a version of the two current AO systems for KI use should be evaluated.  Complete when NGAO baseline architecture selected.

        - Instrument Balance

- Consider the relative merit of installing NGAO on Keck I vs Keck II. This must take into account the long-term instrumentation strategy for Keck, available laser infrastructure, and impact on operations.  Complete when architecture and location requirements documented.

        - GLAO for non-NGAO Instruments

- Consider the relative performance, cost, risk, and schedule of GLAO compensation using an ASM for non-NGAO instruments.  Complete when expected performance benefit for each instrument documented.

        - Instrument Reuse

- Consider the cost/benefit of reuse of existing Keck AO instruments, particularly OSIRIS and NIRC2, versus the benefit of design freedom for an all-new instrument suite.  Complete when issues documented Observatory strategy adopted.

        - Telescope Wavefront Errors

- Review new data on the telescope static and dynamic wavefront errors.  Determine how and whether NGAO can correct for these errors.  Determine the performance benefit of a large LOWFS patrol field to enable use of the brightest possible NGS.  Consider whether a separate sensor outside the NGAO FOV would be useful for measuring/correcting the telescope errors.  Complete when impact on current Keck LGS AO system understood and impact on NGAO reviewed.

      - Adaptive Optics System Trade Studies

- The following are the medium and high priority trade studies identified in an Appendix of the NGAO proposal.  Low priority trade studies have been deferred.

        - AO Enclosure Temperature

- Consider the performance, cost, risk, reliability & maintainability of cooling a Nasmyth NGAO enclosure.  Calculate sensitivity impact as function of waveband (V through L-band).  Complete when enclosure operating temperature selected.

        - Optical Relay Design

- Consider the relative performance, cost & risk of an OAP & Offner relay.  Consider image quality vs. FoV, pupil image quality & the flowdown of requirements onto the (variable distance) LGS wavefront sensor(s).  Confirm that off-axis LGS aberrations out to 90" field radius are acceptable.  Complete when an NGAO baseline optical design is selected.

        - Field Rotation Strategy

- Consider the relative performance, cost, reliability & maintainability of compensating field rotation using 1 or more K-mirrors vs using 1 or more instrument rotators.  Complete when baseline approach & instrument requirements documented.

        - Dichroics

- Determine the observation requirements for 1 or more dichroic changers. Different observing programs may desire different distributions of light among HO WFS, LO WFS & science light paths.  Complete when dichroic changer requirements documented.

        - Rayleigh Rejection

- Evaluate the impact of unwanted Rayleigh backscatter to NGAO system performance.  Consider the relative performance, cost, risk & schedule of various strategies for mitigation of LGS Rayleigh backscatter. Techniques include background subtraction, modulation & optimizing projection location.  This issue is closely coupled to laser pulse format, with pulsed lasers generally providing more options for Rayleigh mitigation than CW lasers.  Complete when NGAO baseline architecture selected.

        - LGS Wavefront Sensor Type

- Consider alternative WFS designs (e.g. Shack-Hartmann vs. pyramid) for different laser pulse formats.  Evaluate and compare the advantages of e.g. short pulse tracking using radial geometry CCDs and mechanical pulse trackers.  Complete when LGS WFS requirements have been documented.

        - LGS Wavefront Sensor Number of Subapertures

- Consider alternative WFS designs (e.g. Shack-Hartmann vs. pyramid) for different laser pulse formats.  Evaluate and compare the advantages of e.g. short pulse tracking using radial geometry CCDs and mechanical pulse trackers.  Complete when LGS WFS requirements have been documented.

        - Slow Wavefront Sensor

- Determine the requirements, if any, for slow wavefront sensor for tracking of non-common-path aberrations between the HOWFS and science instruments.  Determine potential waveband for slow WFS operation.  Consider if a single NGS HOWFS can be pressed into service for this purpose (with another lenslet array)?  Consider impact of dark current in longer exposures.  Complete when Slow WFS requirements are documented.

        - Low Order Wavefront Sensor Architecture

- Consider the cost/benefit and technical maturity of MEMS-based correction within the LOWFS, using MOAO control techniques.  Include consideration of additional metrology systems required, if any.  Compare with cost/benefit of MCAO system to provide tip/tilt star sharpening.  Complete when LOWFS requirements and sky coverage estimates have been documented.

        - Number and Type of Low Order Wavefront Sensors

- Perform a cost/benefit analysis for the optimal type, waveband, and number of tip/tilt and tip/tilt/focus low-order WFS.  Complete when LOWFS requirements and sky coverage estimates have been documented.

        - Centroid Anisoplanatism

- Consider the impact of centroid anisoplanatism (e.g. the tip/tilt error due to coma in the low-order WFS) and mitigation strategies, if necessary.  Evaluate the difference between Zernike (z-tilt) and centroid tilt (g-tilt) for NGAO sensors.  Complete when documented and mitigation strategy adopted.

        - Deformable Mirror Stroke Requirement

- Determine required DM stroke based on performance, cost, risk, reliability & maintainability.  Consider both global & inter-actuator stroke & quantify the performance penalty for different levels of actuator saturation.  Determine DM stroke offloading requirements to other NGAO system elements.  Complete when DM stroke, stroke offloading & related system requirements documented.

        - Stand-alone Tip/Tilt Mirror versus DM on Tip/Tilt Stage

- Consider the performance, cost, risk, reliability, and maintainability of a stand-alone tip/tilt mirror vs. mounting an otherwise necessary mirror (e.g. a DM) on a fast tip/tilt stage. Note that high BW correction is difficult with a large or heavy mirror.  Complete when tip/tilt approach selected.

        - Correcting Fast Tip/Tilt with DM

- Consider the performance, cost, risk, reliability, and maintainability of performing the highest bandwidth tip/tilt correction using DM actuators. Note that allocation of some time/tilt control to the DM complicates the control system, may increase the stroke requirement & thus the DM cost.  Complete when control system & DM stroke requirements determined.

        - Focus Compensation

- Consider cost/benefit of different approaches to focus compensation due to sodium layer motion.  Include consideration of the proper combination of LGS focus, LOWFS focus and Slow WFS focus.  Complete when focus tracking strategy has been documented and reflected in error budgets.

      - Laser Facility Trade Studies

        - Laser Pulse Format

- Consider the performance, cost, risk, reliability, and maintainability of different sodium laser pulse formats, including usability under various weather scenarios, infrastructure and beam transport issues, and commercial readiness.  Complete when laser pulse format requirements have been documented.

        - Free Space versus Fiber Relay

- Consider the performance, cost, risk, upgradability, reliability & maintainability of free-space guide star laser transport vs hollow core fiber transport.  Complete when a beam transport system has been selected.

        - LGS Asterism Geometry and Size

- Consider the technical performance tradeoff for different LGS asterism geometries (e.g. quincunx, ring, 1+triangle, or hex) and asterism radii.  Include consideration of fixed or variable asterism radius in terms of optimizing Strehl of the tip/tilt stars and resulting sky coverage.  Complete when LGS asterism, HO WFS, and LO WFS requirements have been documented.

        - Variable versus Fixed LGS Asterism Geometry

- Consider the cost/benefit of continually varying the LGS asterism radius vs. a fixed number of radii (e.g. 5", 25", 50").  Complete when LGS asterism requirements have been documented.

    - Functional Requirements

- Based on the system requirements, performance budgets and the system architecture choices, develop functional requirements for the AO system, laser system, operations tools and science instruments.

      - AO System

      - Laser System

      - Operations Tools

      - Science Instruments

    - Technology Drivers Summary

    - Technical Risk Assessment

  - AO System

    - AO System Architecture

- Based on system requirements, design the opto-mechanical layout and specify components for the optical paths of the receiver system (“receiver” means guidestar, tip/tilt star, and science beam handling and diagnostics; as distinguished from “transmitter” which indicates the laser transport and launch system).

    - AO Enclosure

- Based on system requirements and performance budgets, design an enclosure to control air flow, temperature, humidity, scattered light, etc. as required. Input to this process are results of a trade study determining optical surface temperatures required to meet emissivity requirements. Also input to this process is a determination of humidity requirements for certain components such as DMs. The work includes interaction with the optical designer to assess scattered light issues and to design appropriate baffles and beam blocks. Output is an enclosure system design with specifications for components of this system along with recommendations for vendor sources.

    - Opto-Mechanical Design

- Based on system requirements and performance budgets, design the optical relays and specify optical components for the optical paths of the receiver.  Perform analyses to verify performance consistent with system error budgets (terms assigned to static and non-common path wavefront errors, temperature induced drifts, and optical component tolerances) and modify design accordingly to meet these error budgets. Perform similar analyses and rectifications for meeting throughput, emissivity, and stability budget requirements.

      - Field Rotation

- Based on system requirements and performance budgets, determine the optimal approach to addressing field rotation for the science instruments and NGAO system, and provide a conceptual design.  Different approaches can be considered for the rotational needs of the science instruments, the wavefront sensors and the laser launch asterism.

      - Optical Relay

- Based on system requirements and performance budgets, design the optical system layout that supports the optical design for the receiver. Perform analyses to verify performance consistent with system error budgets: terms assigned to mechanical drift, flexure, temperature, and machine tolerances.

      - Optical Switchyard

- Based on system requirements and performance budgets, design the optical switchyard that will distribute light between the various wavefront sensors, acquisition cameras and science instruments, and determine the requirements on this system and its components.

      - Optical Support Structure

- Based on system requirements and performance budgets, design the mechanical system that supports the optical and electronic components of the receiver. Perform analyses to verify performance and rectify as necessary

      - Wavefront Sensors

        - High Order LGS Wavefront Sensors

        - High Order NGS Wavefront Sensors

        - Low Order NGS Wavefront Sensors

        - Calibration Wavefront Sensors

      - Wavefront Correctors

        - Tip/Tilt

        - Deformable Mirror

      - Atmospheric Dispersion Correction

- Define the software and hardware needed to address atmospheric dispersion including pointing corrections between the wavefront sensing and science wavelengths, and as appropriate visible and IR ADCs for the science instruments and wavefront sensors.

      - Acquisition Cameras

        - NGS Acquisition Camera

        - LGS Acquisition Camera

      - Alignment, Calibration, Diagnostics, Metrology and Monitoring

- Define the tools needed to support routine alignment and calibration and to provide the required routine metrology and diagnostics.  Monitoring tools that are not part of the AO system, such as an external MASS/DIMM should be included under this category.  Alignment, calibration and diagnostics tools will like include a telescope simulator with multiple NGS and LGS sources and a means of simulating turbulence, as well as arc lamps for science instrument calibration.

    - Non-Real-Time Control

      - Non-RTC Software Design

- Based on system operations requirements and in corroboration with the AO Optical Bench design and AO System design, develop a software architecture and maintenance plan for all remote and automatic real time control software. Also, develop data collection and management systems.

      - Non-RTC Electrical Design

- Based on system requirements and in collaboration with the optical and mechanical designers, determine the electrical system requirements for supporting the optical bench including motors, shutters, filter wheels, and other robotic or remotely operable control stages and devices. Also, determine requirements for drive electronics and control boxes for these stages and the associated cabling, connectors, and interfacing. Also, determine the power requirements and design the control signal and power routing to meet overall system noise requirements (this is exclusive of real-time control and wavefront sensing, which is covered in a separate description). Collaborate with the software team to determine computer interface and operability requirements. Output is an electronic/electrical component and wiring layout, control box placement (in corroboration with the mechanical designer), power load analyses, specifications for components, and review/summary of vendor sources for the components.

    - Real-time Control

- Based on system requirements, operations requirements, and error budgets, determine an architecture for the real-time controller, including both hardware and software configuration. Input to this process includes candidate wavefront sensing, tomography, tip/tilt, and DM control and signal processing algorithms as provided by the system engineering group as a result of trade studies. Design work includes specification of hardware interface requirements, hardware processor speed, data rate, and storage requirements, design of the data flow, design of the algorithm implementation software, and design of the diagnostic and telemetry streams. Work includes analysis and modeling of performance at the low-level of implementation, e.g. taking into account data transmission delays, processor delays, and data resolution.

      - RTC Architecture Analysis and Design Study

- Based on system requirements, operations requirements, and error budgets, determine an architecture for the real-time controller, including both hardware and software configuration. Input to this process includes candidate wavefront sensing, tomography, tip/tilt, and DM control and signal processing algorithms as provided by the system engineering group as a result of trade studies. Output of this process is an analysis of candidate architectures, simulations of expected real-time performance, and guidance (in the form of strawman designs) for the RTC software module definition and RTC hardware module definition tasks.

      - RTC Software Module Definition

- Given the architectural design and results of the RTC design study, specify the software development environment tools required (& analyze vendors of such), develop a software top level block diagram, define software data structures and data flow paths, define software command language for interface to the system controller/user interface, design diagnostic and telemetry streams, specify software module functions at a detailed level. Develop a real-time software implementation and test plan.

      - RTC Hardware Module Definition

- Given the architectural design and results of the RTC design study, specify the hardware platform (or platform options, through PDR phase), specify the hardware interfaces, including required cabling, in consideration of real-time data flow and diagnostic/telemetry streams, determine the overall size, mounting, and power requirements. If specifying custom processor boards (likely, with a transputer/FPGA architecture) design the board layout in conformance with fab-house design rules, specify the component processors and all other components needed to enable assembly of the boards. Develop a hardware acceptance test plan. Specify test equipment needed.

  - Laser Facility

    - Laser System Architecture

- Based on system requirements and the error budgets, develop a system for producing laser beacons sufficient for NGAO. An input to this process is the result of a trade study determining the field of view, number of guidestar beacons, and constellations for various science observing conditions. Produce as output: the system architecture and design/specifications for creating and projecting the guidestars, controlling the pointing, maintaining output beam quality, diagnostics, and user control.

    - Laser Enclosure

    - Laser

- Based on system requirements and error budgets, specify a laser or set of lasers to produce guidestars. Take into consideration the current state of the art and availability of lasers. An input to this process is the result of a trade study determining the desirable pulse format or formats and power per guidestar. Produce as output: a summary of the laser options versus requirements.

    - Laser Launch

- Based on system requirements and error budgets, develop the systems required for delivering the laser power from the laser to the sky.

      - Laser Beam Transport

      - Laser Pointing and Diagnostics

      - Laser Launch Telescope

    - Laser Safety Systems

      - Personnel and Equipment Safety Systems

      - Aircraft and Satellite Safety Systems

    - Laser Traffic Control

- All telescopes on Mauna Kea are currently required to participate in the Laser Traffic Control System.  Determine what changes will be needed to accommodate NGAO in this system.

    - Laser System Control

      - Laser System Software

      - Laser System Electronics

  - Operations Tools

    - Operations Architecture

- Define the overall software and computer architectures needed to support the operations tools.

    - Observing Setup

- Define the software tools needed to perform AO and laser system configurations and calibrations in preparation for the night’s observng.

    - User Interface

- Define the user interface tools and on-line documentation to be used for routine daytime preparation and nighttime operation, including an astronomer user interface, an operator user interface and troubleshooting.

    - Astronomer Planning

- Define the software tools and on-line documentation that will be needed to support observation planning by astronomers.

    - Science Instruments and Telescope Interfaces

- Define the software tools and interfaces needed to support pointing offloads, focus offloads, automated focus correction versus instrument configuration, nodding and chopping.

    - Performance Monitoring

- Define the software tools and performance needed to 1) monitor and record the observing conditions, 2) predict performance based on AO telemetry and/or external seeing monitors, 3) to monitor and record the current performance, and 4) to compare the performance versus prediction.

    - Automation and Optimization

- Define the software tools and performance needed to automate the NGAO nighttime operation for optimal observing efficiency and for optimal performance.

  - Science Instruments

    - OSIRIS

    - Interferometer

    - OHANA

    - Near-IR Imager

    - Visible Imager

    - Visible IFU

    - Deployable Near-IR IFU

    - Mid-IR IFU

  - System Design Manual

- Summary of the products produced in WBS 3 including definitions of the functional requirements, descriptions of the design approach for major subsystems, a summary of technology drivers and the associated research needs, performance budgets and error budgets and a technical risk analysis.

- System Engineering Management Plan

- Note that this document (KAON 414) represents a simplified version of the SEMP that will need to be prepared under this WBS for the entire NGAO project.

  - Project Plan

- A task definition, cost estimation, list of major milestones, WBS structure and an MS project plan will be prepared for the entire NGAO project (excluding the SD phase).

  - Risk Assessment & Management Plan

- The risk assessment prepared as Section 17 of the NGAO proposal can be used as a starting point.

  - Preliminary Design Phase Plan

- A detailed project plan for the PD phase of the NGAO project.

  - Integration & Test Plans

    - Subsystem Integration & Test Plans

    - System Integration & Test Plans

  - Configuration Management Plan

  - Project Management Plan

  - System Engineering Management Plan

- Document summarizing the products produced in WBS 4 including a description of the project objectives and major milestones, a description of the project organization, a description of the project management process, a description of the project decision process and major decision points, a risk assessment and a risk management plan, and configuration management plans for hardware, software and documentation.

# Appendix: System Design Phase Team Meeting Schedule