## Mtg Schedule
NGAO System Design Phase Team Meeting Schedule
Version 1.0 11/7/06
Bold = Co-located; Non-Bold = Video/Teleconference
Date | # | Venue | Major Meeting Goal | Science/Management | Systems Engineering | Optics/Mechanics | Electronics/Software | WFS/WFP | Laser/DM | Instrument/Observatory | Other Events
|  |  |  | Milestone | Milestone | Milestone | Milestone | Milestone | Milestone | Milestone
2006-09-14 | 1 | UCI | Kickoff | NGAO SD Plan | Model/Tool Validation
Sci. Case I
[11 empty] | 2006-09-15 | Keck Sci Mtg (UCI)
2006-11-14 | 2 | CIT | Performance Drivers |  | Identify Perf. Drivers |  |  | Var/Fixed LGS Ast |  | Interfer. Requirements
|  |  | SRD I |  | SRD I |  |  | LGS Ast Geom & Sz |  | Instr. Study Strategy
[11 empty] | 2006-11-06 | SSC (UCLA)
2006-12-13 | 3 | Video | Various TS's |  | Obs. Effic. Budget | Rayleigh Rejection |  |  |  | Sci. Instr Reuse
[5 empty] | Site Monitoring Update | Tip/Tilt Stage v. DM |  |  |  | Instrument Balance
MCAO/MOAO
[11 empty] | 16-19 Nov 06 | CfAO Fall Retreat
2007-01-22 | 4 | Keck | Performance Budgets | Continuous Sci. Field | Photometric Budget | Tel Wavefr Errors |  | LOWFS Num & Type
|  |  |  | Operations Arch. I | Astrometric Budget |  |  | HOWFS Num & Type
High-contrast Budget
Polarimetric Budget
Throughput Budget
[11 empty] | 2007-01-24 | SSC (Keck)
2007-03-07 | 5 | Video | SRD II | K- & L-band Science | SRD II | AM2 | NGAO vs Upgrades |  |  | Interfer. Support
|  |  | Various TS's | GLAO for non-AO | Subsys Funct Req I | Optical Relay
2007-04-18 | 6 | UCSC | Various TS's | d-IFU Opt Sampling |  | Field Rotat. Strategy |  | Focus Compens. | DM Stroke Req | Dichroics
|  |  |  | Risk Analysis I |  | Encl/Relay Temp. |  |  | Laser Pulse Format
[11 empty] | 2007-04-03 | SSC (Ca)
2007-05-30 | 7 | Video | Software Review I | Operations Tools I |  | Laser Enclosure | Software Architecture | Slow WFS | Free/Fiber BTO | Obs. Interfaces I
[8 empty] | Centroid Anisoplan | DM RfI | Instrument Interfaces
[11 empty] | 2007-06-20 | SSC (Keck)
2007-07-09 | 8 | UCSC | 5-day Retreat |  | SRD III | Sci Path Opt Des I | Non-real-time Softwr I | HOWFS I | Laser RfI | Calibr. Stimulus I
[6 empty] | Mech Structure I |  | LOWFS II
2007-08-22 | 9 | Video | Cost Review I | Cost Estimate I | Subsystem Test Plans |  | Electronics I | Real-time Control I
SDM I
[11 empty] | TBD | Keck Sci Mtg (TBD)
2007-09-11 | 10 | CIT | Infrastructure I |  | Science Verification | Sci Path Opt Des II |  |  | LGS Delivery I | Obs. Interfaces II
[6 empty] | Mech Structure II |  |  |  |  | 2007-11-06 | SSC (Ca)
2007-11-05 | 11 | Video | Software Review II | Operations Tools II | SDM II |  | Non-real-time Softwr II |  |  | Instrument #1 I
2007-12-12 | 12 | Keck | 3-day Meeting | Risk Analysis II | Integr. & Test Plan I |  | Electronics II | HO WFS II
|  |  | Cost Review II | Cost Estimate II | Subsys Funct Req I |  |  | LO WFS II
2008-01-09 | 13 | Video | SDR Preparation | SDR Prep | SDR Prep | SDR Prep | SDR Prep | SDR Prep | SDR Prep | SDR Prep
|  |  | Prelim. Design Prop. |  | SRD IV
[11 empty] | 2008-01-24 | SSC (Keck)
2008-03-31 | 14 | Keck | SDR | SDR
[11 empty] | 2008-04-03 | SSC (Ca) TBC
2008-04-04 | 15 | TBD | Prelim. Design Kickoff |  |  | Sci Path Opt Des III |  | Real-time Control II | LGS Deliver II | Calibr. Stimulus II
Mech Structure III
2008-05-14 | 16 | Video | Software Review III | Operations Tool III |  |  | Non-real-time Softwr III |  | DM RfP
[11 empty] | TBD | SSC (Keck)
2008-06-25 | 17 | TBD | Infrastructure II |  | Integr. & Test Plan II |  | Electronics III |  | Laser RfP | Instrument #1 II
[5 empty] | SDM III |  |  |  |  | Observatory Interfaces III

## Wk-hrs
NGAO System Design Phase Team Meeting Schedule
Version 0.9 9/25/06
Bold = Co-located; Non-Bold = Video/Teleconference
Cumulative Total
Date | # | Venue | Major Meeting Goal | Science/Management | Systems Engineering | Optics/Mechanics | Electronics/Software | WFS/WFP | Laser/DM | Instrument/Observatory | Other Events
|  |  |  | Milestone | Milestone | Milestone | Milestone | Milestone | Milestone | Milestone
414
2006-09-14 | 1 | UCI | Kickoff | 80 | 334
Sci. Case I
[11 empty] | 2006-09-15 | Keck Sci Mtg (UCI)
2006-11-07 | 2 | CIT | Performance Drivers |  | 200 |  |  | 10 |  | 40 |  |  | 664
|  |  | SRD I |  | 400 |  |  | 20 |  | 40
[11 empty] | 2006-11-06 | SSC (UCLA)
2006-12-13 | 3 | Video | Various TS's |  | 240 | 40 |  |  |  | 120 |  |  | 1674
[5 empty] | 80 | 60 |  |  |  | 10
80
[11 empty] | 16-19 Nov 06 | CfAO Fall Retreat | 2434
2007-01-22 | 4 | Keck | Performance Budgets | 100 | 240 | 80 |  | 260
|  |  |  | 70 | 240 |  |  | 50
320
[5 empty] | 40 | [7 empty] | 3194
40
[11 empty] | 2007-01-24 | SSC (Keck)
2007-03-07 | 5 | Video | SRD II | 40 | 800 | 40 | 100 |  |  | 200
|  |  | Various TS's | 20 | 630 | 60 | [6 empty] | 5084
2007-04-18 | 6 | UCSC | Various TS's | 100 |  | 80 |  | 30 | 50 | 60
|  |  |  | 40 |  | 100 |  |  | 100
[11 empty] | 2007-04-03 | SSC (Ca) | 5644
2007-05-30 | 7 | Video | Software Review I | 200 |  | 100 | 100 | 80 | 100 | 50
[8 empty] | 40 | 50 | 150 |  |  | 6514
[11 empty] | 2007-06-20 | SSC (Keck)
2007-07-09 | 8 | UCSC | 5-day Retreat |  | 890 | 80 | 100 | 60 | 200 | 60 |  |  | 7964
[6 empty] | 20 |  | 40
2007-08-22 | 9 | Video | Cost Review I | 100 | 100 |  | 100 | 250 |  |  |  |  | 8544
30
[11 empty] | TBD | Keck Sci Mtg (TBD) | 9344
2007-09-11 | 10 | CIT | Infrastructure I |  | 360 | 50 |  |  | 210 | 150
[6 empty] | 30 |  |  |  |  | 2007-11-06 | SSC (Ca)
10274
2007-11-05 | 11 | Video | Software Review II | 200 | 30 |  | 100 |  |  | 300
2007-12-12 | 12 | Keck | 3-day Meeting | 40 | 100 |  | 100 | 60 |  |  |  |  | 12424
|  |  | Cost Review II | 100 | 630 |  |  | 60
2008-01-09 | 13 | Video | SDR Preparation | 80 | 80 | 80 | 80 | 80 | 80 | 80
|  |  | Prelim. Design Prop. |  | 800
[11 empty] | 2008-01-24 | SSC (Keck) | 12904
2008-02-04 | 14 | Keck | SDR | 480
[11 empty] | 2008-04-03 | SSC (Ca) TBC | 13504
2008-04-04 | 15 | TBD | Prelim. Design Kickoff |  |  | 40 |  | 250 | 210 | 60
[6 empty] | 40 | [6 empty] | 13854
2008-05-14 | 16 | Video | Software Review III | 200 |  |  | 100 |  | 50
[11 empty] | TBD | SSC (Keck) | 14644
2008-06-25 | 17 | TBD | Infrastructure II |  | 100 |  | 100 |  | 290 | 300
[5 empty] | 20 |  |  |  |  | 150
|  |  | Subsystem Total (Hrs) | 1850 | 6764 | 900 | 880 | 1290 | 1340 | 1620
|  |  | Allocated Total (Hrs) | 14644
|  |  | Contingency (Hrs) | 3261 | 18.21%
|  |  | SD Plan Total (Hrs) | 17905