## v26 tracked
WBS | Task Name | Lead | % Complete | % Work Complete | Work | Start | Finish | Plan | Notes (updated 11/1/07)
0 | NGAO System Design Phase Schedule |  | 48% | 53% | 15,840 hrs | 2006-06-21 08:00 | 2008-04-17 11:12
1 | SD Phase Management | PW | 51% | 63% | 2,164 hrs | 2006-06-21 08:00 | 2008-04-17 11:12
1.1 | Planning and Contracting | PW | 79% | 78% | 230 hrs | 2006-06-21 08:00 | 2007-11-29 15:40
1.1.1 | NGAO Proposal to SSC |  | 100% | 100% | 0 hrs | 2006-06-21 08:00 | 2006-06-21 08:00
1.1.2 | Management Structure Decision by Directors |  | 100% | 100% | 0 hrs | 2006-07-14 08:00 | 2006-07-14 08:00
1.1.3 | SD Phase System Engineering Management Plan | PW | 100% | 100% | 80 hrs | 2006-09-01 08:00 | 2006-09-29 17:00
1.1.4 | SD Phase Contracts Generated | PW | 100% | 100% | 60 hrs | 2006-09-27 08:00 | 2006-10-27 17:00
1.1.5 | Director Approval |  | 100% | 100% | 0 hrs | 2006-10-09 08:00 | 2006-10-09 08:00
1.1.6 | SD Partner Contracts Issued | PW | 100% | 100% | 0 hrs | 2006-10-27 17:00 | 2006-10-27 17:00
1.1.7 | Mid-year Replan | PW | 100% | 100% | 40 hrs | 2007-03-19 08:00 | 2007-03-27 17:00
1.1.8 | FY08 Replan | PW | 0% | 0% | 50 hrs | 2007-11-12 13:00 | 2007-11-29 15:40
1.2 | Project Meetings |  | 42% | 79% | 1,352 hrs | 2006-06-21 08:00 | 2008-04-02 17:00
1.2.1 | Executive Committee Telecons | PW... | 75% | 75% | 360 hrs | 2006-06-21 08:00 | 2008-04-02 17:00
1.2.2 | Science Advisory Committee Telecons | CM | 0% | 0% | 40 hrs | 2006-10-02 08:00 | 2008-03-27 17:00
1.2.3 | Team Meetings |  | 85% | 83% | 952 hrs | 2006-09-14 08:00 | 2008-01-09 12:00
1.2.3.1 | Team Meeting #1 (mgmt, science & technical - Irvine) |  | 100% | 100% | 68 hrs | 2006-09-14 08:00 | 2006-09-14 17:00
1.2.3.2 | Team Meeting #2 (CIT) |  | 100% | 100% | 80 hrs | 2006-11-14 08:00 | 2006-11-14 17:00
1.2.3.3 | Team Videocon #3 |  | 100% | 100% | 44 hrs | 2006-12-13 08:00 | 2006-12-13 12:00
1.2.3.4 | Team Meeting #4 (Keck) |  | 100% | 100% | 80 hrs | 2007-01-22 08:00 | 2007-01-22 17:00
1.2.3.5 | Team Videocon #5 |  | 100% | 100% | 44 hrs | 2007-03-07 08:00 | 2007-03-07 12:00
1.2.3.6 | Team Meeting #6 (UCSC) |  | 100% | 100% | 80 hrs | 2007-04-25 08:00 | 2007-04-26 17:00
1.2.3.7 | Team Videocon #7 |  | 100% | 100% | 44 hrs | 2007-05-30 13:00 | 2007-05-30 17:00
1.2.3.8 | Team Retreat #8 (UCSC) |  | 100% | 100% | 220 hrs | 2007-07-09 08:00 | 2007-07-11 12:00
1.2.3.9 | Team Videocon #9 |  | 100% | 100% | 44 hrs | 2007-08-22 08:00 | 2007-08-22 12:00
1.2.3.10 | Team Meeting #10 (CIT) |  | 100% | 100% | 80 hrs | 2007-09-11 08:00 | 2007-09-11 17:00
1.2.3.11 | Team Videocon #11 |  | 20% | 20% | 44 hrs | 2007-11-05 08:00 | 2007-11-05 12:00
1.2.3.12 | Team Meeting #12 (Keck) |  | 0% | 0% | 80 hrs | 2007-12-12 08:00 | 2007-12-12 17:00
1.2.3.13 | Team Videocon #13 |  | 0% | 0% | 44 hrs | 2008-01-09 08:00 | 2008-01-09 12:00
1.3 | Tracking and Reporting | PW | 85% | 94% | 120 hrs | 2006-09-16 17:00 | 2008-04-03 17:00
1.3.1 | Report Preparation/Presentation | PW | 85% | 94% | 120 hrs | 2006-10-02 08:00 | 2007-12-11 12:00
1.3.2 | Keck Science Meeting 06 (UCI) |  | 100% | 100% | 0 hrs | 2006-09-16 17:00 | 2006-09-16 17:00
1.3.3 | SSC meeting (UCLA) |  | 100% | 100% | 0 hrs | 2006-11-06 08:00 | 2006-11-06 08:00
1.3.4 | SSC meeting (Keck) |  | 100% | 100% | 0 hrs | 2007-01-24 08:00 | 2007-01-24 08:00
1.3.5 | SSC meeting (CA) |  | 100% | 100% | 0 hrs | 2007-04-03 08:00 | 2007-04-03 08:00
1.3.6 | SSC meeting (Keck) |  | 100% | 100% | 0 hrs | 2007-06-20 08:00 | 2007-06-20 08:00
1.3.7 | Keck Science Meeting 07 |  | 100% | 100% | 0 hrs | 2007-09-15 08:00 | 2007-09-15 08:00
1.3.8 | SSC meeting (CA) |  | 20% | 0% | 0 hrs | 2007-11-06 08:00 | 2007-11-06 08:00
1.3.9 | SSC meeting (Keck) |  | 0% | 0% | 0 hrs | 2008-01-24 08:00 | 2008-01-24 08:00
1.3.10 | SSC meeting (CA) |  | 0% | 0% | 0 hrs | 2008-04-03 17:00 | 2008-04-03 17:00
1.4 | Proposals & Fundraising |  | 0% | 0% | 0 hrs | 2006-10-27 17:00 | 2007-01-01 08:00
1.4.1 | Dates & deliverables identified by Directors |  | 0% | 0% | 0 hrs | 2006-10-27 17:00 | 2006-10-27 17:00
1.4.2 | Support Advancement Office |  | 0% | 0% | 0 hrs | 2007-01-01 08:00 | 2007-01-01 08:00
1.5 | System Design Report & Review | SA | 0% | 0% | 462 hrs | 2007-10-01 08:00 | 2008-04-17 11:12
1.5.1 | System Design Report | PW | 0% | 0% | 40 hrs | 2008-02-20 11:12 | 2008-03-03 11:12
1.5.2 | System Design Review | PW | 0% | 0% | 422 hrs | 2007-10-01 08:00 | 2008-04-17 11:12
1.5.2.1 | Identify Reviewers | SA | 0% | 0% | 12 hrs | 2007-10-01 08:00 | 2007-12-14 17:00
1.5.2.2 | Review Package Distributed | SA | 0% | 0% | 8 hrs | 2008-03-03 11:12 | 2008-03-04 11:12
1.5.2.3 | Reviewer Comments Addressed | PW | 0% | 0% | 120 hrs | 2008-03-18 11:12 | 2008-03-25 11:12
1.5.2.4 | System Design Review Support | PW | 0% | 0% | 242 hrs | 2008-03-03 11:12 | 2008-03-31 11:12
1.5.2.5 | System Design Review Meeting | SA | 0% | 0% | 0 hrs | 2008-03-31 11:12 | 2008-03-31 11:12
1.5.2.6 | Reviewer Report Received |  | 0% | 0% | 0 hrs | 2008-04-14 11:12 | 2008-04-14 11:12
1.5.2.7 | Response to Reviewer Report & Distribution | PW | 0% | 0% | 40 hrs | 2008-04-14 11:12 | 2008-04-17 11:12
2 | System Requirements | PW | 50% | 61% | 3,254 hrs | 2006-10-02 08:00 | 2007-11-02 17:00
2.1 | Science Requirements | CM | 50% | 62% | 2,890 hrs | 2006-10-02 08:00 | 2007-10-15 17:00
2.1.1 | Solar System Science Requirements | FM | 59% | 78% | 650 hrs | 2006-10-02 08:00 | 2007-08-31 17:00
2.1.1.1 | Companions & Multiplicity of Small Solar System Bodies | FM | 80% | 94% | 250 hrs | 2006-10-02 08:00 | 2007-05-15 17:00
2.1.1.1.1 | Point Source Companion Sensitivity Requirements |  | 75% | 92% | 100 hrs | 2006-10-02 08:00 | 2007-05-15 17:00
2.1.1.1.2 | Spectral Sensitivity & Spectral Resolution Requirements |  | 85% | 97% | 100 hrs | 2006-10-02 08:00 | 2007-05-15 17:00
2.1.1.1.3 | Observing Scenarios | DLM | 80% | 89% | 25 hrs | 2006-12-04 08:00 | 2007-05-15 17:00
2.1.1.1.4 | Science Instrument Requirements |  | 80% | 95% | 25 hrs | 2006-12-04 08:00 | 2007-05-15 17:00
2.1.1.2 | Moons of the Giant Planets | FM | 31% | 34% | 150 hrs | 2006-12-04 08:00 | 2007-08-31 17:00
2.1.1.2.1 | Performance Requirements |  | 10% | 17% | 100 hrs | 2006-12-04 08:00 | 2007-08-31 17:00
2.1.1.2.2 | Observing Scenarios | DLM | 50% | 72% | 25 hrs | 2007-01-29 08:00 | 2007-08-31 17:00
2.1.1.2.3 | Science Instrument Requirements |  | 40% | 61% | 25 hrs | 2007-01-29 08:00 | 2007-08-31 17:00
2.1.1.3 | Shape & Size of Asteroids | FM | 69% | 88% | 250 hrs | 2007-01-29 08:00 | 2007-05-15 17:00
2.1.1.3.1 | Spatial Resolution Requirements |  | 70% | 88% | 100 hrs | 2007-01-29 08:00 | 2007-05-15 17:00
2.1.1.3.2 | Spectral Sensitivity & Spectral Resolution Requirements |  | 80% | 95% | 100 hrs | 2007-01-29 08:00 | 2007-05-15 17:00
2.1.1.3.3 | Observing Scenarios |  | 40% | 55% | 25 hrs | 2007-03-05 08:00 | 2007-05-15 17:00
2.1.1.3.4 | Science Instrument Requirements |  | 80% | 94% | 25 hrs | 2007-03-05 08:00 | 2007-05-15 17:00
2.1.2 | Galactic Science Requirements | ML | 43% | 47% | 1,000 hrs | 2006-10-02 08:00 | 2007-08-31 17:00
2.1.2.1 | Galactic Center Proper Motions: Astrometry | AG | 61% | 68% | 200 hrs | 2006-10-02 08:00 | 2007-07-02 17:00
2.1.2.1.1 | Astrometry requirements |  | 40% | 60% | 150 hrs | 2006-10-02 08:00 | 2007-07-02 17:00
2.1.2.1.2 | Observing Scenarios |  | 75% | 92% | 25 hrs | 2006-11-27 08:00 | 2007-07-02 17:00
2.1.2.1.3 | Science Instrument Requirements |  | 75% | 92% | 25 hrs | 2006-11-27 08:00 | 2007-07-02 17:00
2.1.2.2 | Galactic Center Radial Velocities & Stellar Populations: Integral Field Spectroscopy | AG | 53% | 73% | 200 hrs | 2006-11-27 08:00 | 2007-08-01 17:00
2.1.2.2.1 | Performance Requirements |  | 50% | 71% | 150 hrs | 2006-11-27 08:00 | 2007-08-01 17:00
2.1.2.2.2 | Observing Scenarios |  | 50% | 72% | 25 hrs | 2007-01-29 08:00 | 2007-08-01 17:00
2.1.2.2.3 | Science Instrument Requirements |  | 60% | 81% | 25 hrs | 2007-01-29 08:00 | 2007-08-01 17:00
2.1.2.3 | Galactic Center Nature of Sgr A*: 3-5 um Color & 2 um Polarimetry Variability | Cancel | 10% | 0% | 0 hrs | 2007-01-29 08:00 | 2007-01-29 17:00
2.1.2.4 | Planets around Low Mass Stars & Brown Dwarfs: Companion Sensitivity | ML | 54% | 78% | 200 hrs | 2006-10-02 08:00 | 2007-06-01 17:00
2.1.2.4.1 | Companion Sensitivity Performance Requirements |  | 60% | 81% | 150 hrs | 2006-10-02 08:00 | 2007-06-01 17:00
2.1.2.4.2 | Observing Scenarios |  | 40% | 60% | 25 hrs | 2006-11-27 08:00 | 2007-06-01 17:00
2.1.2.4.3 | Science Instrument Requirements |  | 60% | 81% | 25 hrs | 2006-11-27 08:00 | 2007-06-01 17:00
2.1.2.5 | Debris Disks, Protostellar Envelopes & Outflows: Contrast | LH | 10% | 17% | 200 hrs | 2007-01-29 08:00 | 2007-07-02 17:00
2.1.2.5.1 | Contrast Performance Requirements |  | 10% | 17% | 150 hrs | 2007-01-29 08:00 | 2007-07-02 17:00
2.1.2.5.2 | Observing Scenarios |  | 10% | 17% | 25 hrs | 2007-03-05 08:00 | 2007-07-02 17:00
2.1.2.5.3 | Science Instrument Requirements |  | 10% | 17% | 25 hrs | 2007-03-05 08:00 | 2007-07-02 17:00
2.1.2.6 | Debris Disks, Protostellar Envelopes & Outflows: Polarimetry |  | 0% | 0% | 200 hrs | 2007-05-15 08:00 | 2007-08-31 17:00
2.1.2.6.1 | Polarimetry Performance Requirements |  | 0% | 0% | 150 hrs | 2007-05-15 08:00 | 2007-08-31 17:00
2.1.2.6.2 | Observing Scenarios |  | 0% | 0% | 25 hrs | 2007-05-15 08:00 | 2007-08-31 17:00
2.1.2.6.3 | Science Instrument Requirements |  | 0% | 0% | 25 hrs | 2007-05-15 08:00 | 2007-08-31 17:00
2.1.3 | Extragalactic Science Requirements | CM | 52% | 72% | 1,000 hrs | 2006-10-02 08:00 | 2007-10-01 17:00
2.1.3.1 | Resolved Stellar Populations in Crowded Fields |  | 57% | 81% | 300 hrs | 2006-10-02 08:00 | 2007-10-01 17:00
2.1.3.1.1 | Performance Requirements |  | 60% | 81% | 250 hrs | 2006-10-02 08:00 | 2007-10-01 17:00
2.1.3.1.2 | Observing Scenarios |  | 60% | 82% | 25 hrs | 2006-12-11 08:00 | 2007-10-01 17:00
2.1.3.1.3 | Science Instrument Requirements |  | 50% | 72% | 25 hrs | 2006-12-11 08:00 | 2007-10-01 17:00
2.1.3.2 | High Redshift Galaxies |  | 67% | 87% | 300 hrs | 2006-10-02 08:00 | 2007-06-01 17:00
2.1.3.2.1 | Encircled Energy (& d-IFU) Performance Requirements |  | 70% | 88% | 200 hrs | 2006-10-02 08:00 | 2007-06-01 17:00
2.1.3.2.2 | Observing Scenarios |  | 70% | 88% | 50 hrs | 2006-12-11 08:00 | 2007-06-01 17:00
2.1.3.2.3 | Science Instrument Requirements |  | 60% | 80% | 50 hrs | 2006-12-11 08:00 | 2007-06-01 17:00
2.1.3.3 | Nearby Galaxies |  | 40% | 58% | 200 hrs | 2006-12-11 08:00 | 2007-08-31 17:00
2.1.3.3.1 | Encircled Energy & PSF Performance Requirements |  | 40% | 59% | 150 hrs | 2006-12-11 08:00 | 2007-08-31 17:00
2.1.3.3.2 | Observing Scenarios |  | 20% | 32% | 25 hrs | 2007-03-05 08:00 | 2007-08-31 17:00
2.1.3.3.3 | Science Instrument Requirements |  | 60% | 80% | 25 hrs | 2007-03-05 08:00 | 2007-08-31 17:00
2.1.3.4 | Gravitational Lensing |  | 38% | 48% | 200 hrs | 2006-12-11 08:00 | 2007-07-02 17:00
2.1.3.4.1 | Encircled Energy & PSF Performance Requirements |  | 30% | 44% | 150 hrs | 2006-12-11 08:00 | 2007-07-02 17:00
2.1.3.4.2 | Observing Scenarios |  | 30% | 43% | 25 hrs | 2007-03-05 08:00 | 2007-07-02 17:00
2.1.3.4.3 | Science Instrument Requirements |  | 60% | 78% | 25 hrs | 2007-03-05 08:00 | 2007-07-02 17:00
2.1.4 | Science Case Requirements Document | CM | 33% | 37% | 240 hrs | 2006-10-02 08:00 | 2007-10-15 17:00
2.1.4.1 | Science Case Requirements Doc Rev 1 |  | 100% | 100% | 40 hrs | 2006-10-02 08:00 | 2006-10-19 17:00
2.1.4.2 | Science Case Requirements Doc Rev 2 |  | 40% | 40% | 120 hrs | 2007-04-02 08:00 | 2007-06-01 17:00
2.1.4.3 | Science Case Requirements Doc Rev 3 |  | 0% | 0% | 40 hrs | 2007-06-05 08:53 | 2007-07-09 17:00
2.1.4.4 | Science Case Requirements Doc Final |  | 0% | 0% | 40 hrs | 2007-09-26 08:53 | 2007-10-15 17:00
2.2 | Observatory Requirements | CN | 58% | 64% | 224 hrs | 2006-10-02 08:00 | 2007-09-07 17:00
2.2.1 | Development Requirements | CN | 100% | 100% | 16 hrs | 2006-10-02 08:00 | 2006-11-24 17:00
2.2.2 | Observatory Interface Requirements | CN | 100% | 100% | 24 hrs | 2006-10-02 08:00 | 2006-10-27 17:00
2.2.3 | Science Operations Requirements | DLM | 100% | 100% | 64 hrs | 2006-10-02 08:00 | 2006-11-24 17:00
2.2.4 | Observatory Requirements Rev 2 | PW | 50% | 50% | 80 hrs | 2007-01-22 08:00 | 2007-02-09 17:00
2.2.5 | Observatory Requirements Rev 3 | CN | 0% | 0% | 20 hrs | 2007-04-09 08:00 | 2007-05-18 17:00
2.2.6 | Observatory Requirements Rev 4 | CN | 0% | 0% | 20 hrs | 2007-07-16 08:00 | 2007-09-07 17:00
2.3 | System Requirements Document |  | 37% | 32% | 140 hrs | 2006-10-09 08:00 | 2007-11-02 17:00
2.3.1 | Traceability Matrix | CN | 24% | 17% | 60 hrs | 2006-10-09 08:00 | 2007-10-20 17:00
2.3.1.1 | Traceability Matrix Rev 1 | CN | 100% | 100% | 10 hrs | 2006-10-09 08:00 | 2006-10-20 17:00
2.3.1.2 | Traceability Matrix Rev 2 | PW | 0% | 0% | 10 hrs | 2007-02-12 08:00 | 2007-02-27 17:00
2.3.1.3 | Traceability Matrix Rev 3 | CN | 0% | 0% | 20 hrs | 2007-06-15 08:00 | 2007-06-28 17:00
2.3.1.4 | Traceability Matrix Rev 4 | CN | 0% | 0% | 20 hrs | 2007-10-09 08:00 | 2007-10-20 17:00
2.3.2 | System Requirements Document | PW | 46% | 44% | 80 hrs | 2006-11-27 08:00 | 2007-11-02 17:00
2.3.2.1 | SRD Rev 1 | PW | 100% | 100% | 20 hrs | 2006-11-27 08:00 | 2006-12-08 17:00
2.3.2.2 | SRD Rev 2 | PW | 75% | 76% | 20 hrs | 2007-04-16 08:00 | 2007-05-15 17:00
2.3.2.3 | SRD Rev 3 | PW | 0% | 0% | 20 hrs | 2007-08-13 08:00 | 2007-08-31 17:00
2.3.2.4 | SRD Final SD Phase Version | PW | 0% | 0% | 20 hrs | 2007-10-22 08:00 | 2007-11-02 17:00
3 | System Design | PW | 48% | 55% | 9,282 hrs | 2006-08-14 08:00 | 2008-03-21 17:00
3.1 | Systems Engineering | RD | 80% | 84% | 5,208 hrs | 2006-08-14 08:00 | 2008-01-17 15:00
3.1.1 | Performance Budgets | RD | 76% | 75% | 2,144 hrs | 2006-08-14 08:00 | 2007-11-27 15:00
3.1.1.1 | Model Assumptions | CN | 99% | 96% | 292 hrs | 2006-08-14 08:00 | 2007-09-06 11:26
3.1.1.1.1 | TMT site monitoring data mining | RF | 100% | 100% | 80 hrs | 2006-08-14 08:00 | 2007-06-29 17:00
3.1.1.1.1.1 | Tools in place & 1st release | RF | 100% | 100% | 40 hrs | 2006-08-14 08:00 | 2006-09-14 17:00
3.1.1.1.1.2 | Release updated data (every two months) | RF | 100% | 100% | 40 hrs | 2006-09-18 08:00 | 2007-06-29 17:00
3.1.1.1.2 | Telescope dynamic performance data | CN | 100% | 100% | 120 hrs | 2006-10-02 08:00 | 2006-11-30 17:00
3.1.1.1.3 | Telescope static wavefront errors | CN | 100% | 100% | 20 hrs | 2006-10-02 08:00 | 2006-11-30 17:00
3.1.1.1.4 | Sodium return vs laser format | DG | 100% | 100% | 40 hrs | 2006-11-01 08:00 | 2006-11-30 17:00
3.1.1.1.5 | Evaluate & Adopt New Model Assumptions | RD | 78% | 63% | 32 hrs | 2007-06-11 08:00 | 2007-09-06 11:26
3.1.1.1.5.1 | New Model Assumptions Rev 1 | RD | 100% | 100% | 20 hrs | 2007-06-11 08:00 | 2007-06-15 17:00
3.1.1.1.5.2 | New Model Assumptions Rev 2 | RD | 0% | 0% | 12 hrs | 2007-09-05 08:00 | 2007-09-06 11:26
3.1.1.2 | Model/Tool Validation | CN | 45% | 76% | 334 hrs | 2006-08-14 08:00 | 2007-06-29 17:00
3.1.1.2.1 | Agreement between Tomography Codes | DG | 100% | 100% | 40 hrs | 2006-08-14 08:00 | 2006-09-29 17:00
3.1.1.2.2 | Agreement between Sky Coverage Codes | RD | 100% | 100% | 40 hrs | 2006-10-16 08:00 | 2006-11-03 17:00
3.1.1.2.3 | Anchor to Keck II LGS AO PSFs | CN | 25% | 42% | 40 hrs | 2006-10-02 08:00 | 2007-06-29 17:00
3.1.1.2.4 | Anchor to On-sky MGSU Experiments | RF | 100% | 100% | 10 hrs | 2006-11-10 10:40 | 2006-11-15 17:00
3.1.1.2.5 | Anchor to LAO Lab Experiments | DG | 50% | 73% | 204 hrs | 2006-11-06 08:00 | 2007-06-29 17:00
3.1.1.3 | Throughput | AB | 100% | 100% | 32 hrs | 2006-10-02 08:00 | 2007-05-18 17:00
3.1.1.4 | Background | AB | 99% | 98% | 41 hrs | 2006-10-02 08:00 | 2007-05-18 17:00
3.1.1.4.1 | Document Proposal Analysis | AB | 25% | 25% | 1 hr | 2006-10-02 08:00 | 2006-10-02 16:12 |  | Cancelled
3.1.1.4.2 | Develop Background Performance Budget | AB | 100% | 100% | 40 hrs | 2006-10-02 08:00 | 2007-05-18 17:00
3.1.1.5 | Wavefront Error vs Sky Coverage | RD | 67% | 44% | 125 hrs | 2006-10-02 08:00 | 2007-09-28 17:00
3.1.1.5.1 | Document WFE Budget Rev 1 | RD | 100% | 100% | 55 hrs | 2006-10-02 08:00 | 2007-05-04 17:00
3.1.1.5.2 | Document WFE Budget Rev 2 | RD | 0% | 0% | 70 hrs | 2007-06-19 08:00 | 2007-09-28 17:00
3.1.1.6 | Encircled Energy vs Sky Coverage | DG | 100% | 100% | 110 hrs | 2006-10-23 08:00 | 2007-05-04 17:00
3.1.1.7 | Photometric Accuracy | MB | 100% | 100% | 240 hrs | 2006-10-16 08:00 | 2007-01-26 17:00
3.1.1.8 | Astrometric Accuracy | BC | 100% | 100% | 240 hrs | 2006-11-13 08:00 | 2007-06-29 17:00
3.1.1.9 | Polarimetric Accuracy | MI | 75% | 92% | 40 hrs | 2007-02-05 08:00 | 2007-05-25 17:00
3.1.1.10 | Companion Sensitivity | RF | 100% | 100% | 180 hrs | 2006-11-13 08:00 | 2007-05-25 17:00
3.1.1.11 | Observing Efficiency | DLM | 50% | 80% | 100 hrs | 2007-02-05 08:00 | 2007-09-28 17:00
3.1.1.12 | Observing Uptime | EJ | 25% | 23% | 80 hrs | 2007-08-27 08:00 | 2007-09-28 17:00
3.1.1.13 | Performance Budgets Summary |  | 40% | 40% | 100 hrs | 2007-05-28 08:00 | 2007-10-19 17:00
3.1.1.13.1 | Performance Budgets Summary Ver 1 | MB | 100% | 100% | 40 hrs | 2007-05-28 08:00 | 2007-06-08 17:00
3.1.1.13.2 | Performance Budgets Summary Ver 2 | MB | 0% | 0% | 60 hrs | 2007-10-01 08:00 | 2007-10-19 17:00
3.1.1.14 | Science Products |  | 0% | 0% | 230 hrs | 2007-10-01 08:00 | 2007-11-27 15:00
3.1.1.14.1 | All-In Science Simulations | CN | 0% | 0% | 80 hrs | 2007-10-01 08:00 | 2007-10-31 17:00
3.1.1.14.2 | Additional Science Characterization Results |  | 0% | 0% | 150 hrs | 2007-11-01 08:00 | 2007-11-27 15:00
3.1.1.14.2.1 | Point Source Sensitivities | AB | 0% | 0% | 30 hrs | 2007-11-01 08:00 | 2007-11-27 15:00
3.1.1.14.2.2 | PSF Uniformity & Stability | CN | 0% | 0% | 100 hrs | 2007-11-01 08:00 | 2007-11-21 17:00
3.1.1.14.2.3 | Other | RF | 0% | 0% | 20 hrs | 2007-11-19 08:00 | 2007-11-22 15:00
3.1.2 | Trade Studies | RD | 97% | 97% | 1,462 hrs | 2006-10-16 08:00 | 2007-07-27 17:00
3.1.2.1 | System Architecture Trade Studies |  | 100% | 100% | 618 hrs | 2006-10-16 08:00 | 2007-05-18 17:00
3.1.2.1.1 | MOAO & MCAO TS | DG | 100% | 100% | 80 hrs | 2006-11-13 08:00 | 2006-12-15 17:00
3.1.2.1.2 | NGAO versus Keck AO upgrades TS (meeting 5) | PW | 100% | 100% | 100 hrs | 2007-02-05 08:00 | 2007-03-02 17:00
3.1.2.1.3 | Adaptive Secondary Mirror option TS (m5) | PW | 100% | 100% | 16 hrs | 2007-04-06 08:00 | 2007-04-30 17:00
3.1.2.1.4 | K & L-band Science TS (m5) | Cancel | 0% | 0% | 1 hr | 2007-02-05 08:00 | 2007-02-05 12:00
3.1.2.1.5 | Keck Interferometer Support TS (m5) | CN | 100% | 100% | 120 hrs | 2006-10-16 08:00 | 2007-03-02 17:00
3.1.2.1.6 | Instrument Balance TS | Cancel | 0% | 0% | 1 hr | 2006-11-13 08:00 | 2006-11-14 17:00
3.1.2.1.7 | GLAO for non-NGAO Instruments TS (m5) | RF | 100% | 100% | 20 hrs | 2007-02-05 08:00 | 2007-03-02 17:00
3.1.2.1.8 | Science Instrument Re-use Cost/Benefit TS (m3) | AM | 100% | 100% | 120 hrs | 2006-11-13 08:00 | 2007-05-18 17:00
3.1.2.1.9 | Telescope Wavefront Errors TS | CN | 100% | 100% | 80 hrs | 2006-12-04 08:00 | 2006-12-20 17:00
3.1.2.1.10 | Observing Model TS | DLM | 100% | 100% | 80 hrs | 2006-11-13 08:00 | 2007-05-04 17:00
3.1.2.2 | Adaptive Optics System Trade Studies |  | 92% | 91% | 642 hrs | 2006-10-30 08:00 | 2007-07-27 17:00
3.1.2.2.1 | AO Enclosure Temperature TS (m6) | Cancel | 25% | 25% | 1 hr | 2007-01-02 08:00 | 2007-01-03 08:27
3.1.2.2.2 | Optical Relay TS (m6) | RD | 25% | 33% | 60 hrs | 2007-01-02 08:00 | 2007-06-15 17:00 |  | Cancelled
3.1.2.2.3 | Field Rotation Strategy TS (m6) | RD | 25% | 51% | 60 hrs | 2007-01-02 08:00 | 2007-06-15 17:00 |  | Cancelled
3.1.2.2.4 | Dichroics & Beamsplitters TS (m6) | Cancel | 0% | 0% | 1 hr | 2007-01-02 08:00 | 2007-01-03 09:52
3.1.2.2.5 | Rayleigh Rejection TS (m3) | VV | 100% | 100% | 72 hrs | 2006-10-30 08:00 | 2007-05-09 17:00
3.1.2.2.6 | LGS WFS Type TS (m4) | VV | 100% | 100% | 30 hrs | 2006-12-04 08:00 | 2007-01-19 17:00
3.1.2.2.7 | LGS WFS number of subapertures TS (m4) | VV | 100% | 100% | 20 hrs | 2006-12-04 08:00 | 2007-01-19 17:00
3.1.2.2.8 | Slow WFS TS (m7) | Cancel | 0% | 0% | 1 hr | 2007-04-23 08:00 | 2007-04-23 10:30
3.1.2.2.9 | LOWFS Architecture TS | RF | 100% | 100% | 220 hrs | 2006-12-04 08:00 | 2007-05-09 17:00
3.1.2.2.10 | Number & Type of LOWFS TS (m4) | RC | 100% | 100% | 60 hrs | 2006-12-04 08:00 | 2007-01-26 17:00
3.1.2.2.11 | Centroid Anisoplanatism TS (m7) | Cancel | 0% | 0% | 1 hr | 2007-04-23 08:00 | 2007-04-23 14:00
3.1.2.2.12 | Deformable Mirror Stroke Requirement TS (m6) | Cancel | 0% | 0% | 1 hr | 2007-01-02 08:00 | 2007-01-03 11:50
3.1.2.2.13 | Stand-alone vs DM on T/T Stage TS (m3) | Cancel | 50% | 50% | 1 hr | 2006-10-30 08:00 | 2006-10-30 12:00
3.1.2.2.14 | Correcting Fast T/T with DM TS | Cancel | 0% | 0% | 1 hr | 2006-12-08 10:00 | 2006-12-08 17:00
3.1.2.2.15 | Focus Compensation TS (m6) | Cancel | 0% | 0% | 1 hr | 2007-01-22 08:00 | 2007-01-24 11:44
3.1.2.2.16 | d-IFU & LOWFS AO & Object Selection TS | AM | 50% | 61% | 112 hrs | 2007-05-28 08:00 | 2007-07-27 17:00
3.1.2.3 | Laser Facility Trade Studies |  | 100% | 100% | 142 hrs | 2006-10-16 08:00 | 2007-06-22 17:00
3.1.2.3.1 | Laser Pulse Format TS (m6) | Cancel | 0% | 0% | 1 hr | 2007-01-02 08:00 | 2007-01-02 10:00
3.1.2.3.2 | Free Space vs Fiber TS (m7) | Cancel | 25% | 25% | 1 hr | 2007-01-30 08:00 | 2007-01-30 10:00
3.1.2.3.3 | LGS Asterism Geometry & Size TS (m2) | RF | 100% | 100% | 20 hrs | 2006-10-23 08:00 | 2006-10-27 17:00
3.1.2.3.4 | Variable vs fixed LGS Asterism Cost/Benefit TS (m2) | VV | 100% | 100% | 20 hrs | 2006-10-16 08:00 | 2006-10-27 17:00
3.1.2.3.5 | Uplink compensation | DG | 100% | 100% | 100 hrs | 2007-05-21 08:00 | 2007-06-22 17:00
3.1.2.4 | Trade Study Conclusions Summary | CN | 100% | 100% | 60 hrs | 2007-05-14 08:00 | 2007-06-08 17:00
3.1.3 | System Architecture | RD | 58% | 86% | 1,602 hrs | 2007-05-08 08:00 | 2008-01-17 15:00
3.1.3.1 | Candidate Subsystems | RD | 100% | 100% | 480 hrs | 2007-05-21 08:00 | 2007-06-29 17:00
3.1.3.1.1 | Define Candidate Subsystems | RD | 100% | 100% | 228 hrs | 2007-05-21 08:00 | 2007-06-01 17:00
3.1.3.1.2 | Subsystems Performance Evaluation | RD | 100% | 100% | 72 hrs | 2007-06-04 08:00 | 2007-06-15 17:00
3.1.3.1.3 | Subsystems Cost Evaluation | CN | 100% | 100% | 72 hrs | 2007-06-04 08:00 | 2007-06-15 17:00
3.1.3.1.4 | Subsystems Risk Analysis | CN | 100% | 100% | 36 hrs | 2007-06-18 08:00 | 2007-06-22 17:00
3.1.3.1.5 | Organize Candidate Subsystems | RD | 100% | 100% | 72 hrs | 2007-06-25 08:00 | 2007-06-29 17:00
3.1.3.2 | Candidate Architectures | RD | 100% | 100% | 556 hrs | 2007-07-09 08:00 | 2007-08-17 17:00
3.1.3.2.1 | Define Candidate Architectures | RD | 100% | 100% | 328 hrs | 2007-07-09 08:00 | 2007-07-20 17:00
3.1.3.2.2 | Architectures Performance Evaluation | RD | 100% | 100% | 72 hrs | 2007-07-23 08:00 | 2007-08-03 17:00
3.1.3.2.3 | Architectures Cost Evaluation | CN | 100% | 100% | 72 hrs | 2007-07-23 08:00 | 2007-08-03 17:00
3.1.3.2.4 | Architecture Risk Analysis | CN | 100% | 100% | 36 hrs | 2007-08-06 08:00 | 2007-08-10 17:00
3.1.3.2.5 | Adopt Baseline Architecture(s) | RD | 100% | 100% | 48 hrs | 2007-08-13 08:00 | 2007-08-17 17:00
3.1.3.3 | Functional Requirements | PW | 42% | 62% | 520 hrs | 2007-05-08 08:00 | 2008-01-17 15:00
3.1.3.3.1 | Draft Functional Requirements Document | PW | 100% | 100% | 20 hrs | 2007-05-22 14:11 | 2007-05-31 17:00
3.1.3.3.2 | AO System Functional Requirements Ver 1 | CN | 100% | 100% | 160 hrs | 2007-07-09 08:00 | 2007-08-17 17:00
3.1.3.3.3 | AO System Functional Requirements Ver 2 | CN | 25% | 25% | 80 hrs | 2007-10-29 08:00 | 2007-11-30 17:00
3.1.3.3.4 | Laser System Functional Requirements Ver 1 | VV | 100% | 100% | 96 hrs | 2007-07-09 08:00 | 2007-08-03 17:00 |  | Changed lead from JC to VV
3.1.3.3.5 | Laser System Functional Requirements Ver 2 | VV | 40% | 55% | 48 hrs | 2007-10-29 08:00 | 2007-11-30 17:00 |  | Changed lead from JC to VV
3.1.3.3.6 | Science Operations Functional Requirements Ver 1 | DLM | 0% | 0% | 50 hrs | 2007-08-06 08:00 | 2007-08-31 17:00
3.1.3.3.7 | Science Operations Functional Requirements Ver 2 | DLM | 0% | 0% | 50 hrs | 2007-10-29 08:00 | 2007-11-30 17:00
3.1.3.3.8 | Science Instruments Function Allocation Ver 1 | SA | 0% | 0% | 8 hrs | 2007-05-08 08:00 | 2007-05-31 17:00
3.1.3.3.9 | Science Instruments Function Allocation Ver 2 | SA | 0% | 0% | 8 hrs | 2008-01-14 08:00 | 2008-01-17 15:00
3.1.3.4 | Technology Drivers Summary | Cancel | 0% | 0% | 1 hr | 2007-10-25 15:11 | 2007-10-25 17:00
3.1.3.5 | Technical Risk Analysis Ver 1 | CN | 100% | 100% | 20 hrs | 2007-08-27 08:00 | 2007-09-14 17:00
3.1.3.6 | Technical Risk Analysis Ver 2 | CN | 0% | 0% | 25 hrs | 2007-12-03 08:00 | 2007-12-28 17:00
3.2 | AO System | DG | 16% | 16% | 1,709 hrs | 2007-05-29 08:00 | 2007-12-14 17:00
3.2.1 | AO System Architecture | DG | 60% | 60% | 40 hrs | 2007-09-04 08:00 | 2007-11-23 17:00
3.2.2 | AO Enclosure | JM | 2% | 2% | 40 hrs | 2007-10-01 08:00 | 2007-11-07 17:00
3.2.3 | Opto-mechanical | BB | 15% | 14% | 959 hrs | 2007-05-29 08:00 | 2007-12-14 17:00
3.2.3.1 | Field Rotation | BB | 40% | 40% | 45 hrs | 2007-09-04 08:00 | 2007-11-02 17:00
3.2.3.2 | Optical Relay | BB | 40% | 42% | 60 hrs | 2007-09-04 08:00 | 2007-11-02 17:00
3.2.3.3 | Optical Switchyard | BB | 2% | 2% | 50 hrs | 2007-09-04 08:00 | 2007-11-02 17:00
3.2.3.4 | Optical Support Structure | BB | 5% | 5% | 45 hrs | 2007-11-05 08:00 | 2007-11-30 17:00
3.2.3.5 | Wavefront Sensors | VV | 9% | 12% | 240 hrs | 2007-08-22 15:52 | 2007-11-16 17:00
3.2.3.5.1 | High Order LGS Wavefront Sensors | VV | 10% | 10% | 80 hrs | 2007-08-22 15:52 | 2007-11-16 17:00
3.2.3.5.2 | High Order NGS Wavefront Sensor | VV | 15% | 15% | 40 hrs | 2007-08-22 15:52 | 2007-11-16 17:00
3.2.3.5.3 | Low Order NGS Wavefront Sensors | VV | 5% | 16% | 80 hrs | 2007-08-22 15:52 | 2007-11-16 17:00
3.2.3.5.4 | Calibration Wavefront Sensor | CN | 5% | 5% | 40 hrs | 2007-08-22 15:52 | 2007-11-16 17:00
3.2.3.6 | Wavefront Correctors | CN | 2% | 10% | 115 hrs | 2007-08-13 08:00 | 2007-11-30 17:00
3.2.3.6.1 | Tip/Tilt Corrector | BB | 2% | 2% | 20 hrs | 2007-10-01 08:00 | 2007-11-30 17:00
3.2.3.6.2 | Deformable Mirror | CN | 2% | 3% | 50 hrs | 2007-08-13 08:00 | 2007-09-21 17:00
3.2.3.6.3 | Tip/tilt Vibration Mitigation | CN | 2% | 21% | 45 hrs | 2007-08-22 15:52 | 2007-09-28 17:00
3.2.3.7 | Acquisition Cameras | CN | 50% | 50% | 40 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.2.3.7.1 | NGS Acquisition Camera | CN | 50% | 50% | 20 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.2.3.7.2 | LGS Acquisition Camera | CN | 50% | 50% | 20 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.2.3.8 | Atmospheric Dispersion Correction | RD | 30% | 42% | 24 hrs | 2007-08-21 08:00 | 2007-12-14 17:00
3.2.3.9 | Alignment, Calibration, Diagnostics, Metrology and Monitoring | CN | 25% | 25% | 60 hrs | 2007-05-29 08:00 | 2007-06-29 17:00
3.2.3.10 | Atmospheric Profiler | MB | 2% | 2% | 50 hrs | 2007-08-22 15:52 | 2007-10-02 17:00
3.2.3.11 | d-IFU & LOWFS AO & Object Selection | AM | 0% | 0% | 200 hrs | 2007-08-22 15:52 | 2007-11-07 17:00
3.2.3.12 | PSF Monitoring Camera | MB | 2% | 11% | 30 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.2.4 | Non-real-time Control | EJ | 10% | 17% | 330 hrs | 2007-06-25 08:00 | 2007-11-22 17:00
3.2.4.1 | Non-RTC Software | EJ | 10% | 12% | 170 hrs | 2007-06-25 08:00 | 2007-08-31 17:00
3.2.4.2 | Non-RTC Electronics | EJ | 10% | 22% | 160 hrs | 2007-07-23 08:00 | 2007-11-22 17:00
3.2.5 | Real-time Control | DG | 16% | 18% | 340 hrs | 2007-08-01 08:00 | 2007-12-03 17:00
3.2.5.1 | RTC Architecture Analysis and Design Study | DG | 20% | 20% | 180 hrs | 2007-08-01 08:00 | 2007-08-31 17:00
3.2.5.2 | RTC Software Module Definition | EJ | 10% | 10% | 80 hrs | 2007-09-03 08:00 | 2007-12-03 17:00
3.2.5.3 | RTC Hardware Module Definition | MR | 20% | 20% | 80 hrs | 2007-09-03 08:00 | 2007-12-03 17:00
3.3 | Laser Facility |  | 9% | 10% | 570 hrs | 2007-08-06 08:00 | 2007-12-19 17:00
3.3.1 | Laser System Architecture | VV | 25% | 25% | 80 hrs | 2007-08-27 08:00 | 2007-10-19 17:00
3.3.2 | Laser Enclosure | JM | 10% | 10% | 80 hrs | 2007-10-22 08:00 | 2007-12-19 17:00
3.3.3 | Laser | DG | 10% | 10% | 20 hrs | 2007-10-22 08:00 | 2007-12-07 17:00
3.3.4 | Laser Launch Facility | VV | 4% | 6% | 200 hrs | 2007-08-06 08:00 | 2007-09-07 17:00
3.3.4.1 | Laser Beam Transport | CN | 2% | 2% | 50 hrs | 2007-08-06 08:00 | 2007-09-07 17:00
3.3.4.2 | Laser Pointing & Diagnostics | VV | 5% | 9% | 80 hrs | 2007-08-06 08:00 | 2007-09-07 17:00
3.3.4.3 | Laser Launch Telescope | VV | 5% | 6% | 70 hrs | 2007-08-06 08:00 | 2007-09-07 17:00
3.3.5 | Laser Safety Systems | JC | 6% | 6% | 40 hrs | 2007-10-08 08:00 | 2007-11-02 17:00
3.3.5.1 | Personnel and Equipment Safety Systems | JC | 10% | 10% | 20 hrs | 2007-10-08 08:00 | 2007-11-02 17:00
3.3.5.2 | Aircraft, Satellite & Laser Traffic Control Safety Systems | JC | 2% | 2% | 20 hrs | 2007-10-08 08:00 | 2007-11-02 17:00
3.3.6 | Laser System Control | JC | 8% | 8% | 150 hrs | 2007-10-01 08:00 | 2007-12-14 17:00
3.3.6.1 | Laser System Software | EJ | 10% | 10% | 80 hrs | 2007-10-01 08:00 | 2007-12-14 17:00
3.3.6.2 | Laser System Electronics | JC | 5% | 5% | 70 hrs | 2007-10-01 08:00 | 2007-12-14 17:00
3.4 | Science Operations | DLM | 5% | 6% | 790 hrs | 2007-05-22 08:00 | 2007-12-14 17:00
3.4.1 | Astronomical Observations Operations | DLM | 9% | 12% | 340 hrs | 2007-05-28 08:00 | 2007-12-14 17:00
3.4.1.1 | Pre-Observing Interfaces | DLM | 50% | 40% | 60 hrs | 2007-07-26 08:00 | 2007-08-24 17:00
3.4.1.1.1 | AO Guide Star Interface | EM | 80% | 80% | 20 hrs | 2007-07-26 08:00 | 2007-08-24 17:00
3.4.1.1.2 | Science Observations Simulation Tools | EM | 20% | 20% | 40 hrs | 2007-07-26 08:00 | 2007-08-24 17:00
3.4.1.2 | Observing Interfaces | DLM | 6% | 6% | 80 hrs | 2007-05-28 08:00 | 2007-12-14 17:00
3.4.1.2.1 | Acquisition | EM | 10% | 10% | 20 hrs | 2007-05-28 08:00 | 2007-07-25 17:00
3.4.1.2.2 | Observing Sequences | EM | 10% | 10% | 20 hrs | 2007-05-28 08:00 | 2007-07-25 17:00
3.4.1.2.3 | Instrument, AO & Telescope Observer Interfaces | EJ | 2% | 2% | 20 hrs | 2007-05-28 08:00 | 2007-07-25 17:00
3.4.1.2.4 | Science Data Quality Monitoring | EM | 2% | 2% | 20 hrs | 2007-10-17 08:00 | 2007-12-14 17:00
3.4.1.3 | Post-Observing Interfaces | DLM | 2% | 5% | 200 hrs | 2007-10-01 08:00 | 2007-11-30 17:00
3.4.1.3.1 | Generic Data Products | EM | 2% | 2% | 20 hrs | 2007-10-01 08:00 | 2007-11-27 17:00
3.4.1.3.2 | Science Data Quality Assessment | EM | 2% | 2% | 20 hrs | 2007-10-01 08:00 | 2007-11-27 17:00
3.4.1.3.3 | Science Data Archiving | EM | 2% | 2% | 40 hrs | 2007-10-01 08:00 | 2007-11-27 17:00
3.4.1.3.4 | PSF Reconstruction | DLM | 2% | 7% | 120 hrs | 2007-10-01 08:00 | 2007-11-30 17:00
3.4.2 | AO-Instrument Operations | DLM | 2% | 2% | 450 hrs | 2007-05-22 08:00 | 2007-10-26 17:00
3.4.2.1 | AO-Instrument Operations Architecture | DLM | 2% | 2% | 270 hrs | 2007-05-22 08:00 | 2007-10-26 17:00
3.4.2.1.1 | AO-Instrument Observing Modes | DLM | 2% | 2% | 80 hrs | 2007-05-22 08:00 | 2007-06-22 17:00
3.4.2.1.2 | AO-Instrument Operations Support | DLM | 2% | 2% | 20 hrs | 2007-06-25 08:00 | 2007-07-13 17:00
3.4.2.1.3 | AO-Instrument Configuration & Setup | DLM | 2% | 2% | 20 hrs | 2007-07-05 08:00 | 2007-10-26 17:00
3.4.2.1.4 | AO-Instrument Calibrations | MvD | 2% | 2% | 20 hrs | 2007-06-04 08:00 | 2007-09-25 17:00
3.4.2.1.5 | AO-Instrument Nighttime Operation Modes | DLM | 2% | 2% | 20 hrs | 2007-06-04 08:00 | 2007-09-25 17:00
3.4.2.1.6 | AO-Instrument Science Acquisition & Control | EM | 2% | 2% | 20 hrs | 2007-07-02 08:00 | 2007-10-23 17:00
3.4.2.1.7 | AO-Instrument Health Monitoring & Automated Recovery | EJ | 2% | 2% | 20 hrs | 2007-06-11 08:00 | 2007-10-02 17:00
3.4.2.1.8 | AO-Instrument Laser Traffic Control | DS | 2% | 2% | 10 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.4.2.1.9 | AO-Instrument User Interfaces | EJ | 2% | 2% | 40 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.4.2.1.10 | AO-Instrument Maintenance Plan | EJ | 2% | 2% | 20 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.4.2.2 | AO-Instrument Operations Optimization | DLM | 2% | 2% | 180 hrs | 2007-06-18 08:00 | 2007-07-27 17:00
3.4.2.2.1 | AO-Instrument Performance Prediction | MvD | 2% | 2% | 80 hrs | 2007-06-18 08:00 | 2007-07-27 17:00
3.4.2.2.2 | AO-Instrument Real-Time Optimization | MvD | 2% | 2% | 80 hrs | 2007-06-18 08:00 | 2007-07-27 17:00
3.4.2.2.3 | AO-Instrument Environment Monitoring | EJ | 2% | 2% | 20 hrs | 2007-06-18 08:00 | 2007-07-06 17:00
3.5 | Science Instruments | SA | 31% | 14% | 865 hrs | 2006-10-02 08:00 | 2008-03-21 17:00
3.5.1 | Instrument Requirements & Initial Definitions | SA | 50% | 50% | 132 hrs | 2007-04-09 08:00 | 2008-01-25 17:00
3.5.1.1 | Top Level Instrument Requirements & Definitions | SA | 93% | 77% | 16 hrs | 2007-04-09 08:00 | 2007-05-04 17:00
3.5.1.2 | Instrument Suite Version 1 | SA | 0% | 0% | 13 hrs | 2007-05-07 08:00 | 2007-05-24 12:00
3.5.1.2.1 | Instrument Function Allocation Review with Science Team | SA | 100% | 100% | 3 hrs | 2007-05-07 08:00 | 2007-05-07 17:00
3.5.1.2.2 | Summary Descriptions of Instruments | SA | 0% | 0% | 10 hrs | 2007-05-08 08:00 | 2007-05-24 12:00 |  | Expect to complete initial report 10/1/07
3.5.1.3 | Instrument Suite Version 2 | SA | 0% | 0% | 23 hrs | 2008-01-10 08:00 | 2008-01-25 17:00
3.5.1.3.1 | Instrument Review with Science Team | SA | 0% | 0% | 3 hrs | 2008-01-10 08:00 | 2008-01-11 17:00
3.5.1.3.2 | Revised Summary Descriptions of Instruments | SA | 0% | 0% | 20 hrs | 2008-01-14 08:00 | 2008-01-25 17:00
3.5.1.4 | Instrument Interfaces | SA | 0% | 0% | 80 hrs | 2007-06-06 08:00 | 2007-06-29 17:00
3.5.1.4.1 | Hardware Instrument Interfaces | SA | 0% | 0% | 40 hrs | 2007-06-06 08:00 | 2007-06-22 17:00
3.5.1.4.2 | Software Instrument Interfaces | SA | 60% | 75% | 40 hrs | 2007-06-12 08:00 | 2007-06-29 17:00
3.5.2 | Deployable NIR IFU (DNIRI) | SA | 100% | 100% | 278 hrs | 2007-05-07 08:00 | 2008-03-07 17:00
3.5.2.1 | DNIRI Concept Development | SA | 97% | 98% | 50 hrs | 2007-05-07 08:00 | 2007-06-15 17:00 |  | Expect to complete initial report 10/1/07
3.5.2.2 | DNIRI AO Interface Issues | SA | 100% | 100% | 40 hrs | 2007-06-18 08:00 | 2007-07-03 17:00
3.5.2.2.1 | Object Selection for DNIRI | SA | 80% | 80% | 32 hrs | 2007-06-18 08:00 | 2007-06-29 17:00
3.5.2.2.2 | AO Design for DNIRI | SA | 80% | 95% | 4 hrs | 2007-07-02 08:00 | 2007-07-02 17:00
3.5.2.2.3 | DNIRI AO Boundary | SA | 100% | 100% | 4 hrs | 2007-07-03 08:00 | 2007-07-03 17:00
3.5.2.3 | DNIRI Spectrograph Concepts | SA | 100% | 100% | 60 hrs | 2007-07-04 08:00 | 2007-08-07 17:00
3.5.2.4 | DNIRI Imager Concepts | SA | 0% | 0% | 60 hrs | 2007-07-04 08:00 | 2007-08-07 17:00
3.5.2.5 | DNIRI Concept Review with AO Team | SA | 0% | 0% | 8 hrs | 2007-08-08 08:00 | 2007-08-08 17:00
3.5.2.6 | DNIRI Report ver 1 | SA | 0% | 0% | 40 hrs | 2007-08-10 08:00 | 2007-09-18 17:00
3.5.2.7 | DNIRI Report ver 2 | SA | 42% | 45% | 20 hrs | 2008-01-25 08:00 | 2008-03-07 17:00
3.5.3 | Single Object Imagers/Low Resolution Spectrographs (SOI/LRS) | SA | 50% | 50% | 139 hrs | 2007-05-07 08:00 | 2008-03-10 17:00
3.5.3.1 | SOI/LRS Coronagraph Requirements | SA | 50% | 50% | 20 hrs | 2007-05-07 08:00 | 2007-06-01 17:00 |  | First draft completed, part of initial report
3.5.3.2 | SOI/LRS Spectrograph Requirements | SA | 50% | 83% | 5 hrs | 2007-06-04 08:00 | 2007-06-15 17:00 |  | First draft completed, part of initial report
3.5.3.3 | SOI/LRS Concept Development | SA | 0% | 0% | 24 hrs | 2007-06-18 08:00 | 2007-06-29 17:00 |  | First draft completed, part of initial report
3.5.3.4 | SOI/LRS Concept Review | SA | 0% | 0% | 6 hrs | 2007-07-02 08:00 | 2007-07-03 17:00
3.5.3.4.1 | SOI/LRS Concept Review with Science Team | SA | 0% | 0% | 3 hrs | 2007-07-02 08:00 | 2007-07-02 17:00
3.5.3.4.2 | SOI/LRS Concept Review with AO Team | SA | 41% | 36% | 3 hrs | 2007-07-03 08:00 | 2007-07-03 17:00
3.5.3.5 | SOI/LRS Reports | SA | 50% | 50% | 84 hrs | 2007-07-05 08:00 | 2008-03-10 17:00
3.5.3.5.1 | SOI/LRS Near-IR ver 1 | SA | 50% | 50% | 30 hrs | 2007-07-05 08:00 | 2007-10-16 17:00 |  | Expect to complete initial report 10/1/07
3.5.3.5.2 | SOI/LRS Visibile ver 1 | SA | 0% | 0% | 30 hrs | 2007-07-06 08:00 | 2007-10-17 17:00 |  | Expect to complete initial report 10/1/07
3.5.3.5.3 | SOI/LRS Near-IR ver 2 | SA | 0% | 0% | 12 hrs | 2008-01-25 08:00 | 2008-02-15 17:00
3.5.3.5.4 | SOI/LRS Visible ver 2 | SA | 4% | 2% | 12 hrs | 2008-02-18 08:00 | 2008-03-10 17:00
3.5.4 | Single Object IFUs (SOIFU) | SA | 50% | 50% | 134 hrs | 2007-04-30 08:00 | 2008-02-29 17:00
3.5.4.1 | Near-IR IFU Requirements Review | SA | 0% | 0% | 5 hrs | 2007-04-30 08:00 | 2007-05-11 17:00 |  | Expect to complete initial report 10/1/07
3.5.4.2 | Visible IFU Requirements Review | SA | 0% | 0% | 8 hrs | 2007-09-18 08:00 | 2007-10-16 17:00
3.5.4.3 | Visible IFU Concept Development | SA | 0% | 0% | 45 hrs | 2007-10-17 08:00 | 2007-11-28 17:00
3.5.4.4 | SOIFU Concept Review | SA | 0% | 0% | 6 hrs | 2007-11-29 08:00 | 2007-11-30 17:00
3.5.4.4.1 | SOIFU Concept Review with Science Team | SA | 0% | 0% | 3 hrs | 2007-11-29 08:00 | 2007-11-29 17:00
3.5.4.4.2 | SOIFU Concept Review with AO Team | SA | 0% | 0% | 3 hrs | 2007-11-30 08:00 | 2007-11-30 17:00
3.5.4.5 | Single Object IFU Reports | SA | 0% | 0% | 70 hrs | 2007-12-03 08:00 | 2008-02-29 17:00
3.5.4.5.1 | SOIFU Near-IR ver 1 | SA | 0% | 0% | 12 hrs | 2007-12-03 08:00 | 2007-12-14 17:00
3.5.4.5.2 | SOIFU Visible ver 1 | SA | 0% | 0% | 30 hrs | 2007-12-17 08:00 | 2008-01-11 17:00
3.5.4.5.3 | SOIFU Near-IR ver 2 | SA | 0% | 0% | 8 hrs | 2008-01-28 08:00 | 2008-02-08 17:00
3.5.4.5.4 | SOIFU Visible ver 2 | SA | 0% | 0% | 20 hrs | 2008-02-18 08:00 | 2008-02-29 17:00
3.5.5 | Special Purpose High Contrast Instrument (HCI) | SA | 0% | 0% | 61 hrs | 2008-01-10 08:00 | 2008-03-21 17:00
3.5.5.1 | HCI Requirements Development | SA | 0% | 0% | 13 hrs | 2008-01-10 08:00 | 2008-02-21 17:00
3.5.5.2 | HCI Concept Development | SA | 0% | 0% | 40 hrs | 2008-02-22 08:00 | 2008-03-20 17:00
3.5.5.3 | HCI Concept & Need Review with Science Team | SA | 25% | 14% | 8 hrs | 2008-03-21 08:00 | 2008-03-21 17:00
3.5.6 | Interferometer | CN | 0% | 0% | 80 hrs | 2006-10-02 08:00 | 2007-10-30 17:00
3.5.7 | OHANA | CN | 0% | 0% | 40 hrs | 2007-02-01 08:00 | 2007-04-11 17:00
3.5.8 | Thermal Near-IR Imager | Cancel | 66% | 43% | 1 hr | 2007-07-09 08:00 | 2007-07-24 16:00
3.6 | System Design Manual (SDM) | PW | 100% | 100% | 140 hrs | 2007-08-13 08:00 | 2008-02-05 13:57
3.6.1 | SDM v1 | PW | 0% | 0% | 60 hrs | 2007-08-13 08:00 | 2007-09-14 17:00
3.6.2 | SDM v2 | PW | 14% | 5% | 80 hrs | 2008-01-17 15:00 | 2008-02-05 13:57
4 | Systems Engineering Management Plan (SEMP) | PW | 14% | 5% | 1,140 hrs | 2007-03-05 08:00 | 2008-02-20 11:12
4.1 | Project Plan | PW | 0% | 0% | 480 hrs | 2007-09-25 13:00 | 2007-12-20 09:09
4.1.1 | WBS and Task Definition | PW | 0% | 0% | 200 hrs | 2007-09-25 13:00 | 2007-11-12 12:00
4.1.2 | Cost Estimation | PW | 0% | 0% | 160 hrs | 2007-10-26 08:00 | 2007-11-30 13:34
4.1.3 | Major Project Milestones | PW | 0% | 0% | 30 hrs | 2007-10-26 08:00 | 2007-11-05 13:34
4.1.4 | Develop Full Schedule (MS Project Plan) | PW | 0% | 0% | 90 hrs | 2007-11-30 13:34 | 2007-12-20 09:09
4.2 | Risk Assessment & Management Plan | DG | 0% | 0% | 40 hrs | 2007-09-25 08:00 | 2007-11-09 17:00
4.3 | Preliminary Design Phase Plan | PW | 64% | 26% | 200 hrs | 2007-03-05 08:00 | 2008-01-24 14:43
4.3.1 | Preliminary Design Phase Plan Version 1 (to Support Observatory FY08 Planning) | PW | 100% | 100% | 40 hrs | 2007-03-05 08:00 | 2007-05-18 17:00
4.3.2 | Preliminary Design Phase Plan Version 2 | PW | 10% | 15% | 80 hrs | 2007-11-12 13:00 | 2007-12-07 10:00
4.3.3 | Preliminary Design Phase Plan Final Version | PW | 0% | 0% | 80 hrs | 2008-01-03 09:09 | 2008-01-24 14:43
4.4 | Integration and Test Plans | CN | 0% | 0% | 180 hrs | 2007-10-26 08:00 | 2008-02-01 11:12
4.4.1 | Subsystem Testing Plans | CN | 0% | 0% | 80 hrs | 2007-10-26 08:00 | 2008-02-01 11:12
4.4.1.1 | AO System Test Plan | CN | 0% | 0% | 20 hrs | 2007-10-26 08:00 | 2007-11-20 13:48
4.4.1.2 | Laser System Test Plan | CN | 0% | 0% | 20 hrs | 2007-11-20 13:48 | 2007-12-14 09:36
4.4.1.3 | Science Operations Test Plan | DLM | 0% | 0% | 20 hrs | 2007-12-14 09:36 | 2008-01-08 15:24
4.4.1.4 | Science Instruments Test Plan | SA | 0% | 0% | 20 hrs | 2008-01-08 15:24 | 2008-02-01 11:12
4.4.2 | System Integration & Test Plans | CN | 0% | 0% | 100 hrs | 2007-12-03 08:00 | 2008-01-31 17:00
4.5 | Configuration Management Plan | EJ | 0% | 0% | 80 hrs | 2007-10-26 08:00 | 2008-01-18 12:00
4.6 | Project Management Plan | PW | 0% | 0% | 80 hrs | 2007-12-20 09:09 | 2008-01-17 09:09
4.7 | SEMP Document | PW | 0% | 0% | 80 hrs | 2008-02-01 11:12 | 2008-02-20 11:12
| = Started | [6 empty] | R | = Work Scope Plan Required
| = Complete | [7 empty] | = Draft submitted
= Work Scope Approved
= Due within 1 month
= Overdue
= Complete
= Started
= Should have started.

## v26 Replan Changes
WBS | Task | Change | Actuals | v26-v24
Changes between v20 & v24
|  | Changes between v24 & v25. Total increase (h) = |  | 31
Changes between v25 & v26. Total increase (h) =
1.1.7 | Mid-yr Replan | Move start to 3/19. End to 3/27.
1.2.2 | Science Advisory Committee Telecons | Cancel? Change to science meetings?
1.2.3.6 | Team Meeting #6 (UCSC) | Change date from 4/18 to 4/25&26
1.3.7 | Keck Science Meeting | Move ahead 1 week
1.5.2.1 | Identify Reviewers | Remove 1h task for RD,DG,CM |  | -3
1.5.2.4 | System Design Review support | Remove 8h of SK
2.1.1.1 | Companions & Multiplicity of Small Solar System Bodies | New end date for all subtasks 5/15/07. FM lead
2.1.1.1.3 | Observing Scenarios | Change lead & hrs to DLM
2.1.1.2 | Moons of the Giant Planets | New end date for all subtasks 8/31/07. FM lead
2.1.1.2.3 | Observing Scenarios | Change lead & hrs to DLM
2.1.1.3 | Shape & Size of Asteroids | New end date for all subtasks 5/15/07. FM lead
2.1.2.1 | Galactic Center Proper Motions: Astrometry | End date for 2.1.2.1.1 ?. New end date for rest of 7/2/07. Changed all to 7/2/7
2.1.2.2 | Galactic Center Radial Velocities & Stellar Populations: Integral Field Spectroscopy | New end date for all subtasks 8/1/07
2.1.2.3 | Galactic Center Nature of Sgr A*: 3-5 um Color & 2 um Polarimetry Variability | Cancel. Remove 200h of student2 effort.
2.1.2.4 | Planets around Low Mass Stars & Brown Dwarfs: Companion Sensitivity | New end date for all subtasks 6/1/07
2.1.2.5 | Debris Disks, Protostellar Envelopes & Outflows: Contrast | New end date for all subtasks 7/2/07
2.1.2.6 | Debris Disks, Protostellar Envelopes & Outflows: Polarimetry | New end date for all subtasks 8/31/07. Change start date to 5/15/07
2.1.3.1 | Resolved Stellar Populations in Crowded Fields | New end date for all subtasks 10/1/07
2.1.3.2 | High Redshift Galaxies | New end date for all subtasks 6/1/07
2.1.3.3 | Nearby Galaxies | New end date for all subtasks 8/31/07
2.1.3.4 | Gravitational Lensing | New end date for all subtasks 7/2/07
2.1.4 | Science Requirements Summary | Change name to Science Case Requirements Document
2.1.4.2 | Science Requirements Summary Rev 2 | New end date of 6/1/07. New start 4/2.
2.1.4.3 | Science Requirements Summary Rev 3 | New end date of 7/9/07
2.2.3 | Science Operations Requirements | Change end date to 5/8/07
2.2.4 | Observatory Reqments rev 2 | Change lead to PW.
2.2.5 | Observatory Reqments rev 3 | Remove 2.2.4 as predecessor
2.2.6 | Observatory Reqments rev 4 | Remove 2.2.5 as predecessor
2.3.1 | Traceability Matrix | Do we need this?
2.3.1.2 | Traceability Matrix rev 2 | Reduce from 80h total to 10h of Wizinowich. PW as lead
2.3.2 | SRD | Change lead of all subtasks & hrs to PW.
2.3.2.1 | SRD Rev 1 | Remove 2.2.3 as a precursor
2.3.2.2 | SRD Rev 2 | Change start to 4/16 & end to 5/15/07. Change predecessor from SCRD2 to 1.
2.3.2.3 | SRD Rev 3 | Change start to 7/17 & end to 7/30/07.
2.3.2.3 | SRD Rev 3 | Change to 8/13-8/31
3.1.1.1.5 | Evaluate & Adopt New Model Assumptions | New task. RD as lead.
3.1.1.1.5.1 | New Model Assumptions Rev 1 | 4h RD, 12h RF, 4H CN. 6/11-15/07 |  | 20
3.1.1.1.5.2 | New Model Assumptions Rev 2 | 4h RD, 4h RF, 4H CN. 9/5-6/07 |  | 12
3.1.1.2.3 | Anchor to Keck II LGS AO PSFs | Change end date to 6/29/07
3.1.1.2.3 | Anchor to Keck II LGS AO PSFs | Consider reducing since TMT doing this with CfAO funding. Still need CN to bring results back to NGAO
3.1.1.2.5 | Anchor to LAO Lab Experiments | Change end date to 6/29/07
3.1.1.2.5 | Anchor to LAO Lab Experiments | Changed RF 40h to RD
3.1.1.3 | Throughput | Change end date to 5/18/07
3.1.1.4.1 | Document Background proposal analysis | Cancel
3.1.1.4.2 | Develop Background performance budget | Change end date to 5/18/07
3.1.1.5.1 | WFE Budget Rev 1 | Change end date to 5/4/07
3.1.1.5.1 | WFE Budget Rev 1 | Added 15h of MB |  | 15
3.1.1.5.2 | WFE Budget Rev 2 | Change predecessor from 3.1.1.2 to 3.1.1.2.1 & 3.1.1.2.2. Change dates: 6/18-9/28/07
3.1.1.5.2 | WFE Budget Rev 2 | Changed RF to MB (30h). Added 3.1.3.2.5 as predecessor to finish.
3.1.1.6 | Encircled Energy | Change end date to 5/4/07
3.1.1.6 | Encircled Energy | Swapped RD & DG hours.
3.1.1.9 | Polarimetric Accuracy | Change end date to 5/25/07
3.1.1.10 | Companion Sensitivity | Change end date to 5/25/07
3.1.1.10 | Companion Sensitivity | Reduce BM from 100 to 30h, increase RF from 60 to 130h, Reduce CN from 80 to 10h, add RD at 10h
3.1.1.11 | Observing Efficiency | Change end date to 9/28/07
3.1.1.12 | Observing Uptime | Move to 8/27-9/28/07
3.1.1.13.1 | Performance budgets summary ver 1 | Change predecessor from 3.1.1.5 to 3.1.1.5.1. MB new lead. Replace 40h of RD with MB; remove 60h of CN. Move in end date to 6/8/7
3.1.1.13.2 | Performance budgets summary ver 2 | MB new lead. Add 3.1.1.12 as predecessor. Replace 40h of CN with 40h of MB
3.1.1.14.1 | All-in Science Simulations | Reduce CN & RF each by 40h
3.1.1.14.1 | All-in Science Simulations | Changing predecessor from 3.1.1.13.2 to 3.1.1.5.2. Move start date from 10/22 to 10/1/07 & end date to 10/31.
3.1.1.14.1 | All-in Science Simulations | This task is not completed in time for SCRD v4. Is this ok or should we delay SCRD v4 or ?
3.1.1.14.2.2 | PSF Uniformity & Stability | Added 20h MB to help identify what is needed to assess impact on performance budgets |  | 20
3.1.1.14.2.3 | Other | Reduce RF from 80 to 20h. End date changed to 11/22
3.1.2.1.3 | ASM Option | Change end date to 4/30/07 & start to 4/6. Remove 24h of BB
3.1.2.1.4 | K & L-band Science | Cancelled
3.1.2.1.6 | Instrument balance | Cancelled
3.1.2.1.7 | GLAO for non-NGAO instruments |  | 45 vs 20h
3.1.2.1.8 | Science Instrument reuse | Change end date to 5/18/07. AM new lead.
3.1.2.1.10 | Observing model | Change end date to 5/4/07
3.1.2.2.1 | AO Enclosure Temperature | Cancelled
3.1.2.2.2 | Optical Relay | Extend end date from 4/13 to 6/15
3.1.2.2.3 | Field Rotation Strategy | To be done with 3.1.2.2.2 Optical relay. RD new lead. Replace JM with RD. Reduce BB by 20h
3.1.2.2.3 | Field Rotation Strategy | Extend end date from 4/13 to 6/15
3.1.2.2.4 | Dichroics & Beamsplitters | Cancelled
3.1.2.2.5 | Rayleigh Rejection | Changed Kelner 40h to VV. Added 32h of VV. Move end date fromr 12/8/6 to 5/11/7 | 72 vs 40h | 32
3.1.2.2.8 | Slow WFS | Cancelled
3.1.2.2.9 | LOWFS architecture | Increased from 160 to 220h. Changed SK from 80 to 100h, VV from 100 to 20h & added 100h of RF. Changed end from 2/9 to 5/9/07 | 160 to 220h | 60
3.1.2.2.10 | Number & Type of LOWFS | Only Type addressed | 80 vs 60h
3.1.2.2.11 | Centroid Anisoplanatism | Cancelled
3.1.2.2.12 | Deformable Mirror Stroke Requirement | Cancelled
3.1.2.2.13 | Stand-alone vs DM on T/T Stage | Cancelled
3.1.2.2.14 | Correcting Fast T/T with DM | Previously cancelled
3.1.2.2.15 | Focus Compensation | Cancelled
3.1.2.2.16 | d-IFU & LOWFS AO & Object Selection TS | New task. 88h AM, 8h each SA,RD,VV. 5/28-7/27/07 |  | 120
3.1.2.3.1 | Laser Pulse Format | Cancelled
3.1.2.3.2 | Free Space vs Fiber | Cancelled
3.1.2.3.3 | LGS Asterism Geometry & Size |  | 100 vs 20h
3.1.2.3.4 | Variable vs fixed LGS Asterism Cost/Benefit |  | 80 vs 20h
3.1.2.3.5 | Uplink compensation | New task. DG as lead at 40h, VV at 60h. Start 4/30, end 6/1
3.1.2.3.5 | Uplink compensation | Changed dates to 5/21-6/22
3.1.2.4 | Trade Study Conclusions Summary | New task. CN lead at 30h. 10h each RD,DG,PW. 5/14-6/8/07 |  | 60
3.1.3.1 | System Architecture ver 1 | Rename as "Candidate Subsystems". Remove 80h of labor. Remove 3.1.1.13.2 as predecessor
3.1.3.1.1 | Define Candidate Subsystems | New subtask. 260h (vs 320h request). 60h RD + 40h each of BB,DG,CN,VV,PW. RD lead. 5/10-5/31/07.
3.1.3.1.1 | Define Candidate Subsystems | 48h RD, 24h for BB,DG,CN,VV,PW + 60h other . Made this a 2wk task starting 5/21. |  | -32
3.1.3.1.2 | Subsystems Performance Evaluation | New subtask. 70h (vs 80h). 34h RD + 12h each of BB,DG&CN. RD lead. 6/1-6/22/07
3.1.3.1.2 | Subsystems Performance Evaluation | 24h for RD,DG,PW. 2 wk task starting 6/4 |  | 2
3.1.3.1.3 | Subsystems Cost Evaluation | New subtask 70h (vs 80h). 20h DG + 10H each of BB,RD,CN,VV,PW. DG lead. 3.1.3.1.1 as predecessor. 6/1-6/22/07
3.1.3.1.3 | Subsystems Cost Evaluation | 24h for BB,CN,VV. Changed lead to CN. 2wk task starting 6/4 |  | 2
3.1.3.1.4 | Subsystems Risk Evaluation | New subtask 40h. 20h CN, 10h DG, 5h each RD,PW. CN lead. 3.1.3.1.1 as predecessor. 6/1-6/22/07
3.1.3.1.4 | Subsystems Risk Analysis | 12h each BB,CN,VV. Changed WBS name. 1 wk task starting 6/18 |  | -4
3.1.3.1.5 | Organize Candidate Subsystems | New subtask 70h (vs 80h). 20h each RD,DG; 15h each CN,PW. 3.1.3.1.2,3&4 as predecessors. 8/27-9/5/07
3.1.3.1.5 | Organize Candidate Subsystems | Pulled in end date from 7/4 to 6/29
3.1.3.1.5 | Organize Candidate Subsystems | 12h each BB,CN,VV,RD,DG,PW. 1 wk task starting 6/25 |  | 2
3.1.3.2 | System Architecture ver 2 | Rename as "Candidate Architectures". Remove 60h of labor. 3.3.1.5 as predecessor
3.1.3.2.1 | Define Candidate Architectures | New subtask. 280h (vs 320h request). 60h each of RD,DG; 40h each of BB,CN,VV,PW. RD lead.
3.1.3.2.1 | Define Candidate Architectures | 68h RD, 52h each BB,DG,CN,VV,PW + 30h other. 2wk task starting 7/9 |  | 48
3.1.3.2.2 | Architectures Performance Evaluation | New subtask. 100h (vs 120h). 30h RD + 15h each of BB,DG,CN,VV,PW. RD lead. 3.1.3.2.1 as predecessor
3.1.3.2.2 | Architectures Performance Evaluation | 24h each RD,DG,PW. 2wk task starting 7/23. Shifted 6h from each to RF to help balance July |  | -28
3.1.3.2.3 | Architectures Cost Evaluation | New subtask. 240h (vs 320h). 60h DG + 40h each BB,RD,CN,VV + 20h PW. DG lead. 3.1.3.2.1 as predecessor
3.1.3.2.3 | Architectures Cost Evaluation | 24h each BB,CN,VV. 2wk task starting 7/23 |  | -168
3.1.3.2.4 | Architectures Risk Evaluation | New subtask 40h. 20h CN, 10h DG, 5h each RD,PW. CN lead. 3.1.3.2.1 as predecessor
3.1.3.2.4 | Architectures Risk Analysis | 12h each BB,CN,VV. Changed WBS name. 1wk task starting 8/6 |  | -4
3.1.3.2.5 | Adopt Baseline Architecture(s) | New subtask. 75h (vs 80h). 30h RD, 15h each DG,CN,PW. RD lead. 3.1.3.2.2,3&4 as predecessors
3.1.3.2.5 | Adopt Baseline Architecture(s) | 8h each BB,RD,DG,CN,VV,PW. 1 wk task starting 8/13 |  | -27
3.1.3.2.6 | System Architecture Ver 1 | New subtask. 100h (vs 120h). 40h RD + 20h each of DG,CN,PW. RD lead. 3.1.3.2.5 as predecessor
3.1.3.2.6 | System Architecture Ver 1 | Pulled in end date from 9/12 to 8/31. Removed 3.1.2.1.4 as predecessor to allow this.
3.1.3.2.6 | System Architecture Ver 1 | Deleted this item. Covered under 3.6 |  | -100
3.1.3.2.7 | System Architecture Ver 2 | New subtask. 70h (vs 0h). 20h each RD,DG,CN + 10h PW. RD lead. 3.2&3.3 as predecessors
3.1.3.2.7 | System Architecture Ver 2 | Deleted this item. Covered under 3.6 |  | -70
3.1.3.3 | Functional Requirements | Was 860h. Put PW as lead.
3.3.3.3.1 | Draft Functional Requirements Document | New subtask. Numbering of subsequent subtasks impacted. PW lead. 20h PW.
3.1.3.3.1 | AO System Functional Requirements v1 | Reduce CN,BB by 15h each; JC,PS by 20h each. Add 15h PW. Moved out start top 8/6/07
3.1.3.3.1 | AO System Functional Requirements v1 | 32h each EJ,RD,DG,CN,PW. Moved to 7/9-8/3. Transferred 16h of PW to CN. Extended to 8/17 to distribute load. |  | 15
3.1.3.3.2 | AO System Functional Requirements v2 | Reduced from 100 to 50h assuming largely covered in 3.2
3.1.3.3.2 | AO System Functional Requirements v2 | 16h each EJ,RD,DG,CN,PW |  | 30
3.1.3.3.3 | Laser System Functional Requirements v1 | Reduce JC by 35h, VV by 15h; add 15h JM, add 10h PW
3.1.3.3.3 | Laser System Functional Requirements v1 | 32h each JC,VV,EJ. Moved to 7/9-8/3 |  | -14
3.1.3.3.4 | Laser System Functional Requirements v2 | Reduced from 65 to 36h assuming largely covered in 3.3
3.1.3.3.4 | Laser System Functional Requirements v2 | 16h each JC,VV,EJ |  | 12
3.1.3.3.5 | Science Operations Functional Reqments v1 | Replace 60h of Other with 10h of PW
3.1.3.3.5 | Science Operations Functional Reqments v1 | Moved task from 7/2-8/2 to 8/6-8/31
3.1.3.3.6 | Science Operations Functional Reqments v2 | Reduced from 100 to 50h assuming largely covered in 3.4
3.1.3.3.7 | Science Instrument Function Allocation v1 | Assume covered under 3.5. Reduce 80h to just 6h of SA, 2h of PW. 3.5.1.2.1 as predecessor. Moved in start to 5/8/07
3.1.3.3.8 | Science Instrument Function Allocation v2 | Assume covered under 3.5. Reduce 80h to just 6h of SA, 2h of PW. 3.5.1.3.1 as predecessor.
3.1.3.4 | Technology Drivers Summary | Reduce from 40h to 10h to document drivers identified in 3.1.3.1 & 3.1.3.2. Removed CN. Reduced DG from 16 to 10h. Change predecessor to 3.1.3.2.5
3.1.3.4 | Technology Drivers Summary | Cancelled |  | -9
3.1.3.5 | Technical Risk Analysis Ver 1 | Reduced from 40h to 10h to document risks from 3.1.3.1.4 & 3.1.3.2.6. Removed DG. Reduced CN from 24 to 10h. CN new lead. 3.1.2.3.2.5 as predecessor & remove 3.1.3.4 as predessor. Moved from 10/26 to 8/27/07 start.
3.1.3.5 | Technical Risk Analysis Ver 1 | Added 6h PW, 2h RD, 2h DG |  | 10
3.1.3.6 | Technical Risk Analysis Ver 2 | Leave at 40h. Change lead to CN. 3.1.3.2.7 as predecessor
3.1.3.6 | Technical Risk Analysis Ver 2 | Removed DG 16h, added 1h to CN |  | -15
3.2.1 | AO System Architecture | Reduce from 240h total to 40h of DG (just in case any remaining issues). Change predecessor to 3.1.3.2.5
3.2.1 | AO System Architecture | Move to 9/4-11/23
3.2.2 | AO Enclosure | Change predecessor to 3.1.3.2.5. Reduce from 100 to 40h - pulled in end to 9/28
3.2.2 | AO Enclosure | Move to 10/1-11/7
3.2.3 | Opto-mechanical | Make predecessor 3.1.3.2.5
3.2.3.1 | Field Rotation | Pull in end date to 11/2/07
3.2.3.1 | Field Rotation | Move to 9/4-11/2
3.2.3.2 | Optical Relay | Pull in end date to 11/2/07
3.2.3.2 | Optical Relay | Move to 9/4-11/2
3.2.3.3 | Optical Switchyard | Pull in end date to 11/2/07
3.2.3.3 | Optical Switchyard | Move to 9/4-11/2
3.2.3.4 | Optical Support Structure | Pull in end date to 11/30/07
3.2.3.5 | Wavefront Sensors | Pull in end date to 11/16/07
3.2.3.5.1 | High order LGS WFSs | Consider DG suggestion of DG lead + BB
3.2.3.5.2 | High order NGS WFS | Consider DG suggestion of DG lead + BB
3.2.3.5.3 | Low Order NGS Wavefront Sensors | VV as new lead. 40h of SK to 20h more of VV & 20h of AM
3.2.3.5.4 | Calibration Wavefront Sensor | CN as new lead. 40h of SK to CN
3.2.3.6 | Wavefront Correctors | Put CN as lead
3.2.3.6.2 | Deformable Mirror | Reduce BB from 50 to 10h. Replace 40h of RF & 30h of RD with 40h of CN. CN as lead
3.2.3.6.2 | Deformable Mirror | Move from 4/2-6/29 to 8/13-9/21
3.2.3.6.3 | Tip/Tilt Vibration Mitigation | New task. CN lead with 20h + 20h EJ & 5h DG. 8/22-9/28/07. Precursor to 3.2.3.6.1 |  | 45
3.2.3.7 | Acquisition Cameras | Replace AB hours & lead with CN (familiar w/ MAGIQ)
3.2.3.8 | Atmospheric Dispersion Correction | BB replaces 16h of SK. RD lead with 4h
3.2.3.9 | Alignment, Diag, Metrology & Monitoring | Add 20h of DLM. Reduce CN & RF by 10h each
3.2.3.10 | Atmospheric Profiler | New task. MB lead at 50h. 7/23-8/31/07
3.2.3.11 | d-IFU & LOWFS AO & Object Selection | New task. AM lead at 200h. DG 40h. JM 80h. 5/21-8/6/07
3.2.3.11 | d-IFU & LOWFS AO & Object Selection | Moved 120h of AM to a new trade study |  | -120
3.2.3.12 | PSF Monitoring Camera | New task. MB lead. 10h MB + 20h CN. 10/1-26/07 |  | 30
3.2.4 | Non-real-time Control | EJ as new lead
3.2.4.1 | Non-RTC Software | Remove 30h of Johnson
3.2.4.2 | Non-RTC Electronics | Remove 40h each of JC&MR & add 40h of EJ
3.2.5.1 | RTC Architecture Analysis & Design Study | Remove 20h each of RF& MR. Change start date to 6/18/07
3.2.5.1 | RTC Architecture Analysis & Design Study | Put back 20h each of RF & MR |  | 40
3.2.5.1 | RTC Architecture Analysis & Design Study | Moved start from 6/18 to 8/1.
3.2.5.2 | RTC Software Module Definition | Consider replacing 20h of Reinig with Palmer
3.2.5.2 | RTC Software Module Definition | Start & end dates forced to 9/3-12/3
3.2.5.3 | RTC Hardware Module Definition | Start & end dates forced to 9/3-12/3
3.3.1 | Laser System Architecture | Change predecessor from 3.1.1.5 to 3.1.1.5.1
3.3.1 | Laser System Architecture | Moved 6/4-8/10 to 8/27-10/19. This also moved out 3.3.2&3.
3.3.3 | Laser | Reduce VV from 100 to 20h. DG new lead. DG to perform with CfAO funding
3.3.4 | Laser Launch Facility | Change start & end dates for all subtasks to 7/23 & 8/31, respectively
3.3.4.1 | Laser beam transport | Replace 20h of SK with 16h of VV. Reduce CN from 35 to 30h. Reduce JC from 5 to 4h
Removed 3.1.2.3.1&2 as predecessors
3.3.4.2 | Laser pointing & diagnostics | Replace 30h of AM with 15h of BB. Replace 30h of SK with 15h of CN. Reduce JC from 20 to 10h.
Removed 3.1.2.3.1&2 as predecessors
3.3.4.3 | Laser launch telescope | Replace 50h of SK with 30h of CN. Reduce JC from 20 to 10h. Reduce VV from 50 to 30h
Removed 3.1.2.3.1&2 as predecessors
3.4 | Science Operations | Added leads for all subtasks
3.4.1.1.1 | AO Guide Star Interface | Shift from 5/1 to 7/26/07 start
3.4.1.1.2 | Science Observation Simulation Tools | Shift from 5/1 to 7/26/07 start
3.4.1.2.1 | Acquisition | Shift from 3/1 to 5/28/07 start
3.4.1.2.2 | Observing Sequences | Shift from 3/1 to 5/28/07 start
3.4.1.2.3 | Instrument, AO & Telescope Observer Interfaces | Shift from 3/1 to 5/28/07 start
3.4.1.3.4 | PSF reconstruction method | New task. 80h for DLM, 40h for MB + postdoc. 9/3/7-1/18/08
3.4.1.3.4 | PSF reconstruction method | Changed dates from 9/3-1/17/08 to 10/1-11/30/07
3.4.2.1.1 | AO-Instrument Observing Modes | Shift from 1/2 to 5/21/07 start
3.4.2.1.2 | AO-Instrument Operations Support | Shift from 2/5 to 6/25/07 start. Pulled in end ot 7/13/07
3.4.2.1.10 | AO-Instrument Maintenance Plan | Changed lead & hrs to EJ from JC
3.4.2.2.1 | AO-Instrument Performance Prediction | Shift from 3/5 to 6/18/07 start
3.4.2.2.2 | AO-Instrument Real-Time Optimization | Shift from 3/5 to 6/18/07 start
3.4.2.2.3 | AO-Instrument Environment Monitoring | Changed lead & hrs to EJ from JC. Shift from 3/5 to 6/18/07 start
3.5 | Science Instruments | New WBS implemented
3.5.1 | Instrument Requirements & Initial Definitions | New task.
3.5.1.1 | Top Level Instrument Requirements Definition | New subtask. 4/16-5/4/07. 16h of SA
3.5.1.2 | Instrument Suite Version 1 | New subtask.
3.5.1.2.1 | Instrument Function Allocation Review with Science Team | New subtask. 5/7/07. 3.5.1.1 as predecessor. 3h SA.
3.5.1.2.2 | Summary Descriptions of Instruments | New subtask. 5/8-6/5/07. 3.5.1.2.1 as predecessor. 10h SA.
3.5.1.3 | Instrument Suite Version 2 | New subtask
3.5.1.3.1 | Instrument Review with Science Team | New subtask. 1/10-1/11/08. 3h SA
3.5.1.3.2 | Revised Summary Descriptions of Instruments | New subtask. 1/14-1/25/08. 3.5.1.4.1 as predecessor. 20h SA
3.4.1.4 | Instrument Interfaces | New subtask
3.4.1.4.1 | Hardware Instrument Interfaces | New subtask. 6/6-6/22/07. 20h SA; 20h JM
3.4.1.4.2 | Software Instrument Interfaces | New subtask. 6/12-6/29/07. 20h SA; 20h EJ
Old 3.5.7 | Deployable NIR IFU | Change to 3.5.2. Change name to "Deployable Near-IR Instrument (DNIRI). Remove 500h. Moved 140h of AM to 3.2.3.11.
3.5.2.1 | DNIRI Concept Development | New subtask. 5/7-6/15/07. 10h SA, 20h me1, 20h oe1
3.5.2.2 | DNIRI AO Interface Issues | New subtask.
3.5.2.2.1 | Object Selection for DNIRI | New subtask. 6/18-6/29/07. 3.5.2.1 as predecessor. 8h each AM, SA, me1, oe1
3.5.2.2.2 | AO Design for DNIRI | New subtask. 7/2/07. 3.5.2.2.1 as predecessor. 4h AM
3.5.2.2.3 | DNIRI/AO Boundary Definition | New subtask. 7/3/07. 3.5.2.2.2 as predecessor
3.5.2.3 | DNIRI Spectrograph Concepts | New subtask. 7/3-8/6/07. 3.5.2.2.3 as predecessor. 20h ea SA,me1,oe1
3.5.2.4 | DNIRI Imager Concepts | New subtask. 7/3-8/6/07. 3.5.2.2.3 as predecessor. 20h ea SA,me1,oe1
3.5.2.5 | DNIRI Concept Review with AO Team | New subtask. 8/8/07. 3.5.2.3&3.5.2.4 as predecessors. 2h each of SA,me1,oe1,AM
3.5.2.6 | DNIRI Report ver 1 | New subtask. 8/9-9/18/07. 3.5.2.5 as predecessor. 40h SA
3.5.2.7 | DNIRI Report ver 2 | New subtask. 1/25-3/7/08. 20h SA
Old 3.5.4 | NIR imager | Delete. Was 200h. Now part of new 3.5.3.
Old 3.5.5 | Visible imager | Delete. Was 200h. Now part of new 3.5.3.
3.5.3 | Single Object Imagers/Low Resolution Spectrographs (SOI/LRS) | New task.
3.5.3.1 | SOI/LRS Coronagraph Requirements | New subtask. 5/7-6/1/07. 3.5.1.1 as predecessor. 20h SA
3.5.3.2 | SOI/LRS Spectrograph Requirements | New subtask. 6/4-6/15/07. 3.5.3.1 as predecessor. 5h SA
3.5.3.3 | SOI/LRS Concept Development | New subtask. 6/18-6/29/07. 3.5.3.1&3.5.3.2 as predecessors. 8h each SA,me2,oe2
3.5.3.4 | SOI/LRS Concept Review | New subtask.
3.5.3.4.1 | SOI/LRS Concept Review with Science Team | New subtask. 7/2/07. 3.5.3.3 as predecessor. 3h SA
3.5.3.4.2 | SOI/LRC Concept Review with AO Team | New subtask. 7/3/07. 3.5.3.3&3.5.3.4.1 as predecessors. 3h SA
3.5.3.5 | SOI/LRS Reports | New subtask.
3.5.3.5.1 | SOI/LRS Near-IR ver 1 | New subtask. 7/5-10/17/07. 3.5.3.4.2 as predecessor. 30h SA
3.5.3.5.2 | SOI/LRS Visible ver 1 | New subtask. 7/5-10/17/07. 3.5.3.4.2 as predecessor. 30h SA
3.5.3.5.3 | SOI/LRS Near-IR ver 2 | New subtask. 1/25-2/15/08. 12h SA
3.5.3.5.4 | SOI/LRS Visible ver 2 | New subtask. 2/18-3/10/08. 3.5.3.5.3 as predecessor. 12h SA
Old 3.5.1 | OSIRIS | Delete. Was 100h. Now part of new 3.5.4.
Old 3.5.6 | Visible IFU | Delete. Was 100h. Now part of new 3.5.4.
3.5.4 | Single Object IFUs (SOIFU) | New task.
3.5.4.1 | Near-IR IFU Requirements Review | New subtask. 4/30-5/11/07. 5h SA
3.5.4.2 | Visible IFU Requirements Review | New subtask. 9/18-10/16/07. 8h SA
3.5.4.3 | Visible IFU Concept Development | New subtask. 10/17-11/28/07. 3.5.4.2 as predecessor. 15h each SA,me3,oe3
3.5.4.4 | SOIFU Concept Review | New subtask.
3.5.4.4.1 | Science Case Team | New subtask. 11/29/07. 3.5.4.1&3.5.4.3 as predecessors. 3h SA
3.5.4.4.2 | AO Team | New subtask. 11/30/07. 3.5.4.4.1 as predecessor. 3h SA
3.5.4.5 | Single Object IFU Reports | New subtask.
3.5.4.5.1 | SOIFU Near-IR ver 1 | New subtask. 12/3-12/14/07. 3.5.4.4.2 as predecessor. 12h SA
3.5.4.5.2 | SOIFU Visible ver 1 | New subtask. 12/17-1/11/08. 3.5.4.5.1 as predecessor. 30h SA
3.5.4.5.3 | SOIFU Near-IR ver 2 | New subtask. 1/28-2/8/08. 8h SA
3.5.4.5.4 | SOIFU Visible ver 2 | New subtask. 2/18-2/29/08. 20h SA
3.5.5 | Special Purpose High Contrast Instrument (HCI) | New task.
3.5.5.1 | HCI Requirements Development | New subtask. 1/10-2/21/08. 13h SA
3.5.5.2 | HCI Concept Development | New subtask. 2/22-3/20/08. 3.5.5.1 as predecessor. 20h SA; 10h each me2,oe2
3.5.5.3 | HCI Concept & Need Review with Science Team | New subtask. 3/21/08. 3.5.5.2 as predecessor. 8h SA
Old 3.5.2 | Interferometer | Change to new 3.5.6. Move to after architecture decision - make 3.1.3.2.5 predecessor. Remove SA (16h). CN as lead. Pull in end date to 10/30/07
3.5.6 | Interferometer | Note that the 30h of "Other" will likely be at least part Ragland
Old 3.5.3 | OHANA | Change to new 3.5.7. Remove SA (8h). CN as lead. Make 3.1.3.2.5 predecessor
Old 3.5.8 | Thermal NIR imager | Cancel. Low priority.
3.6 | SDM | Removed all predecessors. Redistributed labor to subtasks.
3.6.1 | SDM v1 | New subtask. 3.1.3.2.5 as predecessor. PW lead. 25h
3.6.1 | SDM v1 | Increased PW by 15h to 30h; RD by 20h to 30h. Set dates to 8/13-9/14. |  | 25
3.6.2 | SDM v2 | New subtask. PW lead. 55h
3.6.2 | SDM v2 | Increased PW by 10h to 35h; RD by 15h to 25h |  | 25
4.1.1 | WBS and Task Definition | Move from 9/25-10/24 to 9/25-11/12
4.1.2 | Cost estimation | Reduced from 220 to 160h by reducing RD,SA by 5h each, DG,JC by 10h: BB,VV by 15h
4.1.2 | Cost estimation | Removed 4.1.1 as predecessor
4.1.3 | Major Project Milestones | Removed 4.1.1 as predecessor
4.2 | Risk Assessment & Management Plan | Removed 4.1.1 as predecessor
4.3.1 | PD phase plan v1 (to support FY08 planning) | Change completion to 5/18/07
4.4.1.1 | AO System Test Plan | Removed 4.1.1 as predecessor
4.4.1.3 | Science Operations Test Plan | Change hrs & lead to DLM from CN
4.4.1.4 | Science Instrument Test Plan | Change hrs & lead to SA from CN
4.4.2 | System Integration & Test Plans | Transferred 10h from CN to PW
4.4.2 | System Integration & Test Plans | Moved from 10/25-12/5 to 12/3-1/31. Removed 4.1.1 as predecessor
4.5 | Configuration Management Plan | Moved 50h of JJ to EJ & put EJ as lead. Removed 4.1.1 as predecessor
? | Nasmyth platform solidworks model | Needed for AO/laser enclosures (200h)
? | Top end solidworks model | Needed for launch telescope (40h)
| Mechanical & Optical Engineers | Added rate on resource sheet
| Student2 | Had 1000h. Put cost at $0/hr instead of trying to remove them from every task they were on
| Postdoc | Change name to McGraw & initials to EM. Assume have to pay for 66% of a year during SD phase; this is close to the 1260h in the plan (note they will only work 50% of this).
| Adkins | Increased availabity from 10 to 30% starting in May/07
| Bauman | Increased availability from 40 to 50%
| Dekany | Increased availability from 35 to 50%
| Johansson | Reduced availability from 33 to 10% prior to Jun/07 & increased to 50% starting 6/1/07
| Le Mignant | Increased availability from 10 to 35%
| Moore | Reduced availability from 40 to 20%
| Velur | Increased availability from 50 to 75%
| Wizinowich | Increased availability from 34 to 40%
Note: The yellow highlighted changes were made between v20 & v24.
Note: The light green highlighted changes were made between v24 & v25.
Note: The light blue highlighted changes were made between v25 & v26.

## Top-level Replan Sched
Month | System Design Phase Mgmt (WBS1) | Requirements (WBS2 & 3.1.3.3) | System Eng (WBS3.1) | Design (WBS3.2 to 3.6) | System Eng Mgmt Plan (WBS4)
May/07 |  | SCRD v2 | Perf budgets
|  | SRD v2 | Trade studies
|  | FRD v0 & Sci Instrum FRD v1 | Define candidate subsystems
Jun/07 | Prog Rep #3 |  | Perf budget summary v1 | Science Ops
Eval & organize candidate subsystems
Jul/07 |  | SCRD v3 | Define candidate architectures | Science Ops
Aug/07 |  | SRD v3 | Eval & select candidate architectures | Laser Facility & Science Ops
|  | AO Sys, Laser Sys & Sci Ops FRD v1 |  | SDM v1
Sep/07 | Prog Rep #4 |  | Technical risk analysis v1 | AO System
| KSM |  |  | Laser Facility & Science Ops
d-IFU report v1
Oct/07 |  | SCRD v4 | Perf budget summary v2 | AO System, Laser Facility & Science Ops | SEMP + Cost review
Imager/Spect v1
Nov/07 | Prog Rep #5 | SRD v4 |  | AO System | SEMP
|  |  |  | Laser Facility & Science Ops | Cost review
Dec/07 |  |  |  | AO System | SEMP
Laser Facility
Science Ops
Jan/08 | Prog Rep #6 | FRD v2 |  | IFU Report v1 | SEMP
Feb/08 |  |  |  | SDM v2 | SEMP
IFU Report v2
Mar/08 | SDR |  |  | d-IFU report v2
Imager/Spect v2
Apr/08 | Proj Rep #7
SDR Report response
Key = | Complete | In progress

## v20 tracked
WBS | Task Name | Lead | Complete | Work | Start | Finish | Plan | Notes (updated 4/11/07)
0 | NGAO System Design Phase Schedule |  | 21% | 16,725 hrs | 2006-06-21 08:00 | 2008-04-17 10:38
1 | SD Phase Management | PW | 28% | 2,175 hrs | 2006-06-21 08:00 | 2008-04-17 10:38
1.1 | Planning and Contracting | PW | 69% | 230 hrs | 2006-06-21 08:00 | 2007-11-14 10:06
1.1.1 | NGAO Proposal to SSC |  | 100% | 0 hrs | 2006-06-21 08:00 | 2006-06-21 08:00
1.1.2 | Management Structure Decision by Directors |  | 100% | 0 hrs | 2006-07-14 08:00 | 2006-07-14 08:00
1.1.3 | SD Phase System Engineering Management Plan | PW | 100% | 80 hrs | 2006-09-01 08:00 | 2006-09-29 17:00
1.1.4 | SD Phase Contracts Generated | SA | 100% | 60 hrs | 2006-09-27 08:00 | 2006-10-27 17:00 |  | 11/29: Changed lead to PW
1.1.5 | Director Approval |  | 75% | 0 hrs | 2006-10-09 08:00 | 2006-10-09 08:00 |  | Verbal approval received from TA
1.1.6 | SD Partner Contracts Issued | SA | 100% | 0 hrs | 2006-10-27 17:00 | 2006-10-27 17:00 |  | 11/29: Changed lead to PW
1.1.7 | Mid-year Replan | PW | 50% | 40 hrs | 2007-03-05 08:00 | 2007-03-16 17:00
1.1.8 | FY08 Replan | PW | 0% | 50 hrs | 2007-10-25 16:26 | 2007-11-14 10:06
1.2 | Project Meetings |  | 24% | 1,352 hrs | 2006-06-21 08:00 | 2008-04-03 17:00
1.2.1 | Executive Committee Telecons | PW | 43% | 360 hrs | 2006-06-21 08:00 | 2008-04-03 17:00
1.2.2 | Science Advisory Committee Telecons | CM | 0% | 40 hrs | 2006-10-02 08:00 | 2008-03-28 17:00
1.2.3 | Team Meetings |  | 35% | 952 hrs | 2006-09-14 08:00 | 2008-01-09 12:00
1.2.3.1 | Team Meeting #1 (mgmt, science & technical - Irvine) |  | 100% | 68 hrs | 2006-09-14 08:00 | 2006-09-14 17:00
1.2.3.2 | Team Meeting #2 (CIT) |  | 100% | 80 hrs | 2006-11-14 08:00 | 2006-11-14 17:00
1.2.3.3 | Team Videocon #3 |  | 100% | 44 hrs | 2006-12-13 08:00 | 2006-12-13 12:00
1.2.3.4 | Team Meeting #4 (Keck) |  | 100% | 80 hrs | 2007-01-22 08:00 | 2007-01-22 17:00
1.2.3.5 | Team Videocon #5 |  | 100% | 44 hrs | 2007-03-07 08:00 | 2007-03-07 12:00
1.2.3.6 | Team Meeting #6 (UCSC) |  | 0% | 80 hrs | 2007-04-18 08:00 | 2007-04-18 17:00
1.2.3.7 | Team Videocon #7 |  | 0% | 44 hrs | 2007-05-30 13:00 | 2007-05-30 17:00
1.2.3.8 | Team Retreat #8 (UCSC) |  | 0% | 220 hrs | 2007-07-09 08:00 | 2007-07-11 12:00
1.2.3.9 | Team Videocon #9 |  | 0% | 44 hrs | 2007-08-22 08:00 | 2007-08-22 12:00
1.2.3.10 | Team Meeting #10 (CIT) |  | 0% | 80 hrs | 2007-09-11 08:00 | 2007-09-11 17:00
1.2.3.11 | Team Videocon #11 |  | 0% | 44 hrs | 2007-11-05 08:00 | 2007-11-05 12:00
1.2.3.12 | Team Meeting #12 (Keck) |  | 0% | 80 hrs | 2007-12-12 08:00 | 2007-12-12 17:00
1.2.3.13 | Team Videocon #13 |  | 0% | 44 hrs | 2008-01-09 08:00 | 2008-01-09 12:00
1.3 | Tracking and Reporting | PW | 40% | 120 hrs | 2006-09-16 17:00 | 2008-04-03 17:00
1.3.1 | Report Preparation/Presentation | PW | 40% | 120 hrs | 2006-10-02 08:00 | 2007-12-12 12:00
1.3.2 | Keck Science Meeting 06 (UCI) |  | 100% | 0 hrs | 2006-09-16 17:00 | 2006-09-16 17:00
1.3.3 | SSC meeting (UCLA) |  | 100% | 0 hrs | 2006-11-06 08:00 | 2006-11-06 08:00
1.3.4 | SSC meeting (Keck) |  | 100% | 0 hrs | 2007-01-24 08:00 | 2007-01-24 08:00
1.3.5 | SSC meeting (CA) |  | 100% | 0 hrs | 2007-04-03 08:00 | 2007-04-03 08:00
1.3.6 | SSC meeting (Keck) |  | 0% | 0 hrs | 2007-06-20 08:00 | 2007-06-20 08:00
1.3.7 | Keck Science Meeting 07 |  | 0% | 0 hrs | 2007-09-22 17:00 | 2007-09-22 17:00
1.3.8 | SSC meeting (CA) |  | 0% | 0 hrs | 2007-11-06 08:00 | 2007-11-06 08:00
1.3.9 | SSC meeting (Keck) |  | 0% | 0 hrs | 2008-01-24 08:00 | 2008-01-24 08:00
1.3.10 | SSC meeting (CA) |  | 0% | 0 hrs | 2008-04-03 17:00 | 2008-04-03 17:00
1.4 | Proposals & Fundraising |  | 0% | 0 hrs | 2006-10-27 17:00 | 2007-01-01 08:00
1.4.1 | Dates & deliverables identified by Directors |  | 0% | 0 hrs | 2006-10-27 17:00 | 2006-10-27 17:00
1.4.2 | Support Advancement Office |  | 0% | 0 hrs | 2007-01-01 08:00 | 2007-01-01 08:00 |  | No effort assigned
1.5 | System Design Report & Review | SA | 0% | 473 hrs | 2007-10-01 08:00 | 2008-04-17 10:38 | R
1.5.1 | System Design Report | PW | 0% | 40 hrs | 2008-02-20 10:38 | 2008-03-03 10:38
1.5.2 | System Design Review | PW | 0% | 433 hrs | 2007-10-01 08:00 | 2008-04-17 10:38
1.5.2.1 | Identify Reviewers | SA | 0% | 15 hrs | 2007-10-01 08:00 | 2007-12-14 17:00
1.5.2.2 | Review Package Distributed | SA | 0% | 8 hrs | 2008-03-03 10:38 | 2008-03-04 10:38
1.5.2.3 | Reviewer Comments Addressed | PW | 0% | 120 hrs | 2008-03-18 10:38 | 2008-03-25 10:38
1.5.2.4 | System Design Review Support | PW | 0% | 250 hrs | 2008-03-03 10:38 | 2008-03-31 10:38
1.5.2.5 | System Design Review Meeting | SA | 0% | 0 hrs | 2008-03-31 10:38 | 2008-03-31 10:38
1.5.2.6 | Reviewer Report Received |  | 0% | 0 hrs | 2008-04-14 10:38 | 2008-04-14 10:38
1.5.2.7 | Response to Reviewer Report & Distribution | PW | 0% | 40 hrs | 2008-04-14 10:38 | 2008-04-17 10:38
2 | System Requirements | PW | 35% | 3,524 hrs | 2006-10-02 08:00 | 2007-11-02 17:00
2.1 | Science Requirements | CM | 34% | 3,090 hrs | 2006-10-02 08:00 | 2007-10-15 17:00
2.1.1 | Solar System Science Requirements | FM | 44% | 650 hrs | 2006-10-02 08:00 | 2007-04-06 17:00
2.1.1.1 | Companions & Multiplicity of Small Solar System Bodies |  | 49% | 250 hrs | 2006-10-02 08:00 | 2007-01-12 17:00 | R
2.1.1.1.1 | Point Source Companion Sensitivity Requirements |  | 75% | 100 hrs | 2006-10-02 08:00 | 2006-12-01 17:00
2.1.1.1.2 | Spectral Sensitivity & Spectral Resolution Requirements |  | 85% | 100 hrs | 2006-10-02 08:00 | 2006-12-01 17:00
2.1.1.1.3 | Observing Scenarios |  | 50% | 25 hrs | 2006-12-04 08:00 | 2007-01-12 17:00
2.1.1.1.4 | Science Instrument Requirements |  | 80% | 25 hrs | 2006-12-04 08:00 | 2007-01-12 17:00
2.1.1.2 | Moons of the Giant Planets |  | 31% | 150 hrs | 2006-12-04 08:00 | 2007-03-09 17:00 | R
2.1.1.2.1 | Performance Requirements |  | 10% | 100 hrs | 2006-12-04 08:00 | 2007-01-26 17:00
2.1.1.2.2 | Observing Scenarios |  | 50% | 25 hrs | 2007-01-29 08:00 | 2007-03-09 17:00
2.1.1.2.3 | Science Instrument Requirements |  | 40% | 25 hrs | 2007-01-29 08:00 | 2007-03-09 17:00
2.1.1.3 | Shape & Size of Asteroids |  | 49% | 250 hrs | 2007-01-29 08:00 | 2007-04-06 17:00 | R
2.1.1.3.1 | Spatial Resolution Requirements |  | 70% | 100 hrs | 2007-01-29 08:00 | 2007-03-02 17:00
2.1.1.3.2 | Spectral Sensitivity & Spectral Resolution Requirements |  | 80% | 100 hrs | 2007-01-29 08:00 | 2007-03-02 17:00
2.1.1.3.3 | Observing Scenarios |  | 40% | 25 hrs | 2007-03-05 08:00 | 2007-04-06 17:00
2.1.1.3.4 | Science Instrument Requirements |  | 80% | 25 hrs | 2007-03-05 08:00 | 2007-04-06 17:00
2.1.2 | Galactic Science Requirements | ML | 27% | 1,200 hrs | 2006-10-02 08:00 | 2007-04-06 17:00
2.1.2.1 | Galactic Center Proper Motions: Astrometry | AG | 46% | 200 hrs | 2006-10-02 08:00 | 2007-01-12 17:00 | R
2.1.2.1.1 | Astrometry requirements |  | 40% | 150 hrs | 2006-10-02 08:00 | 2006-12-08 17:00
2.1.2.1.2 | Observing Scenarios |  | 75% | 25 hrs | 2006-11-27 08:00 | 2007-01-12 17:00
2.1.2.1.3 | Science Instrument Requirements |  | 75% | 25 hrs | 2006-11-27 08:00 | 2007-01-12 17:00
2.1.2.2 | Galactic Center Radial Velocities & Stellar Populations: Integral Field Spectroscopy | AG | 53% | 200 hrs | 2006-11-27 08:00 | 2007-03-09 17:00 | R
2.1.2.2.1 | Performance Requirements |  | 50% | 150 hrs | 2006-11-27 08:00 | 2007-01-26 17:00
2.1.2.2.2 | Observing Scenarios |  | 50% | 25 hrs | 2007-01-29 08:00 | 2007-03-09 17:00
2.1.2.2.3 | Science Instrument Requirements |  | 60% | 25 hrs | 2007-01-29 08:00 | 2007-03-09 17:00
2.1.2.3 | Galactic Center Nature of Sgr A*: 3-5 um Color & 2 um Polarimetry Variability | AG | 10% | 200 hrs | 2007-01-29 08:00 | 2007-04-06 17:00 | R
2.1.2.3.1 | Performance Requirements |  | 10% | 150 hrs | 2007-01-29 08:00 | 2007-03-02 17:00
2.1.2.3.2 | Observing Scenarios |  | 10% | 25 hrs | 2007-03-05 08:00 | 2007-04-06 17:00
2.1.2.3.3 | Science Instrument Requirements |  | 10% | 25 hrs | 2007-03-05 08:00 | 2007-04-06 17:00
2.1.2.4 | Planets around Low Mass Stars & Brown Dwarfs: Companion Sensitivity | ML | 32% | 200 hrs | 2006-10-02 08:00 | 2007-01-12 17:00 | R
2.1.2.4.1 | Companion Sensitivity Performance Requirements |  | 60% | 150 hrs | 2006-10-02 08:00 | 2006-12-08 17:00 |  | 11/29: Combine w/2.1.1.1.1?
2.1.2.4.2 | Observing Scenarios |  | 40% | 25 hrs | 2006-11-27 08:00 | 2007-01-12 17:00
2.1.2.4.3 | Science Instrument Requirements |  | 60% | 25 hrs | 2006-11-27 08:00 | 2007-01-12 17:00
2.1.2.5 | Debris Disks, Protostellar Envelopes & Outflows: Contrast | LH | 10% | 200 hrs | 2007-01-29 08:00 | 2007-04-06 17:00 | R
2.1.2.5.1 | Contrast Performance Requirements |  | 10% | 150 hrs | 2007-01-29 08:00 | 2007-03-02 17:00
2.1.2.5.2 | Observing Scenarios |  | 10% | 25 hrs | 2007-03-05 08:00 | 2007-04-06 17:00
2.1.2.5.3 | Science Instrument Requirements |  | 10% | 25 hrs | 2007-03-05 08:00 | 2007-04-06 17:00
2.1.2.6 | Debris Disks, Protostellar Envelopes & Outflows: Polarimetry |  | 0% | 200 hrs | 2006-11-27 08:00 | 2007-03-09 17:00 | R
2.1.2.6.1 | Polarimetry Performance Requirements |  | 0% | 150 hrs | 2006-11-27 08:00 | 2007-01-26 17:00
2.1.2.6.2 | Observing Scenarios |  | 0% | 25 hrs | 2007-01-29 08:00 | 2007-03-09 17:00
2.1.2.6.3 | Science Instrument Requirements |  | 0% | 25 hrs | 2007-01-29 08:00 | 2007-03-09 17:00
2.1.3 | Extragalactic Science Requirements | CM | 37% | 1,000 hrs | 2006-10-02 08:00 | 2007-04-27 17:00
2.1.3.1 | Resolved Stellar Populations in Crowded Fields |  | 47% | 300 hrs | 2006-10-02 08:00 | 2007-02-02 17:00 | R
2.1.3.1.1 | Performance Requirements |  | 60% | 250 hrs | 2006-10-02 08:00 | 2006-12-22 17:00
2.1.3.1.2 | Observing Scenarios |  | 60% | 25 hrs | 2006-12-11 08:00 | 2007-02-02 17:00
2.1.3.1.3 | Science Instrument Requirements |  | 50% | 25 hrs | 2006-12-11 08:00 | 2007-02-02 17:00
2.1.3.2 | High Redshift Galaxies |  | 41% | 300 hrs | 2006-10-02 08:00 | 2007-02-02 17:00 | R
2.1.3.2.1 | Encircled Energy (& d-IFU) Performance Requirements |  | 70% | 200 hrs | 2006-10-02 08:00 | 2006-12-22 17:00
2.1.3.2.2 | Observing Scenarios |  | 70% | 50 hrs | 2006-12-11 08:00 | 2007-02-02 17:00
2.1.3.2.3 | Science Instrument Requirements |  | 60% | 50 hrs | 2006-12-11 08:00 | 2007-02-02 17:00
2.1.3.3 | Nearby Galaxies |  | 40% | 200 hrs | 2006-12-11 08:00 | 2007-04-27 17:00 | R | 3/6: Rename to AGNS, nearby galaxies & QSO hosts
2.1.3.3.1 | Encircled Energy & PSF Performance Requirements |  | 40% | 150 hrs | 2006-12-11 08:00 | 2007-03-02 17:00
2.1.3.3.2 | Observing Scenarios |  | 20% | 25 hrs | 2007-03-05 08:00 | 2007-04-27 17:00
2.1.3.3.3 | Science Instrument Requirements |  | 60% | 25 hrs | 2007-03-05 08:00 | 2007-04-27 17:00
2.1.3.4 | Gravitational Lensing |  | 19% | 200 hrs | 2006-12-11 08:00 | 2007-04-27 17:00 | R
2.1.3.4.1 | Encircled Energy & PSF Performance Requirements |  | 30% | 150 hrs | 2006-12-11 08:00 | 2007-03-02 17:00
2.1.3.4.2 | Observing Scenarios |  | 30% | 25 hrs | 2007-03-05 08:00 | 2007-04-27 17:00
2.1.3.4.3 | Science Instrument Requirements |  | 60% | 25 hrs | 2007-03-05 08:00 | 2007-04-27 17:00
2.1.4 | Science Requirements Summary | CM | 25% | 240 hrs | 2006-10-02 08:00 | 2007-10-15 17:00 | R
2.1.4.1 | Science Requirements Summary Rev 1 |  | 100% | 40 hrs | 2006-10-02 08:00 | 2006-10-19 17:00 |  | 11/29: CM to complete by 12/1
2.1.4.2 | Science Requirements Summary Rev 2 |  | 0% | 120 hrs | 2007-02-13 08:00 | 2007-03-02 17:00
2.1.4.3 | Science Requirements Summary Rev 3 |  | 0% | 40 hrs | 2007-06-05 08:53 | 2007-06-22 17:00
2.1.4.4 | Science Requirements Summary Final |  | 0% | 40 hrs | 2007-09-26 08:53 | 2007-10-15 17:00
2.2 | Observatory Requirements | CN | 43% | 224 hrs | 2006-10-02 08:00 | 2007-09-07 17:00 | R
2.2.1 | Development Requirements | CN | 100% | 16 hrs | 2006-10-02 08:00 | 2006-11-24 17:00 |  | 2/28: PW completed for rev 1
2.2.2 | Observatory Interface Requirements | CN | 100% | 24 hrs | 2006-10-02 08:00 | 2006-10-27 17:00 |  | 2/28: PW completed for rev 1
2.2.3 | Science Operations Requirements | DLM | 50% | 64 hrs | 2006-10-02 08:00 | 2006-11-24 17:00
2.2.4 | Observatory Requirements Rev 2 | CN | 0% | 80 hrs | 2007-01-22 08:00 | 2007-02-09 17:00
2.2.5 | Observatory Requirements Rev 3 | CN | 0% | 20 hrs | 2007-04-09 08:00 | 2007-05-18 17:00
2.2.6 | Observatory Requirements Rev 4 | CN | 0% | 20 hrs | 2007-07-16 08:00 | 2007-09-07 17:00
2.3 | System Requirements Document |  | 19% | 210 hrs | 2006-10-09 08:00 | 2007-11-02 17:00
2.3.1 | Traceability Matrix | CN | 12% | 130 hrs | 2006-10-09 08:00 | 2007-10-20 17:00 | R | 11/29: PW to pursue WS plan
2.3.1.1 | Traceability Matrix Rev 1 | CN | 50% | 10 hrs | 2006-10-09 08:00 | 2006-10-20 17:00
2.3.1.2 | Traceability Matrix Rev 2 | CN | 0% | 80 hrs | 2007-02-12 08:00 | 2007-02-27 17:00
2.3.1.3 | Traceability Matrix Rev 3 | CN | 0% | 20 hrs | 2007-06-15 08:00 | 2007-06-28 17:00
2.3.1.4 | Traceability Matrix Rev 4 | CN | 0% | 20 hrs | 2007-10-09 08:00 | 2007-10-20 17:00
2.3.2 | System Requirements Document | PW | 26% | 80 hrs | 2006-11-27 08:00 | 2007-11-02 17:00 | R
2.3.2.1 | SRD Rev 1 | PW | 100% | 20 hrs | 2006-11-27 08:00 | 2006-12-08 17:00 |  | 2/28: PW chose to call complete
2.3.2.2 | SRD Rev 2 | CN | 5% | 20 hrs | 2007-03-09 08:00 | 2007-03-22 17:00
2.3.2.3 | SRD Rev 3 | CN | 0% | 20 hrs | 2007-06-29 08:00 | 2007-07-12 17:00
2.3.2.4 | SRD Final SD Phase Version | CN | 0% | 20 hrs | 2007-10-22 08:00 | 2007-11-02 17:00
3 | System Design | PW | 16% | 9,826 hrs | 2006-08-14 08:00 | 2008-01-18 17:00
3.1 | Systems Engineering | RD | 40% | 5,256 hrs | 2006-08-14 08:00 | 2007-12-28 17:00
3.1.1 | Performance Budgets | RD | 52% | 2,346 hrs | 2006-08-14 08:00 | 2007-12-12 17:00
3.1.1.1 | Model Assumptions | CN | 63% | 260 hrs | 2006-08-14 08:00 | 2007-06-29 17:00
3.1.1.1.1 | TMT site monitoring data mining | RF | 55% | 80 hrs | 2006-08-14 08:00 | 2007-06-29 17:00
3.1.1.1.1.1 | Tools in place & 1st release | RF | 100% | 40 hrs | 2006-08-14 08:00 | 2006-09-14 17:00
3.1.1.1.1.2 | Release updated data (every two months) | RF | 50% | 40 hrs | 2006-09-18 08:00 | 2007-06-29 17:00
3.1.1.1.2 | Telescope dynamic performance data | CN | 100% | 120 hrs | 2006-10-02 08:00 | 2006-11-30 17:00 | R
3.1.1.1.3 | Telescope static wavefront errors | CN | 100% | 20 hrs | 2006-10-02 08:00 | 2006-11-30 17:00 | R
3.1.1.1.4 | Sodium return vs laser format | DG | 100% | 40 hrs | 2006-11-01 08:00 | 2006-11-30 17:00 | R | 11/29: Tenaya ideas.
3.1.1.2 | Model/Tool Validation | CN | 68% | 334 hrs | 2006-08-14 08:00 | 2006-12-15 17:00 | R
3.1.1.2.1 | Agreement between Tomography Codes | DG | 100% | 40 hrs | 2006-08-14 08:00 | 2006-09-29 17:00 | R
3.1.1.2.2 | Agreement between Sky Coverage Codes | RD | 100% | 40 hrs | 2006-10-16 08:00 | 2006-11-03 17:00 |  | 12/6(RD): Agreed to use Spagna
3.1.1.2.3 | Anchor to Keck II LGS AO PSFs | CN | 25% | 40 hrs | 2006-10-02 08:00 | 2006-10-30 17:00
3.1.1.2.4 | Anchor to On-sky MGSU Experiments | RF | 100% | 10 hrs | 2006-11-10 10:40 | 2006-11-15 17:00 |  | 12/12: RF to write implications
3.1.1.2.5 | Anchor to LAO Lab Experiments | DG | 50% | 204 hrs | 2006-11-06 08:00 | 2006-12-15 17:00 |  | 4/10:DG reduced from 70 to 50%
3.1.1.3 | Throughput | AB | 50% | 32 hrs | 2006-10-02 08:00 | 2006-12-29 17:00 | R
3.1.1.4 | Background | AB | 47% | 50 hrs | 2006-10-02 08:00 | 2007-01-09 12:00 | R
3.1.1.4.1 | Document Proposal Analysis | AB | 25% | 10 hrs | 2006-10-02 08:00 | 2006-10-12 17:00
3.1.1.4.2 | Develop Background Performance Budget | AB | 50% | 40 hrs | 2006-10-02 08:00 | 2007-01-09 12:00
3.1.1.5 | Wavefront Error vs Sky Coverage | RD | 33% | 110 hrs | 2006-10-02 08:00 | 2007-01-30 17:00 | R
3.1.1.5.1 | Document WFE Budget Rev 1 | RD | 50% | 40 hrs | 2006-10-02 08:00 | 2006-12-08 17:00
3.1.1.5.2 | Document WFE Budget Rev 2 | RD | 0% | 70 hrs | 2006-12-27 08:00 | 2007-01-30 17:00 |  | 2/5: Transfer 20h to 3.1.2.2.9
3.1.1.6 | Encircled Energy vs Sky Coverage | DG | 75% | 110 hrs | 2006-10-23 08:00 | 2006-12-29 17:00 | R | 2/5: Transfer 20h to 3.1.2.2.10
3.1.1.7 | Photometric Accuracy | MB | 100% | 240 hrs | 2006-10-16 08:00 | 2007-01-26 17:00 | R
3.1.1.8 | Astrometric Accuracy | BC | 50% | 240 hrs | 2006-11-13 08:00 | 2007-06-29 17:00 | R
3.1.1.9 | Polarimetric Accuracy | MI | 75% | 40 hrs | 2007-02-05 08:00 | 2007-03-09 17:00 | R
3.1.1.10 | Companion Sensitivity | BM | 75% | 240 hrs | 2006-11-13 08:00 | 2007-01-09 10:00 | R | 12/12: RF new lead;2/5 -80h
3.1.1.11 | Observing Efficiency | DLM | 50% | 100 hrs | 2007-02-05 08:00 | 2007-03-16 17:00 | R
3.1.1.12 | Observing Uptime | EJ | 25% | 80 hrs | 2007-11-05 08:00 | 2007-12-12 17:00 | R | 11/29: Mistake on dates?
3.1.1.13 | Performance Budgets Summary |  | 0% | 160 hrs | 2007-01-31 08:00 | 2007-07-20 17:00 | R
3.1.1.13.1 | Performance Budgets Summary Ver 1 | RD | 0% | 100 hrs | 2007-01-31 08:00 | 2007-02-27 17:00
3.1.1.13.2 | Performance Budgets Summary Ver 2 | RD | 0% | 60 hrs | 2007-07-02 08:00 | 2007-07-20 17:00
3.1.1.14 | Science Products |  | 0% | 350 hrs | 2007-07-23 08:00 | 2007-10-19 17:00 | R
3.1.1.14.1 | All-In Science Simulations | CN | 0% | 160 hrs | 2007-07-23 08:00 | 2007-08-17 17:00
3.1.1.14.2 | Additional Science Characterization Results |  | 0% | 190 hrs | 2007-08-20 08:00 | 2007-10-19 17:00
3.1.1.14.2.1 | Point Source Sensitivities | AB | 0% | 30 hrs | 2007-08-20 08:00 | 2007-09-13 15:00
3.1.1.14.2.2 | PSF Uniformity & Stability | CN | 0% | 80 hrs | 2007-08-20 08:00 | 2007-09-07 17:00
3.1.1.14.2.3 | Other | RF | 0% | 80 hrs | 2007-10-01 08:00 | 2007-10-19 17:00
3.1.2 | Trade Studies | RD | 37% | 1,790 hrs | 2006-10-16 08:00 | 2007-05-25 17:00
3.1.2.1 | System Architecture Trade Studies |  | 62% | 690 hrs | 2006-10-16 08:00 | 2007-03-30 17:00
3.1.2.1.1 | MOAO & MCAO TS | DG | 100% | 80 hrs | 2006-11-13 08:00 | 2006-12-15 17:00 | R
3.1.2.1.2 | NGAO versus Keck AO upgrades TS (meeting 5) | PW | 100% | 100 hrs | 2007-02-05 08:00 | 2007-03-02 17:00 | R
3.1.2.1.3 | Adaptive Secondary Mirror option TS (m5) | PW | 25% | 40 hrs | 2007-03-05 08:00 | 2007-03-30 17:00 | R
3.1.2.1.4 | K & L-band Science TS (m5) | AB | 0% | 40 hrs | 2007-02-05 08:00 | 2007-03-02 17:00 | R
3.1.2.1.5 | Keck Interferometer Support TS (m5) | CN | 75% | 120 hrs | 2006-10-16 08:00 | 2007-03-02 17:00 | R
3.1.2.1.6 | Instrument Balance TS | SA | 0% | 10 hrs | 2006-11-13 08:00 | 2006-12-08 17:00 | R
3.1.2.1.7 | GLAO for non-NGAO Instruments TS (m5) | RF | 100% | 20 hrs | 2007-02-05 08:00 | 2007-03-02 17:00 |  | 2/28: RF estimates 30-40h total
3.1.2.1.8 | Science Instrument Re-use Cost/Benefit TS (m3) | SA | 50% | 120 hrs | 2006-11-13 08:00 | 2006-12-08 17:00 | R | 2/28: SA says change lead to AM
3.1.2.1.9 | Telescope Wavefront Errors TS | CN | 100% | 80 hrs | 2006-12-04 08:00 | 2006-12-20 17:00 | R
3.1.2.1.10 | Observing Model TS | DLM | 90% | 80 hrs | 2006-11-13 08:00 | 2007-01-12 17:00 | R
3.1.2.2 | Adaptive Optics System Trade Studies |  | 27% | 880 hrs | 2006-10-30 08:00 | 2007-05-25 17:00
3.1.2.2.1 | AO Enclosure Temperature TS (m6) | AB | 25% | 70 hrs | 2007-01-02 08:00 | 2007-04-13 17:00 | R
3.1.2.2.2 | Optical Relay TS (m6) | RD | 25% | 60 hrs | 2007-01-02 08:00 | 2007-04-13 17:00 | R
3.1.2.2.3 | Field Rotation Strategy TS (m6) | BB | 25% | 80 hrs | 2007-01-02 08:00 | 2007-04-13 17:00 | R
3.1.2.2.4 | Dichroics & Beamsplitters TS (m6) | VV | 0% | 60 hrs | 2007-01-02 08:00 | 2007-04-13 17:00 | R
3.1.2.2.5 | Rayleigh Rejection TS (m3) | SK | 75% | 40 hrs | 2006-10-30 08:00 | 2006-12-08 17:00 | R | 11/29: VV new lead;2/5: +65h
3.1.2.2.6 | LGS WFS Type TS (m4) | VV | 100% | 30 hrs | 2006-12-04 08:00 | 2007-01-19 17:00 | R
3.1.2.2.7 | LGS WFS number of subapertures TS (m4) | VV | 100% | 20 hrs | 2006-12-04 08:00 | 2007-01-19 17:00 | R
3.1.2.2.8 | Slow WFS TS (m7) | VV | 0% | 80 hrs | 2007-04-23 08:00 | 2007-05-25 17:00 | R
3.1.2.2.9 | LOWFS Architecture TS | SK | 35% | 160 hrs | 2006-12-04 08:00 | 2007-02-09 17:00 | R | 2/5: Add 20h from 3.1.1.5.2
3.1.2.2.10 | Number & Type of LOWFS TS (m4) | SK | 100% | 60 hrs | 2006-12-04 08:00 | 2007-01-26 17:00 | R | 2/5: RC new lead;+20h frm 3.1.1.6
3.1.2.2.11 | Centroid Anisoplanatism TS (m7) | SK | 0% | 40 hrs | 2007-04-23 08:00 | 2007-05-25 17:00 | R
3.1.2.2.12 | Deformable Mirror Stroke Requirement TS (m6) | RF | 0% | 50 hrs | 2007-01-02 08:00 | 2007-04-13 17:00 | R
3.1.2.2.13 | Stand-alone vs DM on T/T Stage TS (m3) | BB | 50% | 60 hrs | 2006-10-30 08:00 | 2006-12-08 17:00 | R
3.1.2.2.14 | Correcting Fast T/T with DM TS | BB | 0% | 40 hrs | 2006-10-30 08:00 | 2006-12-08 17:00 | R | 11/29: Cancelled
3.1.2.2.15 | Focus Compensation TS (m6) | SK | 0% | 30 hrs | 2007-01-22 08:00 | 2007-05-03 17:00 | R
3.1.2.3 | Laser Facility Trade Studies |  | 35% | 220 hrs | 2006-10-16 08:00 | 2007-03-05 17:00
3.1.2.3.1 | Laser Pulse Format TS (m6) | VV | 0% | 80 hrs | 2007-01-02 08:00 | 2007-01-29 17:00 | R
3.1.2.3.2 | Free Space vs Fiber TS (m7) | CN | 25% | 100 hrs | 2007-01-30 08:00 | 2007-03-05 17:00 | R
3.1.2.3.3 | LGS Asterism Geometry & Size TS (m2) | RF | 100% | 20 hrs | 2006-10-23 08:00 | 2006-10-27 17:00 | R | 11/29: Actual ~ 90 hrs
3.1.2.3.4 | Variable vs fixed LGS Asterism Cost/Benefit TS (m2) | VV | 100% | 20 hrs | 2006-10-16 08:00 | 2006-10-27 17:00 |  | 11/29: Actual ~ 50 hrs
3.1.3 | System Architecture | RD | 0% | 1,120 hrs | 2007-02-28 08:00 | 2007-12-28 17:00
3.1.3.1 | System Architecture Ver 1 | RD | 0% | 80 hrs | 2007-02-28 08:00 | 2007-04-18 17:00 | R
3.1.3.2 | System Architecture Ver 2 | RD | 0% | 60 hrs | 2007-07-23 08:00 | 2007-08-17 17:00 | R
3.1.3.3 | Functional Requirements |  | 0% | 860 hrs | 2007-04-19 08:00 | 2007-11-30 17:00
3.1.3.3.1 | AO System Functional Requirements Ver 1 | CN | 0% | 200 hrs | 2007-04-19 08:00 | 2007-05-14 10:00 | R
3.1.3.3.2 | AO System Functional Requirements Ver 2 | CN | 0% | 100 hrs | 2007-10-29 08:00 | 2007-11-30 17:00 | R
3.1.3.3.3 | Laser System Functional Requirements Ver 1 | JC | 0% | 135 hrs | 2007-04-19 08:00 | 2007-05-16 17:00 | R
3.1.3.3.4 | Laser System Functional Requirements Ver 2 | JC | 0% | 65 hrs | 2007-10-29 08:00 | 2007-11-30 17:00 | R
3.1.3.3.5 | Science Operations Functional Requirements Ver 1 | DLM | 0% | 100 hrs | 2007-04-19 08:00 | 2007-05-22 17:00 | R
3.1.3.3.6 | Science Operations Functional Requirements Ver 2 | DLM | 0% | 100 hrs | 2007-10-29 08:00 | 2007-11-30 17:00 | R
3.1.3.3.7 | Science Instruments Function Allocation Ver 1 | SA | 0% | 80 hrs | 2007-04-19 08:00 | 2007-05-14 17:00 | R
3.1.3.3.8 | Science Instruments Function Allocation Ver 2 | SA | 0% | 80 hrs | 2007-10-29 08:00 | 2007-11-14 12:00 | R
3.1.3.4 | Technology Drivers Summary | DG | 0% | 40 hrs | 2007-07-23 08:00 | 2007-07-26 14:01 | R
3.1.3.5 | Technical Risk Analysis Ver 1 | DG | 0% | 40 hrs | 2007-07-26 14:01 | 2007-08-28 14:01 | R
3.1.3.6 | Technical Risk Analysis Ver 2 | DG | 0% | 40 hrs | 2007-12-03 08:00 | 2007-12-28 17:00 | R
3.2 | AO System | DG | 0% | 1,780 hrs | 2007-03-05 08:00 | 2007-12-14 17:00
3.2.1 | AO System Architecture | DG | 0% | 240 hrs | 2007-04-19 08:00 | 2007-06-20 17:00 | R
3.2.2 | AO Enclosure | JM | 0% | 100 hrs | 2007-05-14 08:00 | 2007-08-17 17:00 | R
3.2.3 | Opto-mechanical | BB | 0% | 700 hrs | 2007-04-02 08:00 | 2007-12-14 17:00
3.2.3.1 | Field Rotation | BB | 0% | 45 hrs | 2007-04-16 08:00 | 2007-08-08 12:00 | R
3.2.3.2 | Optical Relay | BB | 0% | 60 hrs | 2007-04-16 08:00 | 2007-08-15 17:00 | R
3.2.3.3 | Optical Switchyard | BB | 0% | 50 hrs | 2007-04-16 08:00 | 2007-06-29 17:00 | R
3.2.3.4 | Optical Support Structure | BB | 0% | 45 hrs | 2007-10-01 08:00 | 2007-11-16 17:00 | R
3.2.3.5 | Wavefront Sensors | VV | 0% | 240 hrs | 2007-05-07 08:00 | 2007-12-12 17:00 | R
3.2.3.5.1 | High Order LGS Wavefront Sensors | VV | 0% | 80 hrs | 2007-05-07 08:00 | 2007-12-12 17:00
3.2.3.5.2 | High Order NGS Wavefront Sensor | VV | 0% | 40 hrs | 2007-05-07 08:00 | 2007-12-12 17:00
3.2.3.5.3 | Low Order NGS Wavefront Sensors | SK | 0% | 80 hrs | 2007-05-07 08:00 | 2007-12-12 17:00
3.2.3.5.4 | Calibration Wavefront Sensor | SK | 0% | 40 hrs | 2007-05-28 08:00 | 2007-12-12 17:00
3.2.3.6 | Wavefront Correctors | BB | 0% | 140 hrs | 2007-04-02 08:00 | 2007-11-30 17:00 | R
3.2.3.6.1 | Tip/Tilt Corrector | BB | 0% | 20 hrs | 2007-10-01 08:00 | 2007-11-30 17:00
3.2.3.6.2 | Deformable Mirror | BB | 0% | 120 hrs | 2007-04-02 08:00 | 2007-06-29 17:00
3.2.3.7 | Acquisition Cameras | AB | 0% | 40 hrs | 2007-10-01 08:00 | 2007-10-26 17:00 | R
3.2.3.7.1 | NGS Acquisition Camera | AB | 0% | 20 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.2.3.7.2 | LGS Acquisition Camera | AB | 0% | 20 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.2.3.8 | Atmospheric Dispersion Correction | SK | 0% | 20 hrs | 2007-08-20 08:00 | 2007-12-14 17:00 | R
3.2.3.9 | Alignment, Calibration, Diagnostics, Metrology and Monitoring | CN | 0% | 60 hrs | 2007-04-02 08:00 | 2007-06-29 17:00 | R
3.2.4 | Non-real-time Control | JC | 0% | 400 hrs | 2007-06-25 08:00 | 2007-11-23 17:00
3.2.4.1 | Non-RTC Software | EJ | 0% | 200 hrs | 2007-06-25 08:00 | 2007-08-31 17:00 | R
3.2.4.2 | Non-RTC Electronics | JC | 0% | 200 hrs | 2007-07-23 08:00 | 2007-11-23 17:00 | R
3.2.5 | Real-time Control | DG | 0% | 340 hrs | 2007-03-05 08:00 | 2007-08-07 17:00
3.2.5.1 | RTC Architecture Analysis and Design Study | DG | 0% | 180 hrs | 2007-03-05 08:00 | 2007-05-04 17:00 | R
3.2.5.2 | RTC Software Module Definition | EJ | 0% | 80 hrs | 2007-05-07 08:00 | 2007-08-07 17:00 | R
3.2.5.3 | RTC Hardware Module Definition | MR | 0% | 80 hrs | 2007-05-07 08:00 | 2007-08-07 17:00 | R
3.3 | Laser Facility |  | 0% | 750 hrs | 2007-03-06 08:00 | 2007-12-14 17:00
3.3.1 | Laser System Architecture | VV | 0% | 80 hrs | 2007-03-06 08:00 | 2007-05-14 17:00 | R
3.3.2 | Laser Enclosure | JM | 0% | 80 hrs | 2007-05-15 08:00 | 2007-07-12 17:00 | R
3.3.3 | Laser | VV | 0% | 100 hrs | 2007-05-15 08:00 | 2007-07-02 17:00 | R
3.3.4 | Laser Launch Facility | VV | 0% | 300 hrs | 2007-04-09 08:00 | 2007-06-01 17:00 | R
3.3.4.1 | Laser Beam Transport | CN | 0% | 60 hrs | 2007-04-09 08:00 | 2007-06-01 17:00
3.3.4.2 | Laser Pointing & Diagnostics | VV | 0% | 120 hrs | 2007-04-09 08:00 | 2007-06-01 17:00
3.3.4.3 | Laser Launch Telescope | VV | 0% | 120 hrs | 2007-04-09 08:00 | 2007-06-01 17:00
3.3.5 | Laser Safety Systems | JC | 0% | 40 hrs | 2007-10-08 08:00 | 2007-11-02 17:00 | R
3.3.5.1 | Personnel and Equipment Safety Systems | JC | 0% | 20 hrs | 2007-10-08 08:00 | 2007-11-02 17:00
3.3.5.2 | Aircraft, Satellite & Laser Traffic Control Safety Systems | JC | 0% | 20 hrs | 2007-10-08 08:00 | 2007-11-02 17:00
3.3.6 | Laser System Control | JC | 0% | 150 hrs | 2007-10-01 08:00 | 2007-12-14 17:00 | R
3.3.6.1 | Laser System Software | EJ | 0% | 80 hrs | 2007-10-01 08:00 | 2007-12-14 17:00
3.3.6.2 | Laser System Electronics | JC | 0% | 70 hrs | 2007-10-01 08:00 | 2007-12-14 17:00
3.4 | Science Operations | DLM | 0% | 670 hrs | 2007-01-02 08:00 | 2007-12-14 17:00
3.4.1 | Astronomical Observations Operations | DLM | 0% | 220 hrs | 2007-03-01 08:00 | 2007-12-14 17:00
3.4.1.1 | Pre-Observing Interfaces |  | 0% | 60 hrs | 2007-05-01 08:00 | 2007-05-30 17:00 | R
3.4.1.1.1 | AO Guide Star Interface |  | 0% | 20 hrs | 2007-05-01 08:00 | 2007-05-30 17:00
3.4.1.1.2 | Science Observations Simulation Tools |  | 0% | 40 hrs | 2007-05-01 08:00 | 2007-05-30 17:00
3.4.1.2 | Observing Interfaces |  | 0% | 80 hrs | 2007-03-01 08:00 | 2007-12-14 17:00 | R
3.4.1.2.1 | Acquisition |  | 0% | 20 hrs | 2007-03-01 08:00 | 2007-04-30 17:00
3.4.1.2.2 | Observing Sequences |  | 0% | 20 hrs | 2007-03-01 08:00 | 2007-04-30 17:00
3.4.1.2.3 | Instrument, AO & Telescope Observer Interfaces |  | 0% | 20 hrs | 2007-03-01 08:00 | 2007-04-30 17:00
3.4.1.2.4 | Science Data Quality Monitoring |  | 0% | 20 hrs | 2007-10-17 08:00 | 2007-12-14 17:00
3.4.1.3 | Post-Observing Interfaces |  | 0% | 80 hrs | 2007-10-01 08:00 | 2007-11-27 17:00 | R
3.4.1.3.1 | Generic Data Products |  | 0% | 20 hrs | 2007-10-01 08:00 | 2007-11-27 17:00
3.4.1.3.2 | Science Data Quality Assessment |  | 0% | 20 hrs | 2007-10-01 08:00 | 2007-11-27 17:00
3.4.1.3.3 | Science Data Archiving |  | 0% | 40 hrs | 2007-10-01 08:00 | 2007-11-27 17:00
3.4.2 | AO-Instrument Operations | DLM | 0% | 450 hrs | 2007-01-02 08:00 | 2007-10-26 17:00 | R
3.4.2.1 | AO-Instrument Operations Architecture | DLM | 0% | 270 hrs | 2007-01-02 08:00 | 2007-10-26 17:00
3.4.2.1.1 | AO-Instrument Observing Modes | DLM | 0% | 80 hrs | 2007-01-02 08:00 | 2007-02-02 17:00
3.4.2.1.2 | AO-Instrument Operations Support |  | 0% | 20 hrs | 2007-02-05 08:00 | 2007-05-30 17:00
3.4.2.1.3 | AO-Instrument Configuration & Setup |  | 0% | 20 hrs | 2007-07-04 08:00 | 2007-10-26 17:00
3.4.2.1.4 | AO-Instrument Calibrations |  | 0% | 20 hrs | 2007-06-04 08:00 | 2007-09-26 17:00
3.4.2.1.5 | AO-Instrument Nighttime Operation Modes |  | 0% | 20 hrs | 2007-06-04 08:00 | 2007-09-26 17:00
3.4.2.1.6 | AO-Instrument Science Acquisition & Control |  | 0% | 20 hrs | 2007-07-02 08:00 | 2007-10-24 17:00
3.4.2.1.7 | AO-Instrument Health Monitoring & Automated Recovery |  | 0% | 20 hrs | 2007-06-11 08:00 | 2007-10-03 17:00
3.4.2.1.8 | AO-Instrument Laser Traffic Control | DS | 0% | 10 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.4.2.1.9 | AO-Instrument User Interfaces |  | 0% | 40 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.4.2.1.10 | AO-Instrument Maintenance Plan |  | 0% | 20 hrs | 2007-10-01 08:00 | 2007-10-26 17:00
3.4.2.2 | AO-Instrument Operations Optimization |  | 0% | 180 hrs | 2007-03-05 08:00 | 2007-05-04 17:00 | R
3.4.2.2.1 | AO-Instrument Performance Prediction |  | 0% | 80 hrs | 2007-03-05 08:00 | 2007-04-13 17:00
3.4.2.2.2 | AO-Instrument Real-Time Optimization |  | 0% | 80 hrs | 2007-03-05 08:00 | 2007-04-13 17:00
3.4.2.2.3 | AO-Instrument Environment Monitoring |  | 0% | 20 hrs | 2007-04-16 08:00 | 2007-05-04 17:00
3.5 | Science Instruments | SA | 4% | 1,290 hrs | 2006-10-02 08:00 | 2007-11-16 17:00
3.5.1 | OSIRIS |  | 0% | 100 hrs | 2006-12-01 08:00 | 2007-03-05 14:20 | R
3.5.2 | Interferometer |  | 25% | 100 hrs | 2006-10-02 08:00 | 2007-03-30 17:00 | R
3.5.3 | OHANA |  | 0% | 40 hrs | 2007-02-01 08:00 | 2007-04-11 17:00 | R
3.5.4 | Near-IR Imager |  | 0% | 200 hrs | 2006-11-06 08:00 | 2007-05-25 17:00 | R
3.5.5 | Visible Imager |  | 0% | 200 hrs | 2007-05-14 08:00 | 2007-11-09 17:00 | R
3.5.6 | Visible IFU |  | 0% | 100 hrs | 2007-07-02 08:00 | 2007-11-16 17:00 | R
3.5.7 | Deployable Near-IR IFU |  | 0% | 500 hrs | 2007-02-01 08:00 | 2007-06-27 17:00 | R
3.5.8 | Thermal Near-IR Imager |  | 0% | 50 hrs | 2007-07-09 08:00 | 2007-11-16 17:00 | R
3.6 | System Design Manual | PW | 0% | 80 hrs | 2008-01-01 13:00 | 2008-01-18 17:00 | R
4 | Systems Engineering Management Plan (SEMP) | PW | 1% | 1,200 hrs | 2007-03-05 08:00 | 2008-02-20 10:38
4.1 | Project Plan | PW | 0% | 540 hrs | 2007-09-26 13:00 | 2007-12-20 08:34 | R
4.1.1 | WBS and Task Definition | PW | 0% | 200 hrs | 2007-09-26 13:00 | 2007-10-25 16:26
4.1.2 | Cost Estimation | PW | 0% | 220 hrs | 2007-10-25 16:26 | 2007-11-30 12:00
4.1.3 | Major Project Milestones | PW | 0% | 30 hrs | 2007-10-25 16:26 | 2007-11-05 12:00
4.1.4 | Develop Full Schedule (MS Project Plan) | PW | 0% | 90 hrs | 2007-11-30 13:00 | 2007-12-20 08:34
4.2 | Risk Assessment & Management Plan | DG | 0% | 40 hrs | 2007-09-26 13:00 | 2007-11-13 12:00 | R
4.3 | Preliminary Design Phase Plan | PW | 9% | 200 hrs | 2007-03-05 08:00 | 2008-01-24 14:09 | R
4.3.1 | Preliminary Design Phase Plan Version 1 (to Support Observatory FY08 Planning) | PW | 25% | 40 hrs | 2007-03-05 08:00 | 2007-03-30 17:00
4.3.2 | Preliminary Design Phase Plan Version 2 | PW | 0% | 80 hrs | 2007-10-25 16:26 | 2007-11-21 14:26
4.3.3 | Preliminary Design Phase Plan Final Version | PW | 0% | 80 hrs | 2008-01-03 08:34 | 2008-01-24 14:09
4.4 | Integration and Test Plans | CN | 0% | 180 hrs | 2007-10-25 16:26 | 2008-02-01 10:38 | R
4.4.1 | Subsystem Testing Plans | CN | 0% | 80 hrs | 2007-10-25 16:26 | 2008-02-01 10:38
4.4.1.1 | AO System Test Plan | CN | 0% | 20 hrs | 2007-10-25 16:26 | 2007-11-20 13:14
4.4.1.2 | Laser System Test Plan | CN | 0% | 20 hrs | 2007-11-20 13:14 | 2007-12-14 09:02
4.4.1.3 | Science Operations Test Plan | CN | 0% | 20 hrs | 2007-12-14 09:02 | 2008-01-08 14:50
4.4.1.4 | Science Instruments Test Plan | CN | 0% | 20 hrs | 2008-01-08 14:50 | 2008-02-01 10:38
4.4.2 | System Integration & Test Plans | CN | 0% | 100 hrs | 2007-10-25 16:26 | 2007-12-06 16:26
4.5 | Configuration Management Plan | JJ | 0% | 80 hrs | 2007-10-25 16:26 | 2008-01-22 11:26 | R
4.6 | Project Management Plan | PW | 0% | 80 hrs | 2007-12-20 08:34 | 2008-01-17 08:34 | R
4.7 | SEMP Document | PW | 0% | 80 hrs | 2008-02-01 10:38 | 2008-02-20 10:38 | R
| = Started | [5 empty] | R | = Work Scope Plan Required
| = Complete | [6 empty] | = Draft submitted
= Work Scope Approved
= Due within 1 month
= Overdue
= Complete
= Started
= Should have started.