NGAO Status Update and Priorities

June 6, 2007

A. Progress in May (the following priorities were identified in Peter's 4/27 email.  Status is in blue):

1. Complete the Replan

- DONE. v26 of the replan is at http://www.oir.caltech.edu/twiki_oir/bin/view.cgi/Keck/NGAO/SystemDesignPhasePlanning.  This includes a word document (KAON 481), MS Project plan and excel spreadsheet.  A tracked excel version of this plan is also posted at this location.

2. Complete the

- Science case requirements v2.  Some progress has taken place on re-casting the science requirements in terms of fundamental vs derived quantities.  Still needs considerable work.

- System requirements document v2 (including a telecon review). Significant work has taken place (the telecon review was held), but this document still needs considerable work.

- Performance budgets

- Chris posted KAON 303 Mauna Kea CN-M1, CN-M3 models mostly of historical interest.

- Brian Cameron completed KAON 480 Astrometry for NGAO.

- Matthew has posted versions of the WFE spreadsheet in the system architecture collection for Io, Kuiper Belt, Exo Jupiter, Extended Groth strip and Galactic Center.  Note from Claire: The science cases considered in the WFE spreadsheet do not map straightforwardly to the science cases that are being analyzed in the SCRD.  We need to fix this.

- Performance budgets summary.  Matthew has started.

- Trade studies.

- Don updated KAON 475 Tomography Codes Comparison & Validation with Chris' input.

- David completed KAON 476 Observing Models Trade Study.

- Chris has completed/posted KAON 482 Telescope Error Trade Study & KAON 483 Keck Interferometer Support.

- Peter has posted KAON 485 Adaptive secondary mirror trade study.  Comments received from Chris.

- Ralf has posted KAON 487 LOWFS architecture trade study results.

- Definition of candidate subsystems.  Bauman asked for a KAON # for the optical standards.

- Functional requirements v0.  Incorporated some of the optical requirements from Dekany/Bauman.

- Science instruments functional requirements v1.  No progress?

3. Other (not part of the original priorities list):

- System architecture phase has begun & the first two videocons have been held.

- The following work scope planning sheets have been approved:

- 3.1.2.1.8 Science Instrument reuse trade study

- 3.1.2.2.16 LOWFS & D-NIRIR AO & object selection trade study

- 3.1.3 System architecture

- The following work scope planning sheets have been submitted, but need revision and/or review before approval:

- 3.1.1.9 Polarimetric Accuracy (was submitted some time ago)

- 3.1.2.2.2 Optical relay trade study

- 3.1.2.3.5 Uplink compensation trade study

- 3.2.1 AO system architecture

B. Priorities for June

Items 1 and 2 are the highest priority and are in their order of priority.  Item 7 is a reporting milestone that has to be done.  The other items are roughly equal priority.

1. Complete the scheduled parts of the System Architecture phase.

- Define candidate subystems

- Subsystem performance evaluation

- Subsystem cost evaluation

- Subsystem risk analysis

- Organize candidate subsystems

- Plan July 9-13 meeting

2. Complete the Requirements Documents:

- System Requirements Document (SRD) v2.

- Science Case Requirements Document (SCRD) v2.

- Includes completion of observing scenarios

- Get McGrath engaged

- Contract for Marchis student

- Functional Requirements Document (FRD) v0.

3. Complete the Performance Budget Documents:

- Throughput and background

- Wavefront error and encircled energy

- Polarimetric (problem of no science support)

- Companion sensitivity

- Performance Budgets Summary

4. Complete the Trade Study Documents:

- Science instrument reuse

- Optical relay and field rotation strategy (DG to write with BB input)

- Rayleigh rejection (VV to post by June 12)

- Uplink compensation

- + need good progress on d-IFU & LOWFS AO & Object selection

5. Complete the scheduled Science Instruments WBS elements

- Top level instrument requirements & definitions

- Instrument suite version 1

- Instrument interfaces

- DNIRI concept development

- DNIRI AO interface issues

- SOI/LRS requirements & concept development

- SOIFU requirements review

6. Start work on Science Operations WBS elements

7. Management

- Project report #3 due June 18

- Need UC financial report through April

- Will need UC & COO financial reports through May

- SSC presentation June 20