## Sheet1
NGAO System Design Phase WBS Dictionary
Version 0.3
WBS Element |  |  |  | Name | Dictionary | Goal/ Deliverables | hours | comments
1.1 |  |  |  | SD Phase Management | Management of the System Design Phase of the NGAO project
It consists of formal project management of NGAO project, including budget and schedule, and regular reporting to the SSC and Observatory Directors. The Executive Committee (EC) has overall responsibility for the delivery of the key products of the SD Phase.
Includes labor effort for regular project meetings, activities associated with proposal preparation and fundraising, and a formal system design review (SDR).
1.2 |  |  |  | System Requirements | Development of both Science Requirements and System Requirements for NGAO.
1.3 |  |  |  | System Design | Development of the flow-down of System Requirements to Functional Requirements, definition of a design approach for the Preliminary Design phase, and assessment of performance budgets.
| 1.3.1 |  |  | Functional requirements | Develop a detailed functional requirements document for the NGAO system comprising of AO system design (including laser system), Science instruments, and Operational tools. | Serve as the technical part of the proposal to a funding agency for the <design> phase of the project.
|  | 1.3.1.1 |  | AO system requirements | A document describing charecteristics of the NGAO system based on the science requirements and results from trade studies.
|  | 1.3.1.2 |  | Laser Functional Requirements | Write a complete description of the requirements of the NGAO laser(s), the beam transport system(s), and the LLT(s). Evaluate possible configurations, current technologies available. The document will state the essential and desirable requirements based on inputs from Keck, Gemini, Palomar and Subaru. | EC will be able to make a conscious choice of Lasers, BTS, and LLT based on the document. Parts of the document will have prescriptions that can be used as RFQs. | 200
|  | 1.3.1.3 |  | Operational tools
|  | 1.3.1.4 |  | Science Instruments | Description of science intruments that will be fed by NGAO
| 1.3.2 |  |  | System Architecture
|  | 1.3.2.1 |  | Misc. but vital trade studies
|  | 1.3.2.2. |  | AO systerm architecture
|  | 1.3.2.3 |  | Optical design
|  | 1.3.2.4 |  | Mechanical design (including AO enclosure)
|  |  | 1.3.2.2.3.2.1 | HOWFS | Rayleigh rejection trade study will comprise of a model that can be used to look at the effect of Rayleigh scatter on the WFS performance. | A mathematical model of the effect of Rayleigh scatter on the WFS performance for side and center launch. | 40
|  |  | 1.3.2.2.3.2.2 | HOWFS architecture trade study: | Simulation of the NGAO system using Arroyo with a SHWFS and a pyramid WFS. | Simulated closed loop performance for PWFS and SHWFS. | 30
|  | 1.3.2.2.3.3 | 1.3.2.2.3.3.1 | LOWFS architecture | LOWFS architecture trade study: | A document that lets the EC make a decision on the type of LOWFS | 200
|  |  | 1.3.2.2.3.3.2 | # of LOWFS | ???
|  | 1.3.2.3 | 1.3.2.3.1 | Laser System architecture | Writing a document describing the command, control, and data lines to and from the laser. A prescription for diagnostics and design of a GUI for the LGS operator |  | 100
|  |  | 1.3.2.3.2 | laser enclosure | should Keck do this or this a generic document for a laser enclosure and power etc. |  | 100
|  |  | 1.3.2.3.4.1 | fiber or free space BTS | Description of currently available options for fibers and the specifications. Tests with PALAO pulse format and get data from the Subaru folks and perform tests with Keck and Gemini lasers. Detailed characterization of losses due to coupling, extra optics, will be studied. Possible modes of failure will be identified. Cost structure will be prepared comparing free space vs. fiber fed BTS. | EC will be able to make a choice of BTS based on the results of this study and the choice of laser. | 100
|  |  | 1.3.2.3.4.2 | Laser pointing and beam diagnostics | (related to 1.3.2.3.1)a. A document describing (1) architecture for independently pointing each laser beam. (2) Diagnostics | Will be part of the CoDR and will aid EC in preparing RFQs for the laser, BTS parts.
|  |  | 1.3.2.3.4.3 | LLT | ??? |  | 200
|  |  | 1.3.2.3.4.4 | Laser system control | ??? |  | 200
| 1.3.4 |  |  | Performance Budgets | Development of systems level engineering budgets for a variety of astronomical performance metrics, organized around key observing scenarios. The level of detail available to each budget will depend on the state of the art, the resources dedicated to budget generation during the SD phase, and astronomical user experience.
All performance budgets should parameterize the performance behavior vs. the corresponding Sky Coverage Fraction. (When appropriate, coverage levels of 5, 30, and 90% should be assumed).
|  | 1.3.4.1 |  | Model Assumptions | Documentation of the initial assumptions adopted for the development of all performance budgets. This includes median Cn2(h), sodium column density, and optical performance of the Keck Telescope(s).
|  | 1.3.4.2 |  | Model/Tool Validation | Execution of a series of quantitative checks on the validity of key NGAO models and development tools, as compared to results obtained from various laboratory and sky tests with existing AO systems.
Includes labor for the development/extension of new models and tools necessary for the completion of 1.3.4
|  | 1.3.4.3 |  | Throughput | Development of optical transmission budgets for each of the Science path(s), HOWFS, LOWFS(s), and Slow WFS.
|  | 1.3.4.5 |  | Wavefront Error | Development of residual wavefront error budgets for a set of key observational scenarios.
|  | 1.3.4.6 |  | Encircled Energy | Development of encircled energy budgets for a set of key observational scenarios
|  | 1.3.4.9 |  | Differential Photometric Precision | Development of a deviation budget for differential photometric precision for a set of key observational scenarios. To be manageable, this budget should assume statistical independence among the key physical sources of degradation of photometric precision.
Physical effects to be considered may include wind-induced PSF anisoplanatism, photon noise, read noise, flat-fielding variations, field-dependent optical aberrations, imperfect estimation of the anisoplanatism contribution to PSF shape, atmospheric scintillation, filter bandpass uncertainty, transparency waves in the atmosphere, imperfect atmospheric color correction, PSF sampling issues, and nonlinear detector response.
Investigation of the impact of certain terms in the budget may require detailed AO performance simulations. Calculation of other terms may be beyond the scope of the SD phase, resulting in a top-level allocation to the performance budget until otherwise updated.
|  | 1.3.4.10 |  | Differential Astrometric Precision | Development of a deviation budget for differential astrometric precision for a set of key observational scenarios. To be manageable, this budget should assume statistical independence among the key physical sources of degradation of astrometric precision.
Physical effects to be considered may include atmospheric tilt anisoplanatism, wind-induced PSF anisoplanatism, field-dependent optical aberrations, photon noise, read noise, flat-fielding variations, PSF sampling issues, telescope plate scale fluctuations, and nonlinear detector response.
Investigation of the impact of certain terms in the budget may require detailed AO performance simulations. Calculation of other terms may be beyond the scope of the SD phase, resulting in a top-level allocation to the performance budget until otherwise updated.
1.4 |  |  |  | Systems Engineering Management Plan (SEMP) | Development of the overall project plan for NGAO, with emphasis on detailed planning of the Preliminary Design phase activities.