## Revisions_Dec10
Subsystem | Item | Status | Action
RTR | Need to define functions of RTR and AO controls | No ICD draft or list | Doug Morrison planning to help define AO control part
| RTR NGS (Tip/Tilt/Astig/Focus) | Processing is documented where?
| RTR Flow down budget for weight | None now
| RTR Flow down budget for power | None now
| Latency flowdown budget to RTR | Might need more margin? Performance in poor conditions at higher Greenwood frequency
| What correction is applied to Woofer (large) DM what correction is on MEMS | Could be either ground or on axis correction (RTR can accommodate either)
| What tip tilt correction is on Woofer and Science path MEMS | Woofer tip/tilt must correct science, MEMs science leg platform is too slow
| Possible issue with waffle (ALTAIR processing??) | Doesn't appear to be an issue in other systems, actuators that have no nearby wavefront sensor | note ALTAIR DM originally not at pupil but 6.5 km, needed to extrapolate correction our over many actuator that have no nearby subapertures
| NGS modes (rotation/twist/shear) feedback to image rotator | Issue for AO control and RTR interface document
| RTR will work in its own units and modes, AO control must convert/translate | Don't think this is part of AO controls design yet. | Doug Morrison planning to help define AO control part
| More complete simulation of RTR algorithm in full up Monte Carlo simulation | Not priority for CN. DG could extend his RTR code?
LGS WFS
| Value of dither amplitude for LGS S-Calibration (On Sky) | Assume that the dithering technique is going to work | RD: LGS WFS group will study and report back.
| What correction (LTAO or ground layer) to drive large low order DM (woofer) | Not sure what RTR can or should do? How does it effect the wavefront sensor | Don Gavel will calculate the values the LGS WFS, LOWFS, Science paths would see for either scenario
| LGS dichroic should allow HeNe orange (594) to pass to wavefront sensor |  | CN: with change requirements (Consdier coating problem and need calibration light). Note you can buy small diode Lasers that produce 589 see http://www.cnilaser.com/yellow_laser589.htm
| Need to track slope errors for LGS input as well as wavefront rms error | Slope error budget doesn’t exist | RD will develop a flow down budget for this item, Group with line below,
| Compare slope error to wavefront sensor dynamic range | Current input doesn't appear to use lot of dynamic range | Group with line above
| Spot size compared to pixel pitch and charge diffusion | Some analysis/allocation done inside wavefront error budget spread sheet | RD rebalance error budget for LGSF uplink and WFS spot size. Group with action under LGS Facility uplink LGS size.
| DM-to-lenslet (20 nm rms <-> 10% subaperture) | What is the justification for this relation? is it correct? | See flowdown budget for explanation of current thinking. LGS WFS will adopt 5% of the smallest subaper. Check later with Monte Carlo simulation
| Go-to AO control interaction with spots off "cross hairs" | Unknown at this time | RD will investigate experience at LAO and Villages
| What is the correct CCD format (256^2 or 240^2) | Currently using (256^2) | RD and PW will think about 60x60 sub CCD and implications for AO design. Sean Adkins writing KAON on 256^2 CCD and related detector issues.
| Matched Filter centroid vs centroid (4x4) | Assume centroid at present | DG:please estiamte cost/complexity to add matched filter to RTC system WFS processing, leave hook for matched filter for PDR if asked.
| What is the spot elongation on WFS, what effects drive it? | Some analysis/allocation done inside wavefront error budget
| WFS calibration | Baseline LAO lab methods? Move cal. Spots across pixels?
| WFS dynamic range | Baseline 4x4 pixels per subaperture
LGS Facility
| Uplink LGS spot size of 0.9" in WFE | CN has made physical optics simulation of effect, partial results. RD needs to review flow down to WF measurement error | CN/RD review error budget. RD will make a WFE study of perfmance sensativity to uplink spot size. Neyman will document physical optics modeling
AO Relays and Bench |  |  |  | Items on hold or no action
| Implications of DM lenslet misregistration | Zemax distortion modeling between relay pupils and telescope pupil. | Don Gavel document analysis of reduced tolerance on DM-to-Lenslet registration for "go-to" AO. RD add requirement for HODM to LODM registration | Implication of optical aberrations in LGS WFS input beam | Modeling by Mark Ammons and Gavel in AO relay mini review. | No action until LGS WFS mini review completed
| What drives size of "keyhole" for NGAO? Telescope? Rotators? Pupil Illumination changes in Real Time Control (RTC)? | CN has calculated limits, needs to draft requirement. Document as KAON. | EJ will provide numbers to Motion Control and RTC teams based on NGAO FR-2, Keck Obs Report (KOR) 49 and published telescope limits. | Bandwidth implication of Woofer DM on Tip/Tilt stage. | Contacted possible vendor CILAS | No action at this time.
| Interaction between Telescope Focus, WFS focus and instrument focus for various observing modes (IF, NIR-Imager,etc.) | Informaton in configuration spreadsheet. See KAON 550, Peter has posed revision | ALL MUST READ AND COMMENT ON KAON 550! | Servo or Stepper motors | Issue decided for original Keck AO systems. Applicable to NGAO? | No Action: Distributed NGAO control software has selcted servo as being prefered, but Control system will work with either servo or stepper as needed.
| Specification for Temp, Humidity in AO enclosure and on AO Bench | No specs on AO enclosure. Specs for Temp on AO bench | Appears to be a large issue. PW will host a meeting for effected design leads and other engineers. CN will canvas the community to get input for the meeting on all issues.
| NGS wavefront sensor: modes of operation (High order, STRAP replacement). Could have 64x64, 32x32,16x16,8x8,2x2 modes. Which are needed? | Not clear if all modes are needed and for what reasons. | PW science case (what's needed and why) and RD analysis leading to NGS WFS requirements
Control software
| EJ and CN reviewd these items: none for systems engineering group | Done | Done