## Revisions_Jan27
Subsystem | Item | Status | Action
Notes on Color Code
RTC | RTC NGS WFS processing | Processing is documented where? | DonGavel: Add this processing to RTC design documents by the next design review | In progress | Not started
RTC | Latency flowdown budget allocation to RTC | Might need more margin? Performance in poor conditions at higher Greenwood frequency Gavel: Draft analysis of latency, see: latency.pdf on Sys Eng Twiki page Neyman: checked wind speed models and compared to Hilo Metrological data, KAON 503 appears consistent with available wind data: TMT site PASP, Roberts App Optics (emailed Sys Eng team 1/18/2010) | Don Gavel: document calculation of latency as KAON Rich Dekany: will add results from KAON to wavefront error budget spread sheet
| RTC Flow down budget for weight | None now CN had meeting and gave SRD/FRD starting points to Jim | Jim Bell assigned to make mass allocation budget (tree) for AO system and LGS facility (one for each).
| RTC Flow down budget for power | None now CN had meeting and gave SRD/FRD starting points to Ed | Ed Wetherell assigned to make power allocation budget (tree) for AO system and LGS facility.
LGS WFS | Need to define functions of RTC and AO controls | No ICD draft or list | Kevin Tsubota and Doug Morrison (Keck) planning to help define AO control part. ACTION to have meeting between them and RTC team. Neyman can provide ICD outline
| RTC will work in its own units and modes, AO control must convert/translate | Don't think this is part of AO controls design yet. | Kevin Tsubota and Doug Morrison (Keck) planning to help define AO control part. ACTION to have meeting between them and RTC team. Neyman can provide ICD outline
| NGS modes (rotation/twist/shear) feedback to image rotator | Issue for AO control and RTC interface document | Kevin Tsubota and Doug Morrison (Keck) planning to help define AO control part. ACTION to have meeting between them and RTC team. Neyman can provide ICD outline
| RTC compliance matrix | Reviewer comments need to be added to compliance matrix CN contacted Marco (1/27/2010), says he'll start soon | Don Gavel : add Peter's comments to compliance matrix. Neyman will add the completed compliance matrix to Database (Contour)
LGS WFS
| Value of dither amplitude for LGS S-Calibration (On Sky) | Assume that the dithering technique is going to work | Rich Dekany : LGS WFS group will study and report back.
| What correction (LTAO or ground layer) to drive large low order DM (woofer) | Not sure what RTC can or should do? How does it effect the wavefront sensor | Don Gavel will calculate the values the LGS WFS, LOWFS, Science paths would see for either scenario
| LGS dichroic should allow HeNe orange (594) to pass to wavefront sensor |  | CN: with change requirements (Consider coating problem and need calibration light). Note you can buy small diode Lasers that produce 589 see http://www.cnilaser.com/yellow_laser589.htm
| Need to track slope errors for LGS input as well as wavefront rms error and compare slope error to wavefront sensor dynamic range | Slope error budget doesn’t exist; Current input doesn't appear to use lot of dynamic range | RD will develop a flow down budget for this item | ask
| Go-to AO control interaction with spots off "cross hairs" | Unknown at this time | RD will investigate experience at LAO and Villages | ask
| What is the correct CCD format (256^2 or 240^2) | Currently using (256^2) CN: Asked SA about status of KAON still in the draft stages | RD and PW will think about 60x60 sub CCD and implications for AO design. Sean Adkins writing KAON on 256^2 CCD and related detector issues.
| Matched Filter centroid vs. centroid (4x4) | Assume centroid at present | DG:please estimate cost/complexity to add matched filter to RTC system WFS processing, leave hook for matched filter for PDR if asked.
LGS Facility
| Uplink LGS spot size of 0.9" in WFE, is this too large? | CN has made physical optics simulation of effect, partial results. RD needs to review flow down to WF measurement error | CN/RD review error budget. RD will make a WFE study of performance sensitivity to uplink spot size. Neyman will document physical optics modeling
| Spot size compared to pixel pitch and charge diffusion | Some analysis/allocation done inside wavefront error budget spread sheet | RD rebalance error budget for LGSF uplink and WFS spot size. Group with action under LGS Facility uplink LGS size.
AO Relays and Bench
| Implications of DM lenslet misregistration | Zemax distortion modeling between relay pupils and telescope pupil. | Don Gavel document analysis of reduced tolerance on DM-to-Lenslet registration for "go-to" AO. RD add requirement for HODM to LODM registration CN: Drafted KAON for based on Don's statements about go-to AO
| What drives size of "keyhole" for NGAO? Telescope? Rotators? Pupil Illumination changes in Real Time Control (RTC)? | CN has calculated limits, needs to draft requirement. Document as KAON. | CN will provide numbers to Motion Control and RTC teams based on NGAO FR-2, Keck Obs Report (KOR) 49 and published telescope limits.
| Interaction between Telescope Focus, WFS focus and instrument focus for various observing modes (IF, NIR-Imager,etc.) | Information in configuration spreadsheet. See KAON 550, Peter has posed revision CN and Doug Morrison have read. Sent comments to Peter | ALL MUST READ AND COMMENT ON KAON 550!
| Specification for Temp, Humidity in AO enclosure and on AO Bench | No specs on AO enclosure. Specs for Temp on AO bench | Appears to be a large issue. PW will host a meeting for effected design leads and other engineers. CN will canvas the community to get input for the meeting on all issues.
| NGS wavefront sensor: modes of operation (High order, STRAP replacement). Could have 64x64, 32x32,16x16,8x8,2x2 modes. Which are needed? | Not clear if all modes are needed and for what reasons. | PW science case (what's needed and why) and RD analysis leading to NGS WFS requirements

## Items_On_Hold
Subsystem | Item | Status | Action
RTC | Items on hold or no action
| What correction is applied to Woofer (large) DM what correction is on MEMS | Could be either ground or on axis correction (RTC can accommodate either) | Not an issuse, RTC is capable of either.
| What tip tilt correction is on Woofer and Science path MEMS | Woofer tip/tilt must correct science, MEMs science leg platform is too slow | Not an issuse, RTC is capable of either.
| Possible issue with waffle (ALTAIR processing??) | Doesn't appear to be an issue in other systems | Not an issure for NGAO
| More complete simulation of RTC algorithm in full up Monte Carlo simulation | Not priority for CN. DG could extend his RTC code? | No action this item on hold at present
AO Relays and Bench
| Implication of optical aberrations in LGS WFS input beam | Modeling by Mark Ammons and Gavel in AO relay mini review. | No action until LGS WFS mini review completed
| Bandwidth implication of Woofer DM on Tip/Tilt stage. | Contacted possible vendor CILAS | No action at this time.
| Servo or Stepper motors | Issue decided for original Keck AO systems. Applicable to NGAO? | No Action: Distributed NGAO control software has selcted servo as being prefered, but Control system will work with either servo or stepper as needed.
Control software
| EJ and CN reviewed these items: none for systems engineering group | Done | Done
LGS WFS
| DM-to-lenslet (20 nm rms <-> 10% subaperture) | What is the justification for this relation? is it correct? | See flowdown budget for explanation of current thinking. LGS WFS will adopt 5% of the smallest subaper. Check later with Monte Carlo simulation
| What is the spot elongation on WFS, what effects drive it? | Some analysis/allocation done inside wavefront error budget
| WFS calibration | Baseline LAO lab methods? Move cal. Spots across pixels?
| WFS dynamic range | Baseline 4x4 pixels per subaperture