## Sheet1
PBS | Name | No. Rqmts | Comments | Effort Lead | SE Member | PW | RD | CN | EJ | Due 3/31 | Due 4/14 | Due4/28 | PW 3/31 | RD 3/31 | CN 3/31 | EJ 3/31 | PW 4/14 | RD 4/14 | CN 4/14 | EJ 4/14 | PW 4/28 | RD 4/28 | CN 4/28 | EJ 4/28 | Status
0 | NGAO System | 11 | General NGAO requirements | RD | EJ |  | 11 |  | 11 | x |  |  |  | 11 |  | 11 | [8 empty] | OK
1 | AO System | [23 empty] | OK
1.1 | AO Enclosure | 16 |  | JB | PW | 16 |  |  |  |  | x | [5 empty] | 16 | [7 empty] | OK
1.1.1 | AO Bench Enclosure |  | Included in parent PBS | JB | PW | 0 | [18 empty] | OK
1.1.2 | Electronics Enclosure |  | Included in parent PBS | JB | PW | 0 | [18 empty] | OK
1.2 | Opto-Mechanical System | 5 | General Opto-Mech Requirements | DG | PW | 5 |  |  |  | x |  |  | 5 | [11 empty] | OK
1.2.1 | AO Support Structure | 0 |  | DG | PW | 0 |  |  |  | x |  |  | TBW | [11 empty] | OK
1.2.2 | Entrance Window | 0 |  | DG | PW | 0 |  |  |  | x |  |  | TBW | [11 empty] | OK
1.2.3 | Rotator | 1 |  | DG | PW | 1 |  |  |  | x |  |  | 1 | [11 empty] | OK
1.2.4 | Wide Field Relay | 17 |  | DG | PW | 17 |  |  |  | x |  |  | 17 | [11 empty] | OK
1.2.5 | Narrow Field Relay | 16 |  | DG | PW | 16 |  |  |  | x |  |  | 16 | [11 empty] | OK
| Wavefront Correctors | 24 | Need to be split up for narrow, wide, and LOWFS | DG | PW | 24 |  |  |  |  | x | [5 empty] | 24 | [7 empty] | OK
1.2.6 | Optical Switchyard | 10 |  | DG | PW | 10 |  |  |  |  | x | [5 empty] | 10 | [7 empty] | OK
1.2.7 | LGS Wavefront Sensor Assembly | 43 |  | VV | RD |  | 43 |  |  | x |  |  |  | 43 | [10 empty] | OK
1.2.8 | NGS Wavefront Sensor & TWFS | 59 |  | VV | RD |  | 59 |  |  |  | x | [6 empty] | 59 | [6 empty] | OK
1.2.9 | Low Order Wavefront Sensor Assembly | 43 |  | VV | RD |  | 43 |  |  |  |  | x | [9 empty] | 43 |  |  | OK
1.2.10 | Acquisition Camera | 19 |  | CN | PW | 19 |  | 19 |  |  |  | x | [8 empty] | 19 |  | 19 |  | OK
1.2.11 | Atmospheric Dispersion Correctors | 1 |  | DG | PW | 1 |  |  |  |  | x | [5 empty] | 1 | [7 empty] | OK
1.2.12 | Alignment | 1 |  | CN | PW | 1 |  | 1 |  |  | x | [5 empty] | 1 |  | 1 | [5 empty] | OK
1.2.13 | Calibration | 22 |  | CN | PW | 22 |  | 22 |  |  |  | x | [8 empty] | 22 |  | 22 |  | OK
1.2.14 | Diagnostics | 8 |  | CN | PW | 8 |  | 8 |  |  | x | [5 empty] | 8 |  | 8 | [5 empty] | OK
1.2.15 | Vibration Sensor (TBD) | 0 |  | ?? | PW | 0 | [18 empty] | OK
1.3 | Controls | 19 |  | EJ | PW | 19 |  |  | 19 |  |  | x | [8 empty] | 19 |  |  | 19 | OK
1.3.1 | Control Software |  | Included in parent PBS | EJ | PW | 0 |  |  | 0 | [15 empty] | OK
1.3.2 | Control Electronics |  | Included in parent PBS | EJ | PW | 0 |  |  | 0 | [15 empty] | OK
1.4 | Real-Time Controller | 55 |  | DG | EJ |  |  |  | 55 |  |  | x | [11 empty] | 55 | OK
1.4.1 | RTC Hardware / Electronics |  | Included in parent PBS | DG | EJ |  |  |  | 0 | [15 empty] | OK
1.4.2 | RTC Software |  | Included in parent PBS | DG | EJ |  |  |  | 0 | [15 empty] | OK
2 | Laser System | 58 |  | CN | EJ |  |  | 58 | 58 |  | x | [7 empty] | 58 | 58 |  |  |  |  | OK
2.1 | Laser Enclosure | 48 |  | JC | EJ |  |  |  | 48 | x | [5 empty] | 48 | [8 empty] | OK
2.2 | Laser Units | 39 |  | PW | CN | 39 |  | 39 |  | x |  |  | TBW |  | TBW | [9 empty] | OK
2.2.1 | Laser |  | Included in parent PBS | PW | CN | 0 |  | 0 | [16 empty] | OK
2.2.2 | Laser suport hardware |  | Included in parent PBS | PW | CN | 0 |  | 0 | [16 empty] | OK
2.3 | Diagnostics | 0 |  | JC | CN |  |  | 0 | [16 empty] | OK
2.4 | Opto-Mechanical System |  | Possibly included in BTO and LTA rqmts | CN | PW | 0 |  | 0 | [16 empty] | OK
2.4.1 | Optical Switchyard | 0 |  | CN | PW | 0 |  | 0 | [16 empty] | OK
2.4.2 | Laser Shutters | 0 |  | CN | PW | 0 |  | 0 | [16 empty] | OK
2.4.3 | Beam Transport Optics | 3 |  | CN | PW | 3 |  | 3 |  |  |  | x | [8 empty] | 3 |  | 3 |  | OK
2.4.4 | Launch Facility | 35 |  | JC | CN |  |  | 35 |  | x |  |  |  |  | 35 | [9 empty] | OK
2.4.5 | Beam Diagnostics | 0 |  | CN | PW | 0 |  | 0 | [16 empty] | OK
2.5 | Controls | 2 |  | EJ | CN |  |  | 2 | 2 | x |  |  |  |  | 2 | 2 | [8 empty] | OK
2.5.1 | Control SW |  |  | EJ | CN |  |  | 0 | 0 | [15 empty] | OK
2.5.2 | Control Electronics |  |  | EJ | CN |  |  | 0 | 0 | [15 empty] | OK
2.6 | Laser Safety System |  |  | JC | EJ |  |  |  | 0 | [15 empty] | OK
2.6.1 | Personnel Safety | 0 |  | JC | EJ |  |  |  | 0 | [15 empty] | OK
2.6.2 | System Safety | 0 |  | JC | EJ |  |  |  | 0 | [15 empty] | OK
2.6.3 | Aircraft Safety | 1 |  | JC | EJ |  |  |  | 1 | x | [5 empty] | 1 | [8 empty] | OK
2.6.4 | Spacecraft Safety | 0 |  | JC | EJ |  |  |  | 0 | [15 empty] | OK
3 | Science Operations Tools | 0 |  | EJ | PW | 0 |  |  | 0 | [15 empty] | OK
3.1 | Multi-System Command Sequencer |  |  | EJ | PW | 0 |  |  | 0 | [15 empty] | OK
3.2 | Pre-Observing tools |  |  | EJ | PW | 0 |  |  | 0 | [15 empty] | OK
3.3 | Observing tools |  |  | EJ | PW | 0 |  |  | 0 | [15 empty] | OK
3.4 | Post-Observing tools |  |  | EJ | PW | 0 |  |  | 0 | [15 empty] | OK
4 | Atmospheric Profiler | 27 |  | CN | RD |  | 27 | 27 |  |  |  | x | [9 empty] | 27 | 27 |  | OK
5 | Data Server | 0 |  | EJ | RD |  | 0 |  | 0 | [15 empty] | OK
5.1 | Data Server HW |  |  | EJ | RD |  | 0 |  | 0 | [15 empty] | OK
5.2 | Data Server SW |  |  | EJ | RD |  | 0 |  | 0 | [15 empty] | OK
| Total number of requirements: | 583 |  |  |  | 201 | 183 | 214 | 194 |  |  |  | 39 | 54 | 37 | 62 | 60 | 59 | 67 | 58 | 63 | 70 | 71 | 74