NGAO System Design Phase: Work Scope Planning Sheet

WBS Element Title:	Laser Launch Facility, Laser Beam Transport, Laser Pointing

and Diagnostics, Laser Launch Telescope combined with Laser System Architecture

WBS Element Number:	3.3.4, 3.3.4.1, 3.3.4.2, 3.3.4.3 & 3.3.1

Work Package Lead:	V. Velur

Work Package Participants:	B. Bauman (3 hrs allocated), J. Chin (24 hrs allocated), C. Neyman (75 hrs allocated), V. Velur (98 hrs allocated + 80 hrs for 3.3.1) – this is the allocation as per Don’s excel sheet. We may need to re-distribute the allocation. We may need Brian or/and Rene’s help for the LLT design.

# Work Scope

WBS Dictionary Entry: 	3.3.4 Based on system requirements and error budgets, develop the design concept for the systems required for delivering the laser power from the laser to the sky.  Consider potential future upgrades to laser power or changes to laser pulse format.

      - Laser Beam Transport:  Develop the design concept for the system for delivering the laser power from the laser to the launch telescope.  Consider potential future upgrades to laser power or changes to laser pulse format.

      - Laser Pointing and Diagnostics:  Develop the design concept for the system for determining and controlling the alignment and pointing of the laser beams.  Develop the system concept for regular monitoring the beam quality, laser power, and health of the laser launch system.  Consider potential future upgrades to laser power or changes to laser pulse format.

      - Laser Launch Telescope:  Develop the design concept or specify the telescope needed to launch multiple laser beacons.  Consider potential future upgrades to laser power or changes to laser pulse format.

3.3.1 Based on system requirements and the error budgets, develop a system for producing laser beacons sufficient for NGAO. An input to this process is the result of a trade study determining the field of view, number of guide star beacons, and constellations for various science-observing conditions. Produce as output: the system architecture and design/specifications for creating and projecting the guide stars, controlling the pointing, maintaining output beam quality, diagnostics, and user control.

Requirements: 	Shall be based on the FRD.

# Inputs:	laser specifications from 3.3.3

# Assumptions:

- Only SOR and LMCTI laser formats will be considered (if fiber laser format or any other pulsed laser format is also to be considered, it will probably take a lot more time).

- No uplink AO

- Spot size at the Na-layer is obtained from EBS and return #s will be worked on based on that.

- 9 LGS beacons each with the same return.

- The overall BTO transmission is 75%

Other inputs

- FRD

- Error budget spreadsheet

- Uplink AO note written by author to understand the saturation effect.

- LAO laser Twiki page

# Products:

The focus of the products will be to generate proper requirements with feasible conceptual designs to move into the next design phase.

## Review and upgrade FRD requirements from version 1.0 to 2.0.

## Provide a report on the conceptual designs for the beam transport optical systems.  The design will include a layout/block diagram as well as description of the interfaces to other subsystems within and outside of the Laser Facility.

### Laser beam relay optics as defined between the laser and the launch telescope.

### Concepts to generate nine laser beacons from a single or multiple lasers; provide losses with pros and cons of the designs.

### Concepts for pointing and steering of laser beams on sky, includes uplink tip/tilt and maintaining asterism fixed on sky.

## Launch Telescope

### Optical requirements.

### Modeling to determine feasibility as well as volume to fit into the telescope.

## List of diagnostics for BTO and LLT; laser power, beam stability, spectral profile, M2 measurements, and near and far field profiles.

# Methodology:	TBD

# Estimate of effort:

## Completion of FRD requirements version 2.0 – 40 hrs

## Beam Transport Optical System

### BTO conceptual design – 50 hrs

### Means to create nine LGS beacons (splitting one or 3 lasers into 9 beacons) – 30 hrs (developing mechanisms to create beacons).

### Pointing and Steering

#### Method to change the asterism radius and facilitate 3 roving beacons’ pointing – 40 hrs

#### Mechanism to keep LGS asterism fixed on the sky – 20 hrs

#### Method to stabilize LGS spots of WFSs – 20 hrs UTT or DTT)

## LLT conceptual design w/ some preliminary zemax model(s) – 60 hrs

## Beam stability, power, spectral profile, M^2 measurement and LLT diagnostics – 20 hrs

Total requested hrs. = 280 hrs.

# Approvals:			300 hours (reduced to 200 as per Don’s excel spreadsheet) + 80 hrs.

| Control | Name | Date |
| --- | --- | --- |
| Authored by: | Viswa Velur | 09/11/07 |
| Approved by: | WBS X.X Lead |  |
|  | NGAO EC Chair |  |