NGAO System Design Phase: Work Scope Planning Sheet

WBS Element Title:	Laser Safety Systems

WBS Element Number:	3.3.5

Work Package Lead:	Jason Chin

Work Package Participants:

# Work Scope

WBS Dictionary Entry: 	Design safety systems for the laser to protect aircraft, satellites, personnel and equipment.

      - Personnel and Equipment Safety Systems:  Identify the required safety interlock systems.  Identify means of protecting equipment from inadvertent damage during operation.  Specify the top-level safety interlock systems logic sequences and specify hardware components that provide these functions.

      - Aircraft, Satellite & Laser Traffic Control Safety Systems:  Develop the design concept or specify the safety systems needed to protect aircraft pilots (eye safety) and spacecraft from the laser beacons. All telescopes on Mauna Kea are currently required to participate in the Laser Traffic Control System.  Determine what changes will be needed to accommodate NGAO in this system.

Requirements: 	Including any additional requirements, specifications, or instructions necessary to completely but concisely define the scope of work, including corrections to the dictionary definition.  Be clear, where potential confusion might occur, about what will not be covered.

It is possible to provide top-level safety interlocks in a general sense; but without a more detail architecture for the laser, it will not be possible to provide logic sequences for the safety system.

# Inputs:	List key assumptions that are used as starting points for this WBS element.  Reference the source of the assumptions (e.g. reports, journal articles, etc.) and include a list of other NGAO WBS elements (full name and WBS #) that provide results or conclusions used as starting points for this WBS element.

The type of laser and the layout of this laser will affect the amount of work for the safety system.   A key assumption is a laser architecture with part of the system on the telescope (rotating in elevation) and part of the system on a non-gravity affected platform.  This assumption is based on discussion with Craig Denman at Starfire Optical Range and the throughput budget of the laser system.

Input Documentation:

FRD: sec8_laserIntroFRD_rev4.pdf.

K1 LGS Safety Document Requirements (draft)

K1 LGS Safety System Design Report (draft)

# Products:	List all products to be produced by this WBS element.  Examples include graphs, images, software, spreadsheets, simulation codes, and reports.  A draft table of contents for the report should be included.

1.0  Documentation

1.1  An updated version of the FRD v2.0.

1.2  A layout of the safety system with description of the individual subsystems.  The layout will include where subsystem components will be located.

1.3  A first draft on how the conceptual design will meet the possible laser architectures.

1.4  A first draft of an ICD describing possible interfaces between the subsystems.

# Methodology:	Outline your proposed procedure for meeting the goals of the WBS element.   Describe your methodology in sufficient detail that engineers and scientist with similar background can understand your plans and would be able to verify the results.

- Phase 1

Since the laser safety system is not well specified in the FRD, it is assumed this process will take some time to produce ver 2 of the FRD.  Phase I will be to complete the initial FRD ver. 1.  A good starting point is the K1 LGS Safety System Requirements.  It is reasonable to assume the top level requirements will be similar but the conceptual design will diverge depending on the architecture of the laser system. 16  hours.

- Phase II

Phase II will produce a layout of the safety system.  This will be reviewed with others in the group, along with the compliance of the requirements.  16 hours.

- Phase III

Phase III will be completion of the compliance report and initial ICD. 16 hours

Because of the limited hours, the safety system will assume a baseline laser system that will be included as a boundary condition.

# Estimate of effort:	Estimate the number of hours of work required to complete the WBS element.  Compare this estimate to the one given in the SEMP.

Total time requested: 48 hours.

# Approvals:			40 hours

| Control | Name | Date |
| --- | --- | --- |
| Authored by: | Jason Chin | 12/14/06 |
| Approved by: | WBS X.X Lead |  |
|  | NGAO EC Chair |  |