NGAO System Design Phase: Work Scope Planning Sheet

WBS Element Title:	Wavefront Sensors

WBS Element Number:	3.2.3.5

Work Package Lead:	V. Velur

Work Package Participants:	J. Bell, A. Moore, C. Neyman, V. Velur

1.   Work Scope

WBS Dictionary Entry: 	Develop a design concept for each of the required NGAO wavefront sensors:

3.2.3.5.1 High Order LGS Wavefront Sensors:  Given the functional and performance requirements, develop a design concept for the laser guide star high order wavefront sensors. Take into consideration the possible need for both open and closed loop wavefront sensing.

3.2.3.5.2 High Order NGS Wavefront Sensor:  Given the functional and performance requirements, develop a design concept for the natural guide star high order wavefront sensor(s). Take into consideration the possible need for both open and closed loop wavefront sensing.  Include consideration of ADC packaging (ADC design is covered in WBS 3.2.3.8).

3.2.3.5.3 Low Order NGS Wavefront Sensors:  Given the functional and performance requirements, develop a design concept for the low order natural guide star wavefront sensors for the purpose of determining tip/tilt and other low order modes in laser guide star observing mode. Take into consideration the possible need for both open and closed loop wavefront sensing.  Include consideration of ADC packaging (ADC design is covered in WBS 3.2.3.8).

3.2.3.5.4 Calibration Wavefront Sensor:  Given the functional and performance requirements, develop a design concept for the calibration wavefront sensor which will use natural guide star light as a truth wavefront.  This sensor will be periodically used to reset the references of the high order wavefront sensors in laser guide star mode.  Include consideration of ADC packaging (ADC design is covered in WBS 3.2.3.8).

Requirements:		Assumptions will be based upon those in the FRD.

# Inputs:

    - Optical design of the Cascaded relay.

    - FRD

      - Type of each WFS (SH/ PYR)

      - What order/ # of sub-apertures.

      - The position each sensor in the Optical Relay.

      - The FoR for each sensor

      - Positioning accuracy

      - Choice of detector(s) for each WFS (pixel size).

      - Pixel geometry specifics like guard bands, pixel geometry and spot size (for LGS with appropriate elongation) for each WFS

      - Centroiding accuracy, dynamic range, and linearity specifications from FRD for each WFS

      - The Field Stop/ Spatial filter specification

      - TT sensor specification (FoV, dynamic range, etc.)

    - SRD (specifically input of the type of sources on which tip-tilt sensor needs to work and performance margin for binaries, elongated/ asymmetric sources.

    - NGAO System Architecture Definition (KAON 499)

    - Mechanical drawing(s) w/ space constraints and packaging issues clearly stated for the of Cascaded relay.

    - Specification on pick-offs for the WFSs (including the ones shared by the TT(FA) sensors inside the d-NIRI) and rotation if necessary. (input must come from 3.2.3.11)

    - Wavefront sensor error budget spreadsheet.

3.   Products:

- Conceptual optical design(s).

- Feed into relevant sections of FRD version 2.0 (in particular update TT sensor requirements and performance based on the type of source).

- LGS pick off mechanism concepts.

- Conceptual designs and first order optical design for the LGS WFSs, TT(FA) sensors.

- First order Mechanical packaging.

- Preliminary mechanical design and 3D model (at least a cartoon showing the envelopes occupied by the WFSs).

- Acceptance and completeness of concepts and conceptual design with information on what needs to be done during the preliminary design phase.

- Update the terms in the error budget spreadsheet based on conceptual design.

- Documentation for all the above.

4.   Methodology:

- Liaise with opto-mechanical team to understand the optical and mechanical constraints.

- Based on the inputs from section 2, a first order optical design shall be worked out and shared with the rest of the WFS team for scrutiny. This will be documented and sent to the EC for further inputs.

- Conceptual designs for LGS pick offs will be worked out based on work done by the IWG, other projects like Gemini MCAO, and other MOS pick off options and Palomar Tomograph. Mechanism(s) for registering each LGS sensor to the DM will be conceptualized.

- One day meeting to understand risks and look at the acceptance of the work and design with the WFS design team.

- Documentation of the designs with design risks stated.

- Update the FRD and Error Budget Spreadsheet as and when they need updating based on how the conceptual design evolves.

5.  Estimate of effort:

First order design:

LGS WFS: 40 hrs.

NGS HOWFS: 16 hrs.

TT and TTFA sensor: 40 hrs.

TWFS/ Calibration WFS: 16 hrs.

Total: 112 hrs.

First order Mechanical packaging

LGS WFS: 8 hrs.

NGS HOWFS: 4 hrs.

TT and TTFA sensor: 16 hrs. (need to talk to the IWG)

TWFS/ Calibration WFS: 4 hrs.

Total: 32 hrs.

Preliminary mechanical design and 3D model i.e. at least a cartoon showing the envelopes occupied by the WFSs.

LGS WFS: 16 hrs.

NGS HOWFS: 12 hrs.

TT and TTFA sensor: 24 hrs. (Assuming we get enough input from the IWG)

TWFS/ Calibration WFS: 16 hrs.

(The hours above also include the time required to integrate the design into the Cascaded Relay ME design).

Total: 68 hrs.

Meeting to understand risks and look at the acceptance of the work and design with the WFS design team: (4 people x 1 day): 32 hrs.

# Documentation of the designs with design risks:  16 hrs.

6.   Approvals:		Initially allocated: 240 hours.  Estimate: 260 hrs.

| Control | Name | Date |
| --- | --- | --- |
| Authored by: | Viswa Velur | Revised on 10/12/2007 |
| Approved by: | Don Gavel | 10/12/07 |
|  | Peter Wizinowich | 10/12/07 |