## Test schedule
Palomar LGSAO test schedule | [10 empty] | v3: 04/10/06 - AB
13 - 15 April 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2006-04-11
1 | 8:00 | 10:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 2 |  | N | N
2 | 10:00 | 16:00 |  | BTO open-loop control |  |  |  |  | closed | zen | constrained by any Echelle work in East arm | 1 | 6 | AB | N | HeNe
2006-04-12
3 | 8:00 | 16:00 |  | BTO open-loop control |  |  |  |  | closed | slew | constrained by any Echelle work in East arm | 1 | 8 | AB | N | HeNe
4 | 8:00 | 13:00 |  | Install LGS dichroic |  |  |  |  | closed | lab |  | 1 | 5 | JR | N | N
5 | 20:00 | 22:00 |  | Test focus offloading script |  |  |  |  | closed | lab |  | 1 | 2 | MT | N | N
2006-04-13 |  |  |  | 19:23 | 20:11 | 13:43 | 5:24 | 6:12
4 | 8:00 | 12:00 |  | Install AO system |  |  |  |  | closed | zen |  | 1 | 4 |  | N | N
6 | 12:00 | 13:00 |  | Test HOWFS gating |  |  |  |  | closed | zen |  | 1 | 1 | MT | N | N
5 | 13:00 | 16:00 |  | BTO open-loop control |  |  |  |  | closed | slew | constrained by any Echelle work in East arm | 1 | 3 | AB | N | HeNe
7 | 16:00 | 18:00 |  | Test BTO FSM with Na laser |  |  |  |  | closed | zen |  | 1 | 2 | CS | N | Na
| 18:00 | 20:00 |  | dinner | [8 empty] | 2
8 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing & closed-loop performance. | 1 | 0.5 | AB | N | N
9 | 20:30 | 22:30 |  | LLT boresighting |  |  |  |  | NGS | V=3 |  | 1 | 2 | HP | N | N
10 | 22:30 | 23:30 |  | LLT image quality |  |  |  |  | NGS | V=3 | measure NGS image quality using Pulnix | 1 | 1 | RD | N | N
11 | 23:30 | 24:30 |  | LGS characterization |  |  |  |  | LGS | zen | project laser at zenith, measure photometry. | 1 | 1 | AB | Y | Na
12 | 24:30 | 27:30 |  | Close HO loop on laser |  |  |  |  | LGS | zen |  | 1 | 3 | MT | Y | Na
13 | 27:30 | 29:30 |  | contingency | [7 empty] | 1 | 2
2006-04-14 |  |  |  | 19:24 | 20:12 | 13:47 | 5:23 | 6:11
14 | 12:00 | 14:00 |  | Measure UTT FSM noise |  |  |  |  | closed |  |  | 2 | 2 | MT | N | N
15 | 14:00 | 16:00 |  | contingency |  |  |  |  | closed |  |  | 1 | 2
16 | 16:00 | 18:00 |  | Demo off-zenith laser projection |  |  |  |  | closed | track |  | 1 | 2 | AB | N | Na
| 18:00 | 20:00 |  | dinner | [8 empty] | 2
16 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing & closed-loop performance. | 1 | 0.5 | AB | N | N
17 | 20:30 | 22:30 |  | LOWFS focus test |  |  |  |  | NGS | binary |  | 1 | 2 | JR | N | N
18 | 22:30 | 26:30 |  | LGS off-zenith acquisition |  |  |  |  | LGS | V=8 |  | 1 | 4 | AB | Y | Na
19 | 26:30 | 27:30 |  | HOWFS-laser TT correlation |  |  |  |  | LGS | V=8 |  | 1 | 1 | MB | Y | Na
20 | 27:30 | 29:30 |  | contingency | [7 empty] | 1 | 2
2006-04-15 |  |  |  | 19:25 | 20:13 | 13:51 | 5:22 | 6:10
21 | 12:00 | 18:00 |  | contingency |  |  |  |  | closed |  |  | 2 | 6 |  | N | N
| 18:00 | 20:00 |  | dinner | [8 empty] | 2
22 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing & closed-loop performance. | 1 | 0.5 | AB | N | N
23 | 20:30 | 22:00 |  | LOWFS bandwidth vs. star mag. |  |  |  |  | NGS | 8-17 |  | 2 | 1.5 | MT | Y | N
24 | 22:00 | 28:00 |  | LGS science demo observations |  |  |  |  | LGS | V=15 |  | 1 | 6 | AB | Y | Na
25 | 28:00 | 29:00 |  | Flatmap test |  |  |  |  | NGS | stars |  | 3 | 1 | CS | N | N
26 | 29:00 | 29:30 |  | Acquisition camera sensitivity |  |  |  |  | NGS | stars |  | 2 | 0.5 | AB | Y | N