## Test schedule
Palomar LGSAO test schedule | [10 empty] | v2.0: 11/15/05 - AB
14 - 18 Nov 2005 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2005-11-14 |  |  |  | 16:54 | 17:42 | 3:51 | 5:22 | 6:10
1 | 8:00 | 9:00 |  | Install LLT |  |  |  |  | closed | zenith | Install LLT at prime focus | 1 | 1 | RT | N | HeNe
2 | 9:00 | 13:00 |  | BTO servo test |  |  |  |  | closed | zenith | Test LLT servo system, including Q3 | 1 | 4 | JA | N | HeNe
2005-11-15 |  |  |  | 16:54 | 17:42 | 3:55 | 5:23 | 6:11
1 | 9:00 | 16:00 |  | Install Lantronix switch |  |  |  |  | closed |  |  | 1 | 7 | MT | N | N
2 | 9:00 | 16:00 |  | Test UTT control |  |  |  |  | closed |  |  | 1 | 7 | MT | N | N
3 | 9:00 | 16:00 |  | Test HOWFS gating |  |  |  |  | closed |  |  | 1 | 7 | MT | N | N
4 | 9:00 | 16:00 |  | New pupil registration technique |  |  |  |  | closed |  |  | 1 | 7 | MT | N | N
5 | 9:00 | 14:00 |  | BTO open-loop pointing |  |  |  |  | closed | slew | Measure BTO mirror positions over HA, Dec. telescope moves | 2 | 5 | AB | N | HeNe
6 | 14:00 | 14:30 |  | Daily status meeting |  |  |  |  | closed |  |  | 1 | 0.5 | AB | N | N
7 | 15:00 | 16:00 |  | Prepare BTO for Na laser |  |  |  |  | closed | zenith | Install Q1,Q2,Q3 beamsplitters, align Na laser to polar axis | 1 | 1 | AB | N | N
| 16:00 | 17:30 |  | Dinner | [8 empty] | 1.5
8 | 17:30 | 19:00 |  | BTO servo test (Na laser) |  |  |  |  | closed | zenith | Align laser to BTO, test BTO servo with Na laser | 1 | 1.5 | AB | N | Y
9 | 19:00 | 21:00 |  | LLT collimation |  |  |  |  | NGS | V=3 | Optimize LLT collimation on a bright star | 1 | 2 | HP | N | N
10 | 21:00 | 25:00 |  | LLT beam quality |  |  |  |  | LGS | zenith | Optimize laser footprint on LLT primary, test masks | 1 | 4 | RD | N | Y
11 | 25:00 | 26:00 |  | LGS photometry |  |  |  |  | LGS | zenith | Measure LGS and photometric calibrator | 2 | 1 | AB | Y | Y
12 | 26:00 | 28:00 |  | Uplink Tip/tilt |  |  |  |  | LGS | zenith | Close uplink tip/tilt loop on laser | 2 | 2 | MT | Y | Y
13 | 28:00 | 29:30 |  | LOWFS focus sensitivity |  |  |  |  | NGS | V=6 | Measure LOWFS response to known focus change. | 3 | 1.5 | JR | N | N
2005-11-16 |  |  |  | 16:53 | 17:41 | 3:58 | 5:23 | 6:12
1 | 12:00 | 16:00 |  | BTO transmission vs. polarization |  |  |  |  | closed | zenith | Use polarized HeNe to test BTO transmission of lin. Polarized light | 2 | 4 | CS | N | HeNe
2 | 14:00 | 14:30 |  | Daily status meeting |  |  |  |  | closed |  |  | 1 | 0.5 | AB | N | N
| 16:00 | 17:30 |  | Dinner | [8 empty] | 1.5
3 | 17:30 | 18:30 |  | Q3 interlock response time |  |  |  |  | closed | zenith | Test Q3 interlock, measure response time | 1 | 1 | VV | N | Y
4 | 18:30 | 19:30 |  | BTO off-zenith pointing demo. |  |  |  |  | closed | slew | Demo open-loop BTO alignment, Q3 safety interlock, BTO servo. | 1 | 1 | AB | N | Y
2005-11-17 |  |  |  | 16:52 | 17:41 | 4:02 | 5:24 | 6:13
1 |  |  |  | TBD
2005-11-18 |  |  |  | 16:52 | 17:41 | 4:06 | 5:25 | 6:14
1 |  |  |  | TBD