## Test schedule
Palomar NGSAO test schedule | [10 empty] | v4.0: 01/10/06 - MT
11 - 12 Jan 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Eng. Test plan Required | Lead
|  |  |  | suns | 12° | LST | 12° | sunr
2006-01-11 |  |  |  | 17:07 | 17:56 | 7:39 | 5:54 | 6:44
1 | 8:00 | 12:00 |  | Install AO and racks |  |  |  |  | closed |  |  | 1 | 4 | N | RT
2 | 36:00 | 37:30 |  | Perform AO checkout minus tunning centroids |  |  |  |  | close | stim/tel |  | 1 | 1.5 | N | JH
3 | 10:00 | 11:00 |  | Install MM4000, cable and test w/ rot |  |  |  |  | close |  |  | 1 | 1 | N | VV
4 | 11:00 | 13:00 |  | Install MGSU racks and cable MGSU |  |  |  |  | close |  | does not include HOWFS | 1 | 2 | N | MB
5 | 37:30 | 39:30 |  | Balance telescope |  |  |  |  | close |  | LOCK MGSU | 1 | 2 | N | RT
6 | 13:00 | 14:00 |  | Test data acq. With 3 MGSU cameras |  |  |  |  | close |  |  | 1 | 1 | Y-E | MB
7 | 39:30 | 40:30 |  | Verify MGSU pupil registration |  |  |  |  | close | stim | coarse check | 1 | 1 | Y-W | RF
8 | 40:30 | 41:00 |  | Test acquistion of asterism |  |  |  |  | close | stim |  | 2 | 0.5 | Y-W | RF
9 | 41:00 | 42:00 |  | Test HOWFS data recording through MGSU |  |  |  |  | close | stim |  | 1 | 1 | Y-E | MB
| 16:00 | 17:30 |  | dinner | [6 empty] | AB arrives ~19:00 |  | 1.5
10 | 42:00 | 42:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | Check of seeing & AO perf. | 1 | 0.5 | N | MT
11 | 42:30 | 47:30 |  | MGSU data gathering open loop 4 cameras |  |  |  |  | NGS | aster. |  | 1 | 5 | Y-E | RF
12 | 47:30 | 48:30 |  | Pupil registration improvements |  |  |  |  | NGS | V=? |  | 2 | 1 | Y-W | MT
12 | 48:30 | 49:30 |  | Check NGS acqusiiton range |  |  |  |  | NGS | V=? |  | 2 | 1 | Y-E | MT
13 | 49:30 | 51:30 |  | Test flatmaps |  |  |  |  | NGS | V=? |  | 3 | 2 | Y-W | CS
14 | 51:30 | 53:30 |  | MGSU data gathering 2 open loop 4 cameras? |  |  |  |  | NGS | aster. |  | 3 | 2 | Y-E | RF
2006-01-12 |  |  |  | 17:07 | 17:57 | 7:43 | 5:54 | 6:44
1 | 11:00 | 12:00 |  | Test taking data with HOWFS sync'ed to MGSU |  |  |  |  | close | stim |  | 1 | 1 | Y-W | MT
2 | 12:00 | 15:00 |  | Collect wavefront data on all 4 cameras |  |  |  |  | closed | stim | -10 acq left | 2 | 3 | Y-W | JR
|  |  |  | Measure relative pupil registration and orientation |  |  |  |  | close | stim | 3 act, waffle
3 | 15:00 | 16:00 |  | Measure transfer curves |  |  |  |  | closed | stim |  | 2 | 1 | Y-W | CS
4 | 16:00 | 17:00 |  | read noise measurements |  |  |  |  | close |  |  | 3 | 1 | Y-W | ??
| 16:00 | 17:30 |  | dinner | [8 empty] | 1.5
5 | 17:30 | 18:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | Check of seeing & AO perf. | 1 | 0.5 | N | MT
6 | 18:00 | 23:00 |  | MGSU data gathering TT and/or HO closed loop |  |  |  |  | NGS | aster. |  | 1 | 5 | Y-E | RF
7 | 23:00 | 24:00 |  | Pupil Registration improvments |  |  |  |  | NGS | V=? |  | 2 | 1 | Y-W | MT
8 | 24:00 | 26:00 |  | Test flatmaps |  |  |  |  | NGS | V=? |  | 2 | 2 | Y-W | CS
9 | 26:00 | 29:00 |  | MGSU data gathering TT and HO closed loop |  |  |  |  | NGS | aster. |  | 3 | 3 | Y-E | RF
Passive tests
1 |  |  |  | Test RADAR |  |  |  |  | NGS | any | run RADAR and ASCAM in throughout night. | 2 |  | Y-? | AB
2 |  |  |  | LGS software |  |  |  |  | NGS | V=10 | Test functionality of new LGS GUIs | 2 |  | Y-? | AB
Other possible tests
1 |  |  |  | AO performance with 1.5m pupil |  |  |  |  | NGS | V=6 |  | 3 | 3 | Y-? | AB
2 |  |  |  | LOWFS acquisition |  |  |  |  | NGS | V=8 | Test LOWFS acquisition using new IDL software. | 4 | 1 | Y-? | AB
3 |  |  |  | Install LOWFS | [5 empty] | stim |  | 3 | 3 | N | CS
2 | 12:00 | 14:00 |  | Diagnose system crashes |  |  |  |  | closed | stim | Point telescope around dome in daytime. | 2 | 2 | N | CS
Legend
Experiment plan Y = required, N = not required, -E plan exists -W Plan needs to be written