## Test schedule
Palomar NGSAO test schedule | [10 empty] | v2.1: 02/06/05 - AB
9 - 11 Feb 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2006-02-09 |  |  |  | 17:34 | 18:21 | 9:34 | 5:42 | 6:29
1 | 10:00 | 13:00 |  | Install MGSU electronics |  |  |  |  | closed |  | In parallel, install LOWFS baffle, test with white light (JR). | 1 | 3 | VV
2 | 13:00 | 16:00 |  | MGSU checkout |  |  |  |  | closed |  |  | 2 | 3 | VV
| 16:00 | 18:00 |  | dinner | [8 empty] | 2
3 | 18:00 | 18:30 |  | AO checkout |  |  |  |  | NGS | V=8 |  | 1 | 0.5 | AB | N | N
4 | 18:30 | 22:30 |  | Safety system testing |  |  |  |  | NGS | V=8 | Monitor air traffic with ASCAM, IRCAM, and RADAR | 2 | 4 | AM | N | N
5 | 18:30 | 23:30 |  | MGSU experiments |  |  |  |  | NGS | aster |  | 1 | 5 | RD | N | N
6 | 23:30 | 25:30 |  | LOWFS pupil stability |  |  |  |  | NGS | calib | Pupil centration vs. telescope attitude (could be done in daytime if avail.) | 2 | 2 | JR | N | N
7 | 25:30 | 28:30 |  | LOWFS performance |  |  |  |  | NGS | calib | Record TT performance for V=8,10,12,14,16,17,18 | 3 | 3 | AB | Y | N
8 | 28:30 | 29:30 |  | contingency | [8 empty] | 1
2006-02-10 |  |  |  | 17:34 | 18:22 | 9:38 | 5:41 | 6:29
1 | 288:00 | 289:00 |  | Install new DAC card |  |  |  |  | closed |  |  | 2 | 1 | SG
2 | 289:00 | 292:00 |  | BTO open-loop alignment |  |  |  |  | closed |  | In parallel, LOWFS pupil alignment (JR) | 2 | 3 | JA
| 292:00 | 294:00 |  | dinner | [8 empty] | 2
3 | 294:00 | 294:30 |  | AO checkout |  |  |  |  | NGS | V=8 |  | 1 | 0.5 | AB | N | N
4 | 294:30 | 298:30 |  | Safety system testing |  |  |  |  | NGS | V=8 | Monitor air traffic with ASCAM, IRCAM, and RADAR | 2 | 4 | AM | N | N
5 | 294:30 | 299:30 |  | MGSU experiments |  |  |  |  | NGS | aster |  | 1 | 5 | RD | N | N
6 | 299:30 | 301:00 |  | Dual NGS mode checkout |  |  |  |  | NGS | V=8 |  | 2 | 1.5 | JR | N | N
7 | 301:00 | 304:30 |  | LOWFS performance 2 |  |  |  |  | NGS | ? | Record focus, TT performance in dual NGS | 2 | 3.5 | AB | N | N
8 | 304:30 | 305:30 |  | contingency | [8 empty] | 1
2006-02-11 |  |  |  | 17:35 | 18:23 | 9:41 | 5:40 | 6:28
1 | 13:00 | 16:00 |  | BTO open-loop alignment |  |  |  |  | closed |  |  |  | 3
| 16:00 | 18:00 |  | dinner | [8 empty] | 2
2 | 18:00 | 18:30 |  | AO checkout |  |  |  |  | NGS | V=8 |  | 1 | 0.5 | AB | N | N
3 | 18:30 | 22:30 |  | Safety system testing |  |  |  |  | NGS | V=8 | Monitor air traffic with ASCAM, IRCAM, and RADAR | 2 | 4 | AM | N | N
4 | 18:30 | 23:30 |  | MGSU experiments |  |  |  |  | NGS | aster |  | 1 | 5 | RD | N | N
5 | 23:30 | 29:30 |  | contingency | [8 empty] | 6
Backup tests
1 |  |  |  | Diagnose system crashes |  |  |  |  | closed | stim | Point telescope around dome in daytime. | 2 | 3 | MT | N | N
2 |  |  |  | Science |  |  |  |  | NGS |  | Joe Carson (good seeing only), Matthew Britton isoplanatism experiment? | 2 | 4 | AB | N | N