## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.0: 07/07/06 - AB
11 - 13 July 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2006-07-11 |  |  |  | 20:08 | 21:03 | 19:33 | 4:43 | 5:38
1 | 8:00 | 12:00 |  | Install HOWFS chopper |  |  |  |  | closed | zen | Install and test chopper, delay line, cover. | 1 | 4 | JR | N | N
2 | 12:00 | 16:00 |  | Test BTO off-zenith alignment |  |  |  |  | closed | slew | Test BTO 2-D lookup tables | 3 | 4 |  | N
| 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
3 | 16:00 | 17:00 |  | Acquisition camera calibration |  |  |  |  | cloased | dark | Take acquisition camera darks, flats | 2 | 1 | AB | N | N
4 | 17:00 | 18:00 |  | contingency |  |  |  |  | closed |  |  | 1 | 1 |  | N
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
5 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
6 | 21:00 | 22:30 |  | LLT boresighting |  |  |  |  | NGS | V=3 | Boresigh to 200". Check repeatability vs. elevation. | 1 | 1.5 | HP | N | N
7 | 22:30 | 24:00 |  | LLT image quality |  |  |  |  | NGS | V=3 | Collimate LLT, measure image quality. | 1 | 1.5 | RD | N | N
8 | 24:00 | 25:00 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
9 | 25:00 | 26:30 |  | Laser wavelength control |  |  |  |  | LGS | zen | Test laser wavelength control | 2 | 1.5 | EK | Y | Na
10 | 26:30 | 27:30 |  | LGS off-zenith acquisition |  |  |  |  | LGS | V=10 | Demonstrate improved acquisition procedures. | 1 | 1 | AB | N | Na
11 | 27:30 | 28:45 |  | HOWFS chopper |  |  |  |  | LGS | V=10 | Test HOWFS chopper functionality | 2 | 1.25 | JR | N | Na
2006-07-12 |  |  |  | 20:07 | 21:02 | 19:37 | 4:44 | 5:39
12 | 12:00 | 18:00 |  | contingency | [8 empty] | 6
| 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
| 18:00 | 19:00 |  | dinner | [6 empty] | note earlier dinner time |  | 1
13 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
14 | 21:00 | 22:00 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
15 | 22:00 | 24:00 |  | Bright star performance |  |  |  |  | LGS | V=10 | Optimize HO loop performance with bright NGS. | 1 | 2 | MT | Y | Na
16 | 24:00 | 26:00 |  | Faint star performance |  |  |  |  | LGS | V=16 | Acquire V=14,15,16,17 stars. | 2 | 2 | MT | Y | Na
17 | 26:00 | 27:00 |  | LGS isoplanatic angle |  |  |  |  | LGS | V=12 | Measure LGS and NGS isoplanatic angles | 1 | 1 | AB | Y | Na
18 | 27:00 | 28:45 |  | LGS science demo observations |  |  |  |  | LGS | V=15 | Image 2 science targets. | 1 | 1.75 | AB | Y | Na
2006-07-13 |  |  |  | 20:07 | 21:39 | 19:41 | 4:45 | 5:39
19 | 12:00 | 18:00 |  | contingency |  |  |  |  | closed |  |  | 2 | 6 |  | N | N
| 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
| 18:00 | 19:00 |  | dinner | [6 empty] | note earlier dinner time |  | 1
20 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
21 | 21:00 | 22:00 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
22 | 22:00 | 23:30 |  | Performance vs zenith angle |  |  |  |  | LGS | V=10 |  | 1 | 1.5 | AB | Y | Na
23 | 23:30 | 27:30 |  | LGS science demo observations |  |  |  |  | LGS | V=15 | Image 2-3 science targets. | 1 | 4 | AB | Y | Na
Backup experiments
1 | 0:00 | 1:00 |  | Flatmap test |  |  |  |  | NGS | stars |  | 3 | 1 | CS | N | N
2 | 1:00 | 2:00 |  | Acquisition camera sensitivity |  |  |  |  | NGS | stars |  | 3 | 1 | AB | Y | N
3 | 2:00 | 3:30 |  | Demo LOWFS dithering |  |  |  |  | NGS | V=8 | Demonstrate dithering on PHARO. | 2 | 1.5 | MT | N | N
4 | 3:30 | 4:30 |  | HOWFS-laser TT correlation |  |  |  |  | LGS | V=8 |  | 3 | 1 | MB | Y | Na
5 | 4:30 | 5:30 |  | LGS magnitude vs. B field |  |  |  |  | LGS | V=8 | Measure LGS magnitude at ~15 points over sky | 3 | 1 | AB | Y | Na