## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.1: 07/10/06 - AB
11 - 13 July 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2006-07-11 |  |  |  | 20:08 | 21:03 | 19:33 | 4:43 | 5:38
| day |  |  | Switch HOWFS dichroic spot |  |  |  |  | closed | zen | Switch to Na dichroic spot | 1 | 2 | JR
| day |  |  | Debug new software build |  |  |  |  | closed | slew | Reproduce DM loop crash, DM "hot" actuators. | 2 | 2 | MT
| day |  |  | Install HOWFS chopper |  |  |  |  | closed | zen | Install and test chopper, delay line, cover. | 2 | 4 | JR
| day |  |  | Test BTO |  |  |  |  | closed | zen | Test BTO alignment to Q3 and software changes. | 3 | 2 | JA
| day |  |  | Acquisition camera calibration |  |  |  |  | cloased | dark | Take acquisition camera darks, flats | 3 | 1 | AB
| 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
1 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
2 | 21:00 | 22:30 |  | LLT boresighting |  |  |  |  | NGS | V=3 | Boresigh to 200". Check repeatability vs. elevation. | 1 | 1.5 | HP | N | N
3 | 22:30 | 24:00 |  | LLT image quality |  |  |  |  | NGS | V=3 | Collimate LLT, measure image quality. | 1 | 1.5 | RD | N | N
4 | 24:00 | 24:30 |  | Final BTO alignment |  |  |  |  | NGS | V=3 | Realign red laser to LLT | 1 | 0.5 | RD | N | N
5 | 24:30 | 25:30 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
6 | 25:30 | 26:30 |  | LGS off-zenith acquisition |  |  |  |  | LGS | V=10 | Demonstrate improved acquisition procedures. | 1 | 1 | AB | N | Na
7 | 26:30 | 27:45 |  | HOWFS chopper |  |  |  |  | LGS | V=10 | Test HOWFS chopper functionality | 2 | 1.25 | JR | N | Na
2006-07-12 |  |  |  | 20:07 | 21:02 | 19:37 | 4:44 | 5:39
| day |  |  | etalon control | [6 empty] | Install and test etalon thermal and/or tillt control. |  | 8
| day |  |  | Test BTO off-zenith control | [6 empty] | Test new 2-D lookup tables. |  | 2
| 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
1 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
2 | 21:00 | 22:00 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
3 | 22:00 | 23:00 |  | Laser wavelength control |  |  |  |  | LGS | zen | Test laser wavelength control | 2 | 1 | EK | Y | Na
4 | 23:00 | 25:00 |  | Bright star performance |  |  |  |  | LGS | V=10 | Optimize HO loop performance with bright NGS. | 1 | 2 | MT | Y | Na
5 | 25:00 | 27:00 |  | Faint star performance |  |  |  |  | LGS | V=16 | Acquire V=14,15,16,17 stars. | 2 | 2 | MT | Y | Na
6 | 27:00 | 28:00 |  | LGS isoplanatic angle |  |  |  |  | LGS | V=12 | Measure LGS and NGS isoplanatic angles | 1 | 1 | AB | Y | Na
7 | 28:00 | 29:45 |  | LGS science demo observations |  |  |  |  | LGS | V=15 | Image 2 science targets. | 1 | 1.75 | AB | Y | Na
2006-07-13 |  |  |  | 20:07 | 21:39 | 19:41 | 4:45 | 5:39
| day |  |  | contingency |  |  |  |  | closed |  |  | 2 | 6 |  | N | N
| 14:00 | 14:30 |  | Status meeting | [8 empty] | 0.5
| 18:00 | 19:00 |  | dinner | [8 empty] | 1
1 | 20:30 | 21:00 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
2 | 21:00 | 22:00 |  | LGS acquisition |  |  |  |  | LGS | zen | Project laser at zenith, focus, measure photometry. | 1 | 1 | AB | Y | Na
3 | 22:00 | 23:30 |  | Performance vs zenith angle |  |  |  |  | LGS | V=10 |  | 1 | 1.5 | AB | Y | Na
4 | 23:30 | 27:30 |  | LGS science demo observations |  |  |  |  | LGS | V=15 | Image 2-3 science targets. | 1 | 4 | AB | Y | Na
Backup experiments
1 | 0:00 | 1:00 |  | Flatmap test |  |  |  |  | NGS | stars |  | 3 | 1 | CS | N | N
2 | 1:00 | 2:00 |  | Acquisition camera sensitivity |  |  |  |  | NGS | stars |  | 3 | 1 | AB | Y | N
3 | 2:00 | 3:30 |  | Demo LOWFS dithering |  |  |  |  | NGS | V=8 | Demonstrate dithering on PHARO. | 2 | 1.5 | MT | N | N
4 | 3:30 | 4:30 |  | HOWFS-laser TT correlation |  |  |  |  | LGS | V=8 |  | 3 | 1 | MB | Y | Na
5 | 4:30 | 5:30 |  | LGS magnitude vs. B field |  |  |  |  | LGS | V=8 | Measure LGS magnitude at ~15 points over sky | 3 | 1 | AB | Y | Na