## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.0: 10/02/06 - AB
11 - 13 October 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2006-10-10
1 | 9:00 | 17:00 |  | Install diag. bench on LLT |  |  |  |  | N/A | N/A |  | 1 | 8 | AM | N | N
2 | 9:00 | 17:00 |  | Install PF diag. power supplies |  |  |  |  | N/A | N/A |  | 1 | 8 | HP | N | N
3 | 9:00 | 17:00 |  | Final laser checkout & alignment |  |  |  |  | N/A | N/A | Reinstall optical isolator, align laser, test data logging | 1 | 8 | VV | N | N
2006-10-11 |  |  |  | 18:27 | 19:14 | 1:36 | 5:55 | 6:42
1 | 8:00 | 10:00 |  | Install LLT |  |  |  |  | closed | zen |  | 1 | 2 | RT | N | N
2 | 10:00 | 14:00 |  | LLT diagnostics bench checkout |  |  |  |  | closed | zen | Need CSFL off. | 1 | 4 | TT | N | 660
3 | 10:00 | 14:00 |  | BTO software checkout |  |  |  |  | closed | zen | Need CSFL off. | 2 | 4 | JA | N | 660
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
4 | 14:30 | 16:00 |  | LLT alignment to 660nm laser |  |  |  |  | closed | zen | Need CSFL off. | 3 | 1.5 | AB | N | 660
5 | 16:00 | 17:30 |  | Test-fire laser in dome |  |  |  |  | closed | zen | Check alignment, test diagnostics. | 3 | 1.5 | AB | N | Y
| 17:30 | 18:30 |  | dinner | [8 empty] | 1
6 | 19:00 | 19:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
7 | 19:30 | 21:00 |  | LLT boresighting/image quality |  |  |  |  | NGS | V=3 | LLT boresighting & image quality with new camera optics | 3 | 1.5 | HP | N | N
8 | 21:00 | 22:30 |  | LGS characterization |  |  |  |  | LGS | zen | Project laser at zenith, focus, optimize & photometry. | 1 | 1.5 | MT | Y | Y
9 | 22:30 | 24:00 |  | LGS performance (bright star) |  |  |  |  | LGS | V=10 |  | 1 | 1.5 | MT | Y | Y
10 | 24:00 | 27:00 |  | LGS performance (faint star) |  |  |  |  | LGS | V=16 | V=14.0, 15.0, 16.0, 17.0 | 2 | 3 | AB | Y | Y
11 | 27:00 | 30:00 |  | LGS science observations |  |  |  |  | LGS | V=15 | Observe 2 targets. | 2 | 3 | AB | N | Y
2006-10-12 |  |  |  | 18:26 | 19:12 | 1:40 | 5:56 | 6:42
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
1 | 14:30 | 17:30 |  | contingency | [8 empty] | 3
| 17:30 | 18:30 |  | dinner | [6 empty] | 1 |  | 1
2 | 19:00 | 19:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
3 | 19:30 | 21:30 |  | LOWFS performance |  |  |  |  | NGS | V=16 | continue LOWFS performance test from Sep. run | 2 | 2 | JR | Y | N
4 | 21:30 | 22:30 |  | LGS characterization |  |  |  |  | LGS | zen | Project laser at zenith, focus, optimize & photometry. | 1 | 1 | MT | Y | Y
5 | 22:30 | 23:00 |  | Impact of Raleigh on LOWFS |  |  |  |  | LGS | zen |  | 2 | 0.5 | JR | Y | Y
6 | 23:00 | 24:00 |  | UTT performance |  |  |  |  | LGS | zen | determine what is limiting UTT performance | 2 | 1 | AB | Y | Y
7 | 24:00 | 25:30 |  | LGS performance (bright star) |  |  |  |  | LGS | V=10 |  | 1 | 1.5 | MT | Y | Y
8 | 25:30 | 30:00 |  | LGS science observations |  |  |  |  | LGS | V=15 | Observe 2 targets. | 2 | 4.5 | AB | N | Y
2006-10-13 |  |  |  | 18:25 | 19:11 | 1:43 | 5:57 | 6:43
| 14:00 | 14:30 |  | status and safety meeting | [8 empty] | 0.5
1 | 14:30 | 17:30 |  | contingency | [8 empty] | 3
| 17:30 | 18:30 |  | dinner | [8 empty] | 1
2 | 19:00 | 19:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
3 | 19:30 | 20:30 |  | LGS characterization |  |  |  |  | LGS | zen | Project laser at zenith, focus, optimize & photometry. | 1 | 1 | MT | Y | Y
4 | 20:30 | 22:30 |  | LGS isoplanatism |  |  |  |  | LGS | V=15 | Compare LGS and NGS isoplanatic angles | 3 | 2 | AB | Y | Y
5 | 22:30 | 24:30 |  | LGS performance vs. airmass |  |  |  |  | LGS | V=10 | el=90,60,45 | 2 | 2 | AB | Y | Y
6 | 24:30 | 28:30 |  | LGS science observations |  |  |  |  | LGS | V=15 | Observe 3 targets. | 2 | 4 | AB | N | Y
Background experiments
1 |  |  |  | Aircraft camera sensitivity |  |  |  |  | NGS |  |  | 2 |  | JC | N | N
2 |  |  |  | Laser diagnostics benches |  |  |  |  | LGS |  |  | 2 |  | AM | N | Y
Backup experiments
1 | 0:00 | 2:00 |  | LOWFS focus performance |  |  |  |  | NGS | V=17 |  | 2 | 2 | JR | N | N
2 | 2:00 | 3:00 |  | Acquisition camera sensitivity |  |  |  |  | NGS | stars |  | 3 | 1 | AB | Y | N
3 | 3:00 | 4:00 |  | HOWFS-laser TT correlation |  |  |  |  | LGS | V=8 |  | 3 | 1 | MB | Y | Y
4 | 4:00 | 5:30 |  | LGS magnitude vs. B field |  |  |  |  | LGS | V=8 | Measure LGS magnitude at ~15 points over sky | 3 | 1.5 | AB | Y | Y
5 | 5:30 | 7:30 |  | Faint NGS performance |  |  |  |  | NGS | V=14 |  | 2 | 2 | CS | N | N