## Test schedule
Palomar LGSAO test schedule | [10 empty] | v1.2: 10/10/06 - AB
11 - 13 October 2006 (local)
Test # | PDT start | PDT end | stat | Test Name |  |  |  |  | Obs mode | Target | Description / Prerequisites | Priority | Duration | Lead | Clear sky | Laser
|  |  |  | suns | 12° | LST | 12° | sunr
2006-10-12 |  |  |  | 18:26 | 19:12 | 1:40 | 5:56 | 6:42
1 | 17:45 | 19:00 |  | Align LLT diagnostics bench |  |  |  |  | closed | zen |  |  | 1.25 | AM
2 | 18:45 | 19:00 |  | Align laser to BTO |  |  |  |  | closed | zen | confirm alignment in Coude lab | 1 | 0.25 | AB | N | Y
3 | 19:00 | 20:00 |  | Test-fire laser in dome |  |  |  |  | closed | zen | test-fire laser, check focus, signal on LLT diag. cameras | 1 | 1 | AB | N | Y
4 | 20:00 | 20:30 |  | AO Checkout |  |  |  |  | NGS | V=8 | check seeing, NGS performance. | 3 | 0.5 | AB | N | N
5 | 20:30 | 21:30 |  | LGS characterization |  |  |  |  | LGS | zen | Project laser at zenith, focus, optimize & photometry. | 1 | 1 | MT | Y | Y
6 | 21:30 | 23:00 |  | LGS performance (bright star) |  |  |  |  | LGS | V=10 | Acquire star, optimize loops. | 1 | 1.5 | MT | Y | Y
7 | 23:00 | 26:00 |  | LGS performance (faint star) |  |  |  |  | LGS | V=16 | V=14.0, 15.0, 16.0, 17.0 | 2 | 3 | JR | Y | Y
8 | 26:00 | 29:00 |  | LGS science observations |  |  |  |  | LGS | V=15 | Observe 3 targets. | 2 | 3 | AB | N | Y
9 | 29:00 | 29:30 |  | Impact of Raleigh on LOWFS |  |  |  |  | LGS | zen |  | 2 | 0.5 | JR | Y | Y
Background experiments
1 |  |  |  | Aircraft camera sensitivity |  |  |  |  | NGS |  |  | 2 |  | JC | N | N
2 |  |  |  | Laser diagnostics benches |  |  |  |  | LGS |  |  | 2 |  | AM | N | Y
Backup experiments
1 | 0:00 | 1:00 |  | UTT performance |  |  |  |  | LGS | zen | determine what is limiting UTT performance | 2 | 1 | AB | Y | Y
2 | 1:00 | 3:00 |  | LLT flexure test |  |  |  |  | LGS | zen | determine what is limiting UTT performance | 2 | 2 | AB | Y | Y
3 | 3:00 | 5:00 |  | LOWFS performance |  |  |  |  | NGS | V=16 | continue LOWFS performance test from Sep. run | 2 | 2 | JR | Y | N
4 | 5:00 | 7:00 |  | NGS low-light tests |  |  |  |  | NGS | V=15 |  | 3 | 2 | CS | N | N
5 | 7:00 | 9:00 |  | LOWFS focus performance |  |  |  |  | NGS | V=17 |  | 2 | 2 | JR | N | N
6 | 9:00 | 10:00 |  | Acquisition camera sensitivity |  |  |  |  | NGS | stars |  | 3 | 1 | AB | Y | N
7 | 10:00 | 11:00 |  | HOWFS-laser TT correlation |  |  |  |  | LGS | V=8 |  | 3 | 1 | MB | Y | Y
8 | 11:00 | 12:30 |  | LGS magnitude vs. B field |  |  |  |  | LGS | V=8 | Measure LGS magnitude at ~15 points over sky | 3 | 1.5 | AB | Y | Y
9 | 12:30 | 14:30 |  | Faint NGS performance |  |  |  |  | NGS | V=14 |  | 2 | 2 | CS | N | N
10 | 14:30 | 16:30 |  | LOWFS deflection vs. elev. |  |  |  |  | WL |  |  | 2 | 2 | CS | N | N
11 | 16:30 | 18:30 |  | Field-dependent focus on LOWFS |  |  |  |  | WL |  |  | 2 | 2 | CS | N | N
12 | 18:30 | 20:30 |  | LGS isoplanatism |  |  |  |  | LGS | V=15 | Compare LGS and NGS isoplanatic angles | 3 | 2 | AB | Y | Y
13 | 20:30 | 22:30 |  | LGS performance vs. airmass |  |  |  |  | LGS | V=10 | el=90,60,45 | 2 | 2 | AB | Y | Y
14 | 22:30 | 26:30 |  | LGS science observations |  |  |  |  | LGS | V=15 | Observe 3 targets. | 2 | 4 | AB | N | Y